## Sheet1
Hull Comedy Festival Launch
Hull 2017 Contact | Martin Atkinson
martin.atkinson@hull2017.co.uk
(0)7721754934
Artist Contact
Date | 2017-09-26
Doors | 19:00
Start | 20:00
Venue | Hull City Hall
Capacity | 777
Format | Cabaret downstairs using all of upstairs (Gallery and Blacony)
Production | HPSS
Lead Production Contact | HPSS:
Hull 2017: Melissa McVeigh
LX | Provided by HPSS
Followspot
PA | Provided by HPSS
AV | Provided by HPSS
Mics | Provided by HPSS
Bars | Open from 19:00
Bottle bars open with drinks deals and plastic bottles allowed in
Bars open throughout
Schedule
8:00 | Get In from HPSS
9:00 | Danielle Harris arrives
10:00 | Setup/decorate tables | Danielle / Matt / Vols
3 Vols arrive to assist
11:00
12:00 | Lucy Cousins EM in the building
13:00
14:00
15:00 | Riders in dressing room
16:00 | Scanners at City Hall
17:00
17:30 | Vols arrive for Box Office
18:00
18:30 | Comedians Arrive
19:00 | Doors
20:00 | Jayde Adams
20:10 | Sean Walsh
20:30 | Jayde Adams
20:35 | Russell Kane
21:05 | INTERVAL
21:05 | Interval
21:20 | Jayde Adams
21:30 | Jack Gleadow
21:40 | Jayde Adams
21:45 | Joe Lycett
22:15 | Show down
Staff
EM
Hull CoC | Danielle Harris: danniharrisx@googlemail.com 07594212377
City Hall | Lucy Cousins
Vols | 10am-2pm: 3 vols. 5:30pm - 10:30pm: 6 vols
Security | Provided by City Hall
First Aid | Provided by City Hall
Access | Wheelchair users can be seated around tables. A couple of the tables will be raised in order to accommodate wheelchair users
Deliveries | Large steel signs with lights delivered Monday 25 Sep
Large Beach chairs for the front of City Hall
Empty bottles from House of Townend for table lights
Already delivered
Tablecloths
Lights
Pens
Other Activity | DJ
Post Show Activity | Nothing planned from Hull 2017 side
Rider | Diet Coke
Coca Cola
Bottled Water
Coffee/Tea making facilities
Chocolate
Bananas
Beer: Becks
Roles and Responsibilities
Room Dressing
Stage/LX/SND/AV | Bart HPSS
Stage Management | Danielle Harris | (0)7594212377
Front of House Management | Lucy Cousins | HCH
Volunteer Management | Danielle Harris | (0)7594212377
Artist Liaison | Martin Atkinson / Richard McCann / Jed Salisbury | (0)7910199980
Rider | Danielle Harris | (0)7594212377
Press / PR Guest List | Alix Johnson | (0)7980 652898
Comedy Festival Guest List | Gary Jennison
Filming / Photography | David Watson | (0)7479395233
Buses | Matthew Johnson | (0)7921 019760