|  |  |
| --- | --- |
| Mon 12th June | Anna visiting HHC and BJL Photographer booked 1pm to capture close of patterns |
| Tue 13th June |  |
| Wed 14th June | 10am Partners meetingCraig in Hull to show graphics team exhibition space |
| Thu 15th June |  |
| Fri 16th June |  |
| Sat 17th June |  |
| Sun 18th June |  |
| Mon 19th June | Start install* Floorplates
* Wall fixings
 |
| Tue 20th June | Craig to provide lawnmower dimensions and positioning  |
| Wed 21st June | Appoint Assistant Curator – Hannah Lupkin Assemble / Sophie Thompskin (SM) |
| Thu 22nd June | Bracket mower to wall and remove / Laura to lead:Ethan/Nina/Helen Fitchett (ref Tim)/Katy Morris/Rachel Buffy |
| Fri 23rd June | Lawnmower text tracing. Lawnmower back up. Tree of Ties install too. |
| Sat 24th June | Lawnmower text tracing |
| Sun 25th June |  |
| Mon 26th June |  |
| Tue 27th June | Shelving install |
| Wed 28th June | Start final stages of install* Graphics install
* Lighting install
* Book move
* Move objects on to shelves
* Lawnmower
* Tree of Ties
* Shelf install, book install, power install, light install.
 |
| Thu 29th June | Objects installed x 1 accurate volunteer for inventorying until Mon 3rd working with Anna. Trolleys and Perspex glass installed.  |
| Fri 30th June |  |
| Sat 1st July |  |
| Sun 2nd July | Fishing wire install |
| Mon 3rd July | TestingHandover from Anna and Hull 2017 to UoH exhibition team of how to operate exhibition.Confirm capacity with UofH fire safety officer |
| Tue 4th July | 11am TBC Press Preview6.30-8.30pm Private View |