## Sheet1
What were the major challenges of Made in Hull?
Respondents | Response Date | Response Text | Categories
1 | 2017-01-25 13:35 | Having shifted the fundamental tenets of the piece fro the Ferrensway our schedule was pushed back to the extent that there was no margin for error - and even then challenges for the artist in review cycling their work in time for staging. Credit to all for keeping calm and collected
2 | 2017-01-23 15:46 | the production was very short and got crushed into development from the artists side which is not ideal
3 | 2017-01-23 13:56 | The budget, the fact that we had to pull it altogether over Christmas when a lot of people were on holiday, even those in the office.
4 | 2017-01-23 12:10 | Explaining what was going to happen and when
5 | 2017-01-20 14:42 | To achieve the above. Not having a clearly outlined project plan re timetable, roles, milestones etc Feeling later on in the project that honest discussion about content wasnt always encouraged / feeling somewhat 'managed'
6 | 2017-01-16 11:12 | Creatively overlooking so many projects on a short timeline for delivery, budget constraints as ever,