## CHRONO
LOGG
Heralding |  | Abreviations | GH - Gareth Hughes | AJ - Alix Johnson
Production Specification v7 |  |  | CM - Chris Marr | LS - Laura Smith
20.02.17 | GDH
|  |  |  | TITLE | WHAT | FROM TEXT/REFERENCE FROM CDS | OWNER | LOCATION | CONSIDERATIONS | Crate numbers
FEB | Pre-production | 2017-02-13 | HERALDING | Pre-production | Design brief sent out | NA | GH
|  | 2017-02-20 | HERALDING | Pre-production | Design brief responses received | NA | GH
|  | W/C 27 Feb | HERALDING | Pre-production | Identify freelancers for the Institute | NA | GH/Production Company
MARCH | Pre-production | 2017-03-13 | HERALDING | Pre-production | Institute of Rediscovered Wonders brand delivered and costume items | NA | CM
|  | 14 - 31 March | HERALDING | Pre-production | Branding of flatbed, costumes and accessories | NA | Production Company
|  | 27 Marc h | HERALDING | Pre-Production | 5x normal crates delivered to Hull | NA | Production Company | Staples |  | 5
|  | 2017-03-28 |  | Pre-Production | Crates moved to 'tunnel' location - photo shoot - and back to Staples | NA | Production Company | Tunnel Location TBC
APRIL | Prologue | 2017-04-03 | HERALDING | Discovery of crates | Social media and press | "cache of over 500 wooden boxes" - the Indiana jones moment | AJ | Digital | Can this be done CGI? Images to be grainy
| Prologue | 2017-04-12 | HERALDING | Institute of Rediscovered Wonders | Moving some crates to secret location | IfRW flat bed at this point? | Production Company | From LOCATION TBC To Staples | Need starting location and route
| Prologue | W/C 17 April | HERALDING | Secret Location | Digital | web cam with interventions | Production Company | Staples | 10 x crates | 10
APRIL | Phase two | 15/04/2017 - 16/04/2017 | HERALDING | The Seven Alleys | Public intervention | Delivery of 1000's of scrolls to Preston Road area - invitation to come to the carriage at Freedom Centre on 20/4 - 4pm - 8pm 21/4 - 4pm - 8pm 22/04 10 - 4pm 23/04 10 - 4pm | LS | Freedom Centre
| Phase two | 20/04/2017 - 03/05/2017 | HERALDING | The Seven Alleys | Public intervention | On the morning of Thursday 20th April, staff and visitors arriving at Freedom Centre, discover a large number of crates has appeared outside 5. They are marked with the legend, ‘To East Hull with love, from the 7 Alleys’. Over the coming days it emanates sound – harmonic drones, hushed voices speaking urgently, as if from a faraway place, of the Land of Green Ginger and the 7 Alleys, and the ricochet of horses’ hooves galloping. | Production Company | Preston Road, outside Freedom Centre | Overnight install, 5x Standard sized crate - with special animation | 5
|  | 20/04/2017 - 03/05/2017 | The Seven Alleys | The Seven Alleys | Box office - ticketing | Land of Green Ginger carriage installed in Freedom Centre courtyard as ‘box office’ for invitation respondents to sign up for show; staffed by 2 x local (Preston Road) actors and 2 x 2017 box office team in rotation; open 4-8pm on 20th & 21st, 10am-5pm on 22nd; security required throughout. | ???? | Preston Road, outside Freedom Centre | Extra budget for carriage and box office team to be confirmed.
MAY | Phase two | Nobody Nose
|  | 2017-05-08 | HERALDING | Nobody Nose | Social media and press | On or around 8th May the Institute discover a number of crates are marked ‘GNGG Bransholme’. A set of architectural drawings and interior fittings in one of the crates encourage them to believe that they contain the instructions for a built environment. They contact Louise Smith at Northpoint shopping centre who agrees to accept the crates and to have the environment built in Unit 5, which is currently unused but has been cleaned out.s | AJ | N/a | Photo opp??? | 5
|  | CHECKING DIARY WITH NORTH POINT - end w/C 15 May | DURATION WED - SUN | Nobody Nose | Public intervention | A stack of crates in pyramid form appears in Northpoint Shopping Centre - for a few days the crates become a fixture, also providing weary shoppers a place to sit. Crates with smells - Ginger. The crates marked for Bransholme, gradually disappear as the Nose Shrine is built. The crates are then sent to Northpoint (on the w/c 15th or w/c 22nd – weeks 1 and 2 of the build proper) where they sit in the atrium for a period of time. (It’s important that they are there for both weekdays and a weekend.) Over the course of a day they slowly disappear as they are taken into the shop to be ‘assembled’. (Actually they are just removed and taken away.) | Production Company | North Point Shopping Centre Atrium | Install in centre of North Point - stack of boxes - pyramid - 5 crates - animated | 5
|  | 2017-05-22 | HERALDING | Nobody Nose | Social media and press | In an apparently separate occurrence, on or around Monday 22nd May (or it could be later), the Institute discover a strange gold object in one of the crates. It looks important but they are not sure what it is. An article in Hull Daily Mail prints a full size picture of the gold object and appeals to the public to identify it. What could it be? Does anyone know? The photograph is a close up of the object held safely by a pair of conservator’s gloved hands. People are directed to the Institute webpage if they have any suggestions. (The bigger the picture the better – obviously ;-) A member of the public contacts the Institute via the website and says that they believe the object printed in the Hull Daily Mail was the Gold Nose of Green Ginger, dug up when the foundations of the Bransholme estate were being laid, 50 years ago. This tallies with the GNGG on the side of the crates already sent to Bransholme. Further evidence is found in the crates in Northpoint. Meanwhile, Louise Smith has suggested to the Institute that the people that ran Nose to See You pop-up shop last year should be responsible for what people are now calling ‘Nobody Nose’. | AJ/Production Company | Staples | Photo opp???
|  | 2017-06-17 | HERALDING | Nobody Nose | Public intervention | On Saturday 17th June, the Gold Nose of Green Ginger is handed over the Institute. They arrive in a horse and carriage. The Nose Guardian goes to meet them. The Gold Nose of Green Ginger is brought into Nobody Nose… | ???? | North Point Shopping Centre Atrium |  | 1
MAY - JULY | Phase two | w/c 22 May | Photo shoot - taken 18th May | The Common Guild | Social media and press | Margaret finds a crate opening finds tabards… - in a shed |  |  | 1x crate | 1
JULY - SEPTEMBER | Phase three
JULY |  | 1st and 2nd July | HERALDING | Re-Rediffusion | Social media and press | Crate found at the old rediffusion site - discovered - with sucker in - cables into the ground (leading to Pickering Park?) - by Rerediffussion | AJ/Production Company | Beverley Road - site | Fake dig site
JULY |  | 10 - 16 July | Re-Rediffusion | Re-Rediffusion | Social media and press | Recruiting of Veros to collect voices (???) | Aswarm | ??
JULY |  | 24 - 30 July | Re-Rediffusion | Re-Rediffusion | Social media and press | Recruiting of Veros to collect voices (???) | Aswarm | ??
SEPT |  | From 4th Sept | HERALDING | Re-Rediffusion | Social media and press | ….end points the cables are found at Pickering Park, by the Institute of Rediscovery of Wonders (with sucker attachments) | AJ/Production Company | Pickering Park
SEPT |  | 7 Sept - 17Sept | Re-Rediffusion | Re-Rediffusion | Public intervention | Re-rediffusion 'Veros' go out (where?) to collect voices in the community | Aswarm | Hessle Road
OCTOBER |  | 23 Sept - 1 Oct | Re-Rediffusion | Re-Rediffusion | Public intervention | Pickering park - voice swarm | Aswarm | Pickering Park | Voice vessels come in crates - and are left for people to sit on etc as part the sound installation
OCTOBER | Phase three | 2017-09-01 | Little Town | Little Town | Public intervention | 20x crates to be used in the building of the Little Town | Production Company/Set designer
| Phase three | 2017-09-25 | HERALDING | Little Town | Public intervention | Crate will house a small set up for the little people looking through windows - shutters open to reveal the little world in a crate | Production Company
|  | 09/10/2017 - 21/10/1027 | Little Town
NOVEMBER | Phase three | w/c 6 Nov - 11/12 Nov - SHOW | HERALDING | Macnas | Media opportunity | Giant Crate (shipping container sized) - parade opener - with Macnas parade puppet to emerge - from the Small People from Little town - a facimilie of the Little People crate but BIG - in the lead up to the Parade you can see the little people getting BIG | Production Company | To the start of the parade route | Outside the crate has the route map and parade information

## Flatbed schedule
FLAT BED AND INSTITUTE REQUIREMENTS
|  | TIMES | HOURS | Institution of Rediscovered Wonders - delivery arm
14/03/2017 - 28 March | Flat bed delivered to Staples (or location for skin branding) | AM | N/A | N/A
2017-03-28 | Move 5x LoGG Crates to secret location - photo shoot - then return to Staples | 10:00 - 15:00 | 5 | 2
2017-04-20 | Move live crates from Staples to Freedom Centre x5 | 03:00 - 07:00 | 4 | 2
2017-05-03 | Move live crates from Freedom Centre to Staples x5 | 03:00 - 07:00 | 4 | 2
TBC - MAY | Move 12 amount of crates to North Point Shopping Centre | 00:00 - 07:00 | 7 | 4
TBC - MAY - 4 times | Remove 3 amount of crates from North Point Shopping Centre - gradually deminshing | 05:00 - 07:00 | 2 | 2
15 May??? | 1x crates moved to xxx alotment for photo shoot and removed same day | 06:00 - 08:00 | 2 | 2
2017-06-17 | Move one (Golden Nose crate) to green nr North Point Shopping Centre Car park - the Wilko one | 06:00 - 08:00 | 2 | 2
22/23 July | ???? Burny crates

## ACTIONS FROM FEB CDS
ACTIONS FROM CDS - FEB
LEAD
Who's arranging the secret tunnel location for the first photo shoot? | EB
Location for the 12 April HDM reporter to 'witness' the crates being moved? | Alix
Follow up with Yorkshire Water - sorry forgot the guys name - use for crate store | EB
Do we want crates at the Periplum site? | LY
Can we check with Tony about using the shop unit and Freedom Centre Plaza from 20 April to 3 May? | GH/LY
Can we check diary for North Point atrium - May | LY
Check size and load in access for North Point | GH
Location for Margaret's and 10 crates photo shoot | CM
Frame the bonfire conversation - Lone Twin | KF

## IfRW Spec
IfRW Specification
4x costume | Overalls branded | Brand TBC
1x Flat bed with tail lift | Branded | Hire/Partnership MKM
4x hard hats | Branded
4x pairs of gloves | Safety gloves
TIMESCALES | See Chrono Schedule and Flatbed Schedule

## PROD DESIGN AREAS
PRODUCTION DESIGN

## CRATES SPEC
LOGG CRATES
Standard Crates
MATERIAL | Wood esk, need to look like old packing crates - See 'mood presentations' for finish examples
Need to be robust enough to be sat on, stood on, stacked, dropped, left out in the public.
FIXINGS | Handles to load by two people at height
Can be moved by Pallet truck
SIZE | 140cm x 140cm x 210cm
Can be transported on a flatbed truck
Branding | Needs to be able to be replaced (plated or board)
ANIMATION | Can produce recorded sound to a level that can be heard in a crowded shopping centre, can vibrate, can produce smoke - remotely activated and battery operated
Timescales | 5x Special crates delivered by 27 March to central storage location - Hull - (see production schedule for more detail)
9x Special crates delivered on 20th (early) April to Preston Road, Freedom Centre
15 x normal crates delivered mid-May to North Point Shopping Centre
1x normal crate delivered to location in Long Hill, Hull - 18th May
15x special crates delivered in various locations in Hessle Road - Mid-July
20x standard crates delivered to Charlton Bingo Hall, Hull - 1 September
1x special crate delivered to Charlton Bingon Hall - 25 September
1x Giant crate delivered to Hull City Centre - 6 November

## Periplum notes
21.02.17
TITLE OF EVENT | The 7 Alleys
PRODUCTION | Periplum | Artistic content and production
TECHNICAL | TG Events | Site and production management
EVENT | Hull2017 | Event management
VENUE | East Park | Gardens to the front of the Pavilion, behind the Pavilion, the road way leading to the Pavilion, the Arena to the left of the roadway
SPECIFICATION | Show is a promenade piece involving set action performance pieces around the Pavilion and Arena of East Park, the show will involve stage effects (lighting and sound) plus small scale pyrotechnics (stage material and hand held) | The show will involve a community cast working with professional performers
AUDIENCE PROFILE | Audiences will be invited from the Preston Road area and East Park area via a mail out. Audiences will be asked to claim up to 7 tickets for the show. The show is intended for a family audience.
TICKETED | Yes
Dates | Saturday 29th April | IN
| Sunday 30th April | IN
| Monday 1st May | BUILD / PM Rehearsals
| Tuesday 2nd May | BUILD / PM Rehearsals
| Wednesday 3rd May | SHOW
| Thursday 4th May | SHOW
| Friday 5th May | SHOW
| Saturday 6th May | SHOW
| Sunday 7th May | OUT
| Monday 8th May | OUT
Capacity | 1500 per night
Times | DOORS - 21:00
SHOW - 21:30 - 22:30
CLEAR - 23:00
Duration | 1hr

## Sheet2
Periplum audience booking flow chart