## Guidance
ABOUT PROJECT RISK REGISTERS
Every project we have any responsibility for delivering should have a project risk register - it is a useful tool to ensure important things have been considered and safeguards put in place wherever possible. It is a live planning & monitoring tool, to be updated and added to regularly.
The Executive Producer owns the risk register, with Producer, Assistant Producer and third parties contributing.
Third parties cannot own the risk register: there are some risks we cannot devolve (most obviously the risk that the third party will not deliver), and we remain responsible even for those we can. Completing a risk register will help ensure nothing falls between the gaps of in-house and third party delivery. You may want to ask the third party to develop the risk register, add your own risks, then keep it up-to-date via your usual communications & updates with them.
The project team should review the risk register regularly. You might, for example, review all the residual red risks at one meeting, the ambers at the next etc…
If a risk needs to be escalated, it should be raised via an Executive Producer at Tuesday Programming.
NB Project risk registers are different to event risk assessments. Event risk assessments are about preventing harm during a fixed period of activity, and completed by the Tech & Ops team. Project risk registers are about foreseeing and preventing obstacles to your project.
HOW TO COMPLETE A PROJECT RISK REGISTER
Every risk (what could happen) has a potential impact (what that might cause) and requires mitigating action (what you're doing to prevent it). The risk owner is the person responsible for the risk and mitigating action.
Risks are scored twice: Firstly the inherent score, before mitigation, to help you see where to focus your energies; Then the residual score, as it currently stands, to help you see where your mitigating actions haven't worked or are insufficient.
Finally, when the risk is no longer a risk to the project, set its status to Closed, so you can filter it out of future reviews.
Hover over a column heading on the risk register for help on what to put in that column.
PROMPTS
Here is a non-exhaustive list of risks you might consider for your project, with prompts for potential impact & mitigating action:
RISK | POTENTIAL IMPACT | MITIGATING ACTION
Artistic content not representative of vision | Reputational damage with creative team, stakeholders and general public | eg well managed creative process, management of expectations
Cost forecasts inaccurate | Project goes over budget or other project costs must be reduced or removed | eg thorough planning, reliable quotes
Decision making causes delays | Additional pressure on internal project team | eg foreseeing required decisions (greenlight, on sale etc) and scheduling them in
Failure to attract audience/participants | Failure to achieve project objectives and Hull 2017 KPIs | eg full MarComms plan
Failure to contract all parties effectively | Inability to deliver project | eg early involvement of Legal team, use of standard templates
Failure to engage creative team | Inability to deliver project
Failure to pay creative team, suppliers etc in timely manner | Relationships sour; third parties unable to deliver due to cashflow issues | eg early setting up of suppliers on system, correct use of POs, management of expectations
Failure to secure appropriate venue | Inability to deliver project | eg early discussions, backup plans
Failure to secure necessary permissions or licences | Inability to delivery project | eg early involvement of Tech & Ops team, appropriate slot at ESAG
Ill-defined scope: full extent of the project not explored and understood | Additional pressure on internal project team; core components of project put at risk | eg thorough planning
Insufficient budget | Inability to deliver project | eg accurate forecasts, management of expectations
Insufficient insurance cover | Significant legal, financial and reputational repercussions for all partners | eg early involvement of Legal team
Lack of project management | Project gets out of control; ineffective working causes unnecessary pressure; no agreement on roles, responsibilities, outcomes etc | eg roles & responsibilities defined, regular use of Artifax inc milestones, regular project team updates and/or meetings
Partners fail to support/deliver as expected | Additional pressure on internal project team | eg clear roles & responsibilities, contracts where required, regular updates
Procurement process causes delays | Additional pressure on internal project team; failure to procure correctly causes legal issues | eg early involvement of Tech & Ops team
Project documentation not managed centrally | Files get out of sync; people work on different versions simultaneously; no 'single source of truth' | eg agreement on shared document space with controlled access
Reduced availability of project team (due to capacity, leave, turnover, illness etc) | Additional pressure on internal project team | eg reliable documentation to allow others to pick up in someone's absence, advance planning for capacity & planned leave
Scope creep: uncontrolled additions to the project | Additional pressure on internal project team; core components of project put at risk | eg clearly defined project scope, clear process for managing change
Staff or partners inexperienced | Work takes longer than necessary; threats or opportunities are missed | eg making more experienced staff available for support, training if required
Suppliers fail to deliver | Inability to deliver project | eg thorough agreements/contracts
Weather or natural environment | Inability to deliver project as intended | eg weatherproofing, indoor alternatives

## Risk register
|  |  |  | Inherent |  |  |  | Residual |  |  |  | Open
Ref | Risk | Potential impact | Risk owner | Likelihood (1-5) | Impact (1-5) | Risk level | Mitigating action | Likelihood (1-5) | Impact (1-5) | Risk level | Status | Closed
1 | Failure to pay creative team, suppliers etc in timely manner | Relationships sour; third parties unable to deliver due to cashflow issues |  | 3 | 5 | 15 | Suppliers made aware of 30-day payment terms and all been set up on system already. POs raised and awaiting approval. Project budget includes detailed projected cashflow and Finance team are aware. | 1 | 3 | 3 | Open
2 | Insufficient insurance cover | Significant legal, financial and reputational repercussions for all partners |  | 3 | 5 | 15 | Not yet determined insurance requirements - on agenda for next project team meeting. | 3 | 5 | 15 | Open
3 | Scope creep: uncontrolled additions to the project | Additional pressure on internal project team; core components of project put at risk |  | 4 | 4 | 16 | Scope of project signed off at SLT at greenlight. Detailed project brief attached to commissioning & production agreement. All aware that no additional budget is available for extra activity. | 2 | 4 | 8 | Open
4 | Artistic content not representative of vision | Reputational damage with creative team, stakeholders and general public |  | 3 | 5 | 15 | well managed creative process through effective communication, management of expectations |  |  | 0
5 | Cost forecasts inaccurate | Project goes over budget or other project costs must be reduced or removed |  | 3 | 4 | 12 | Thorough planning with budgets set and agreed at the start of the project, reliable quotes from facitities required (stage, toilets, security) |  |  | 0
6 | Decision making causes delays | Additional pressure on internal project team |  | 4 | 5 | 20 | Foreseeing required decisions, project planner in place with deadlines for each stage, scheduled in meetings for the team |  |  | 0
7 | Failure to attract audience/participants | Failure to achieve project objectives and Hull 2017 KPIs |  | 3 | 5 | 15 | Complete the marketing and comms plan. Engage with graphic designer making requirements and deadlines clear |  |  | 0
8 | Failure to contract all parties effectively | Inability to deliver project |  | 3 | 5 | 15 | Use of standard templates for band contracts and creative team contracts. Engage with the ESAG team from council to support with Event planning |  |  | 0
9 | Failure to engage creative team | Inability to deliver project |  | 3 | 5 | 15 | Early meeting to engage creative team |  |  | 0
10 | Failure to secure appropriate venue | Inability to deliver project |  | 2 | 5 | 10 | Ensure that staffing and school site is available for the day |  |  | 0
11 | Failure to secure necessary permissions or licences | Inability to delivery project |  | 3 | 5 | 15 | eg early involvement of Tech & Ops team, appropriate slot at ESAG |  |  | 0
12 | Ill-defined scope: full extent of the project not explored and understood | Additional pressure on internal project team; core components of project put at risk |  |  |  | 0 | Thorough planning and scheduled planning review meetings |  |  | 0
13 | Insufficient budget | Inability to deliver project |  |  |  | 0 | Accurate forecasts, management of expectations |  |  | 0
14 | Insufficient insurance cover | Significant legal, financial and reputational repercussions for all partners |  |  |  | 0 | Early involvement of Legal team for academy |  |  | 0
15 | Lack of project management | Project gets out of control; ineffective working causes unnecessary pressure; no agreement on roles, responsibilities, outcomes etc |  |  |  | 0 | Roles & responsibilities defined, milestones, regular project team updates and/or meetings |  |  | 0
16 | Partners fail to support/deliver as expected | Additional pressure on internal project team |  |  |  | 0 | Cear roles & responsibilities, contracts where required, regular updates gien to all stakeholders |  |  | 0
17 | Project documentation not managed centrally | Files get out of sync; people work on different versions simultaneously; no 'single source of truth' |  |  |  | 0 | Agreement on shared document space on the school server with access for Key team members |  |  | 0
18 | Reduced availability of project team (due to capacity, leave, turnover, illness etc) | Additional pressure on internal project team |  |  |  | 0 | Reliable documentation to allow others to pick up in someone's absence |  |  | 0
19 | Staff or partners inexperienced | Work takes longer than necessary; threats or opportunities are missed |  |  |  | 0 | Engage with ESAG and CCP team for support when required |  |  | 0
20 | Suppliers fail to deliver | Inability to deliver project |  |  |  | 0 | Use suppliers advised by Council partners within ESAG |  |  | 0
21 | Weather or natural environment | Inability to deliver project as intended |  |  |  | 0 | Create a wet weather plan and ensure that all parterns are aware of the plan |  |  | 0
[6 empty] | 0 |  |  |  | 0
[6 empty] | 0 |  |  |  | 0
[6 empty] | 0 |  |  |  | 0
[6 empty] | 0 |  |  |  | 0
[6 empty] | 0 |  |  |  | 0
[6 empty] | 0 |  |  |  | 0
[6 empty] | 0 |  |  |  | 0
[6 empty] | 0 |  |  |  | 0
[6 empty] | 0 |  |  |  | 0
[6 empty] | 0 |  |  |  | 0
[6 empty] | 0 |  |  |  | 0
[6 empty] | 0 |  |  |  | 0
[6 empty] | 0 |  |  |  | 0
[6 empty] | 0 |  |  |  | 0
[6 empty] | 0 |  |  |  | 0
[6 empty] | 0 |  |  |  | 0
[6 empty] | 0 |  |  |  | 0
[6 empty] | 0 |  |  |  | 0
[6 empty] | 0 |  |  |  | 0
[6 empty] | 0 |  |  |  | 0
[6 empty] | 0 |  |  |  | 0
[6 empty] | 0 |  |  |  | 0
[6 empty] | 0 |  |  |  | 0
[6 empty] | 0 |  |  |  | 0
[6 empty] | 0 |  |  |  | 0
[6 empty] | 0 |  |  |  | 0
Note on B2: Crawford James: What might happen?
Note on C2: Crawford James: What would be the result of that happening?
Note on D2: Crawford James: Who is responsible for managing this risk?
Note on E2: Crawford, James: 1 - Rare, 2 - Unlikely, 3 - Possible, 4 - Likely, 5 - Almost certain
Note on F2: Crawford, James: 1 - Negligible, 2 - Minor, 3 - Moderate, 4 - Major, 5 - Catastrophe
Note on H2: Crawford James: What has happened, and what else is planned, to reduce either likelihood or impact of the risk happening, or both - only drop Residual Risk when these actions have taken effect.
Note on I2: Crawford, James: 1 - Rare, 2 - Unlikely, 3 - Possible, 4 - Likely, 5 - Almost certain
Note on J2: Crawford, James: 1 - Negligible, 2 - Minor, 3 - Moderate, 4 - Major, 5 - Catastrophe
Note on L2: Crawford James: Set to 'Closed' when it is no longer a risk to the project, eg all permissions are secured, all parties are contracted...