|  |  |
| --- | --- |
| **Name of Individual / Organisation** | Northern Academy of Performing Arts/Albermarle Music Centre |
| **Name of Project** | We Are The Future! |

Please provide a breakdown of key activities /tasks for your project from start to finish. Please include your preparation and planning activity as well as start / end dates of your public activity (eg. public performance, exhibitions, festival).

|  |  |  |  |  |
| --- | --- | --- | --- | --- |
| **START DATE** | **END DATE** | **ACTIVITY / TASK** | **STATUS** | **NOTES** |
|  |  |  | COMPLETE / ON-TIME / BEHIND |  |
| 09/01/2017 | 03/02/2017 | Start devising and researching show with students (ongoing) |  |  |
| 06/02/2017 | 13/02/2017 | Open auditions |  |  |
| 20/02/2017 | 23/06/217 | Weekly rehearsals |  |  |
| 26/06/2017 | 26/06/2017 | Tech rehearsal at City Hall |  |  |
| 27/06/2017 | 27/06/2017 | Dress Rehearsal City Hall |  |  |
| 28/06/2017 | 29/06/2017 | Performances at City Hall |  |  |
|  |  |  |  |  |
|  |  |  |  |  |
|  |  |  |  |  |
|  |  |  |  |  |
|  |  |  |  |  |
|  |  |  |  |  |
|  |  |  |  |  |
|  |  |  |  |  |
|  |  |  |  |  |

Activity Examples: Planning Meeting, Auditions, Contracting, Rehearsal, Costume Design, Performances