## WRKSHP SCHEDULE
| 2017-02-02 | W/C 6 FEB | 2017-02-14 | HALF TERM | 28 FEB & 1 MAR | W/C 6 MAR | 14 & 15 MAR | 21 & 22 MAR | W/C 27 MAR | 4 & 5 APR | EASTER | 25 & 26 APR | W/C 1 MAY | 9 & 10 MAY | W/C 15 MAY | 22 & 23 MAY | HALF TERM | W/C 5 JUN | 13 & 14 JUN | W/C 19 JUN | 23 & 24 June | 27 & 28 JUNE | 2017-07-02
JACK DURTNALL | [15 empty] | FINISH & SUBMIT FINAL PIECE
SAM LEE
GUEST |  |  |  |  | SAM PIRT |  |  |  |  | SAM PIRT |  | SAM PIRT | [8 empty] | SAM PIRT - Sat |  | SAM PIRT
Topic | [6 empty] | GUEST ARTIST - RICHARD O'NEIL | [6 empty] | GUEST ARTIST - BELINDA & HEIDI |  |  |  |  | rehearsal |  | Rehearsal Fri / Perf to other comm groups Sat |  | Performance
Jack total | 1 |  | 1 |  | 2 |  | 2 |  |  | 2 |  | 2 |  | 2 |  | 2 |  |  | 1 |  | 2 |  | 1 | 18
Sam lee Total | 1 | [5 empty] | 2 | [6 empty] | 2 |  | 2 |  |  |  |  | 2 |  | 1 | 10
Sam Pirt |  |  |  |  | 2 |  |  |  |  | 2 |  | 2 |  |  |  | 2 |  |  |  |  | 1 |  | 1 | 10
Richard | [6 empty] | 2 | [15 empty] | 1 | 3
Heidi & Belinda | [13 empty] | 4 | [8 empty] | 1 | 5
Note on B3: SL up early 2nd, leave night of 3rd -Polly Eldridge

## Sams Diary
Until 30 January | Sam is in India - back on 30th
Thurs 2 Feb | Cld come up night of 1 Feb | Could the school hold a massive session with everyone
2017-02-03 | Filming traveller community, and meet Trinity Brethen
7 - 10 Feb | Not available - Broadsides
w/c 13 Feb | In New York
Tues 21 Feb | Cld go up Monday night, school all day 21 Feb. back that night - NO GOOD AS IT'S HALF TERM
23 & 24 Feb | Aldeburgh - NMB composers residency . Does he need to do this
26 Feb - 1 March | Broadsides tour
3 - 12 March | In Ireland
Tues 14 March | Can go up.
Tues 21 March | Can go up.
W/c 27 March | cld be back in USA
April | Limited as nightingales
Tues 25 April
Tues 9 May
Tues 23 May
June is quite free

## Workshop Artists
Name | Location | Background
Jack Durtnall |  | - the Londoner and brilliant musicians and ethnomusicologist .. fine chap will be perfect very interested too
Richard O’Neil - |  | Romany Gypsy Storyteller mid 50s regular workshop leader fine chap interested costs £350 a day plus travel.. lives in North. Knows Hull and the G7T community well and lots of the Smiths there
Belinda O Hooley and Heidi Tidow - |  | fab duo song writers and life partners who i am crazy about.. will want to lead together though can be separate in classes alongside .. working apart nd together .. waiting to hear if they can or cant depends on a funding bid for another project they are involved with
Sam Pirt .. |  | East Yorkshire based folk musician, accordian player, highly experience in workshops with a range of ages. Interested in song and tune collection from various cultures, including scandanavia and Europe

## Sheet4
PROGRAMME TEAM | No dates |  | Unit |  | £6,000
Sam Lee R & D | 6 |  | £250 | £1,500
Sam Lee workshops | 8 |  | £250 | £2,000
Music leader 10 weeks of 2 workshop days + performance | 21 |  | £250 | £5,250
£8,750
GUEST ARTISTS | No dates |  | Unit |  | £9,600
Guest artists x 5 slots | 10 |  | £250 | £2,500
Guest artists performance fees | 5 |  | £250 | £1,250
Producer Sound UK | 6 |  | £250 | £1,500
Video artist for collecting - budgeted as a local at moment | 6 |  | £250 | £1,500
£6,750
Travel & Accommodation | No Dates | No people |  |  | £7,000
Sam & Polly visit 1 nov travel | 1 | 2 | £166 | £166
Sam & Polly visit 1 nov Accom | 1 | 2 | £60 | £120
Sam & Polly visit 1 nov PDs | 2 | 2 | £20 | £80
Sam travel for film, 5 workshops + performance | 6 | 1 | £50 | £300
Sam accom for 5 workshops + performance | 6 | 1 | £60 | £360
Sam PDs for 5 workshops + performance | 6 | 1 | £20 | £120
Music leader 11 visits inc perf - travel | 21 | 1 | £100 | £2,100
Guest artists travel | 1 | 5 | £100 | £500
Guest artists hotel | 2 | 5 | £60 | £600
guest artists PDs | 2 | 5 | £20 | £200
Total |  |  |  |  | £4,546
MISC COSTS |  | No people | Cost
DBS checks |  | 7 | £74 | £518
Venue hire for final performance |  |  |  | £400
£918
TOTAL | No Dates | No people |  |  | £22,600
£20,964
£1,636