## CHRONO
LOGG
Heralding
Production Specification v1
14.12.16 | GDH
|  |  | TITLE | WHAT | FROM TEXT | LOCATION | CONSIDERATIONS
APRIL | Prologue 2 | W/C 3 April | Discovery of crates | Media opportunity | "cache of over 500 wooden boxes" - the Indiana jones moment | Digital
| Prologue 3 | W/C 17 April | Ministry of Lost and Found | Moving some crates to secret location | Re Rediffusion flat beds at this point? | From ??? To Pumping Station | Actors/costume?
|  | W/C 17 April | Secret Location | Digital | web cam with interventions | Pumping Station | Numbers of crates, number of interventions, regularity - Size of Crates - Miniature, Standard, Huge
APRIL | Phase two |  | Community Heralding
|  |  | The Seven Alleys | Media opportunity ??? | "six crates spotted in the Drain at Preston Road" | Preston Road | Fishing them out? Is there a invention (YEAH DOM!) that has been created to move the crates?
Impact of six in a drain that's got a lot of rubbish in
Design needs to make crates stand apart from the surrounding shite
Reredifussion flat beds and staff - costume (from Phase one)
Standard sized crates
Need to record fiddler (horse and carriage opener) - for Nobody Nose crates
[5 empty] | " Street signs and lighting changes" |  | Gels on lampposts
Could we get a KWL truck/cherry picker branded and have their staff involved?
JUNE 4/6 | Phase two |  | Nobody Nose | Media opportunity | "crates appear same tune played by fiddler from Alleys" |  | Install in centre of North Point - stack of boxes
Reredifussion flat beds and staff - costume (from Phase one)
Standard sized crates - Live
JUNE / JULY? | Phase two |  | The Common Guild | Media opportunity | Margaret finds ten crates stacked - opening finds tabards… |  | Crates - none live
|  |  |  | Finale night | residents create bonfire of crates |  | 20x crates (more?) - burny crates - pyro
SEPTEMBER | Phase two |  | Re-Rediffusion | Media and general profile raising | Vans are seen transporting crates about, unusually high incidence in Bev Road area) | Moving about, Bev Road, over events taking place: Children's Lit Fest, Beverly Folk Festival, Hull Folk Festival? | Reredifussion flat beds and staff - costume (from Phase one) - with smoke, noise and manic flying about
How many interventions? Timings, hitting night time location - rushing up the Avenues, rushing through Ferensway as people come into work…
Crates as before - 8x live crates
OCTOBER | Phase two |  | Little Town |  |  |  | Horse and Carriage - end of piece packing crates up and leaving
How many crates do you get in a carriage?
NOVEMBER | Phase three |  | Parade | Media opportunity | Giant Crate - parade opener - with Macnas parade puppet to emerge |  | Moving people into crate out of eye line, pyro
|  |  | Parade | Interactions | Giant Crate - LOGG closer - to reveal library and distribute books |  | Can this be the same crate - need to carcase an interior that can be fitted over night after the parade

## PROD DESIGN AREAS
PRODUCTION DESIGN
APRIL | Rerediffusion | 2x flatbeds - branded - think Ghostbusters Ecto one - lights, siren (can we get away with that?)
6x staff costumes, equipment
2x special crate mover devices
1x KWL picker truck - branded - partnerships?
APRIL | Crates | Phase 1
|  | Fake street signs | 10x Land of Green Ginger?
|  | Props | 20x 'standard' sized crates
|  | Live crates | 2x battery PA systems - Bells | Rumble packs?
|  | Live crates | 2x smoke grenades - green | Rumble packs?
|  | Live crates | 2x battery PA systems - Voices | Rumble packs?
|  | Live crates | 2x battery PA systems - Siren | Rumble packs?
JUNE | Crates | Bonfire crates | 20x burny crates
OCTOBER | Horse | Horse and Carriage | picking up crates from Bingo Hall
NOVEMBER | Crates | Giant Crate | Bursting open to start the parade
Lots of standard crates - used on Parade?
|  | Giant Crate | Bursting open to reveal library

## SPEC
LOGG CRATES
SIZE
MATERIAL | Wood esk, need to look like old packing crates
Need to be robust enough to be sat on, stood on, stacked, dropped, left out in the public, fire proof?,
Size
http://www.cratingsolutions.co.uk/Services/Products/bespoke-timber-packing-cases-crates.html