|  |  |
| --- | --- |
| **Name of Individual / Organisation** | Hessle Road Network |
| **Name of Project** | 1940 - Now |

Please provide a breakdown of key activities /tasks for your project from start to finish. Please include your preparation and planning activity as well as start / end dates of your public activity (eg. public performance, exhibitions, festival).

|  |  |  |  |  |
| --- | --- | --- | --- | --- |
| **START DATE** | **END DATE** | **ACTIVITY / TASK** | **STATUS** | **NOTES** |
|  |  |  | COMPLETE / ON-TIME / BEHIND |  |
| 01/08/16 | 01/09/16 | Recruit young people to project |  |  |
| 01/09/16 | 01/11/16 | Research visits by young people to residential homes |  |  |
| 01/09/16 | 01/11/16 | Young people carry out further research – on line, library etc. |  |  |
| 01/10/16 | 03/17 | Begin working with dance instructor to develop routine |  |  |
| 01/17 | 01/17 | Create props/sets/costumes |  |  |
| 01/17 | 01/17 | Design leaflets/posters |  |  |
| 02/17 | 02/17 | Distribute leaflets/posters/tickets |  |  |
| 03/17 | 03/17 | Performance |  |  |
|  |  |  |  |  |
|  |  |  |  |  |
|  |  |  |  |  |
|  |  |  |  |  |
|  |  |  |  |  |
|  |  |  |  |  |
|  |  |  |  |  |
|  |  |  |  |  |

Activity Examples: Planning Meeting, Auditions, Contracting, Rehearsal, Costume Design, Performances