## Opt3 - Table 1 - Table 1
2017 LOGG
| MONDAY |  | TUESDAY |  | WEDNESDAY |  | THURSDAY |  | FRIDAY |  | SATURDAY |  | SUNDAY |  |  |  |  | WK
MAR | 6 |  | 7 | TS Oxford | 8 | TS Oxford | 9 | TS Oxford | 10 | TS Oxford | 11 | TS Oxford | 12 | TS Oxford |  |  |  | 10
| 13 |  | 14 |  | 15 | Contract Sign | 16 |  | 17 |  | 18 |  | 19 |  |  |  |  | 11
| 20 |  | 21 |  | 22 |  | 23 |  | 24 |  | 25 |  | 26 |  |  |  |  | 12
| 27 |  | 28 |  | 29 |  | 30 |  | 31 |  | 1 |  | 2 |  |  |  |  | 13
APR | 3 |  | 4 |  | 5 |  | 6 |  | 7 |  | 8 |  | 9 |  |  |  | APR | 14
| 10 | CRATES!! DISCOVER wk | 11 |  | 12 |  | 13 |  | 14 | Good Friday | 15 |  | 16 | Easter Sunday | INSTITUTE PRessL |  |  | 15
| 17 |  | 18 |  | 19 |  | 20 |  | 21 |  | 22 | PERI HELDING | 23 | Horses | Periplum Herlad |  |  | 16
| 24 |  | 25 |  | 26 |  | 27 |  | 28 |  | 29 | Horse Rooftops | 30 |  | Periplum odds |  |  | 17
MAY | 1 |  | 2 |  | 3 | PERI SHOW | 4 | PERI SHOW | 5 | PERI SHOW | 6 | PERI SHOW | 7 |  | PERIPLUM SHOW |  | MAY | 18
| 8 |  | 9 |  | 10 |  | 11 |  | 12 |  | 13 | Josh Herald | 14 | Mother's Day | Joshua Herald |  |  | 19
| 15 |  | 16 |  | 17 |  | 18 |  | 19 |  | 20 |  | 21 |  |  |  |  | 20
| 22 | LONE TWIN HERALD | 23 |  | 24 |  | 25 |  | 26 |  | 27 |  | 28 |  | Lone Twin Herald! |  |  | 21
| 29 | Memorial Day | 30 |  | 31 |  | 1 |  | 2 |  | 3 |  | 4 |  |  |  |  | 22
JUN | 5 |  | 6 |  | 7 |  | 8 |  | 9 |  | 10 |  | 11 |  |  |  | JUN | 23
| 12 |  | 13 |  | 14 |  | 15 |  | 16 |  | 17 | Josh Open Shop | 18 | Father's Day | JOSH SHOP OPEN |  |  | 24
| 19 |  | 20 |  | 21 | @ Beverly Rd Digging hole | 22 | RR Rd works tent activity | 23 | RR Rd works tent activity | 24 | 2A ReRe HERALD | 25 | further press | Herald#1-Aswarm |  |  | 25
| 26 |  | 27 |  | 28 |  | 29 |  | 30 |  | 1 | 2B VEARO LAUNCH | 2 | 2B VEARO 1st run | VEARO |  |  | 26
JUL | 3 | 2B VEARO 1st run | 4 | 2B VEARO 1st run | 5 | 2B VEARO 1st run | 6 | edit & test VEAR data | 7 | edit & test VEAR data | 8 | edit & test VEAR data | 9 | edit & test VEAR data | VEARO |  | JUL | 27
| 10 | edit & test VEAR data | 11 | Test’s inform 2nd run | 12 | 2B VEARO 2nd run | 13 | 2B VEARO 2nd run | 14 | 2B VEARO 2nd run | 15 | 2B VEARO 2nd run | 16 | 2B VEARO 2nd run | VEARO |  |  | 28
| 17 | Aswarm kosova | 18 | SHOW kosova | 19 | SHOW kosova | 20 | SHOW kosova | 21 | SHOW kosova | 22 | LOAN TWIN EVENT | 23 | LOAN TWIN EVENT | Lone Twin Event |  |  | 29
| 24 | Edit & SD | 25 | Edit & SD | 26 | Edit & SD | 27 | Edit & SD | 28 | Edit & SD | 29 | Edit & SD | 30 | Edit & SD | RR & Institute call out |  |  | 30
| 31 | Edit & SD | 1 | pak away | 2 | Aswarm AWAY | 3 |  | 4 |  | 5 |  | 6 |  |  |  |  | 31
AUG | 7 | Aswarm AWAY | 8 |  | 9 |  | 10 |  | 11 |  | 12 |  | 13 |  |  |  | AUG | 32
| 14 | Aswarm AWAY | 15 |  | 16 |  | 17 |  | 18 |  | 19 | JOSH Close Shop>PARADE | 20 |  | Josh PARADE |  |  | 33
| 21 | Aswarm AWAY | 22 |  | 23 | Show Norway | 24 | Show Norway | 25 | Show Norway | 26 | Show Norway | 27 | Show Norway | RR & Institute call out |  |  | 34
| 28 | Show Norway | 29 | Show Norway | 30 | Show Norway | 31 | Show Norway | 1 | Show Norway | 2 | Show Norway | 3 |  | RR & Institute call out |  |  | 35
SEP | 4 | Re build system | 5 | Edit, SD & Test runs | 6 | Edit, SD & Test runs | 7 | Edit, SD & Test runs | 8 | Edit, SD & Test runs | 9 | HERALD #2 VEARO 3rd Hessle | 10 | VEARO Hessle | Herald#2 & VEARO 3C |  |  | 36
| 11 | VEARO Hessle | 12 | VEARO Hessle | 13 | VEARO Hessle | 14 | Master | 15 | Master | 16 |  | 17 |  | VEARO |  |  | 37
| 18 | pack &travel | 19 | Install PikPark | 20 | Install PikPark | 21 | Install PikPark | 22 | Soft launch & adjust Insitu | 23 | VEAR 4B OPEN | 24 |  | Aswarm: PickPark |  |  | 38
| 25 |  | 26 | Turner PRize | 27 |  | 28 | BBC spokenWordFest>2nd | 29 | BBC | 30 |  | 1 |  | Aswarm: PickPark |  |  | 39
OCT | 2 | BBC | 3 |  | 4 |  | 5 |  | 6 |  | 7 | HULL FAIR | 8 | HF | LP Herald |  |  | 40
| 9 | Hull FAIR | 10 | Hull FAIR | 11 | Hull FAIR | 12 | Hull FAIR | 13 | Hull FAIR | 14 | HF & LP OPEN | 15 | HF & LP OPEN | LP-OPEN | Hull FAIR |  | 41
| 16 |  | 17 |  | 18 |  | 19 |  | 20 |  | 21 |  | 22 |  | Little People? |  |  | 42
| 23 |  | 24 |  | 25 |  | 26 |  | 27 |  | 28 | HALF TERM | 29 | HALF TERM | Little People? |  |  | 43
| 30 | HALF TERM | 31 | Halloween | 1 | HALF TERM | 2 | HALF TERM | 3 | HALF TERM | 4 | HALF TERM | 5 | HALF TERM | MAC prep |  |  | 44
NOV | 6 |  | 7 |  | 8 |  | 9 |  | 10 |  | 11 | PARADE | 12 |  | MACNAS PARADE |  |  | ?
© www.calendarlabs.com