**CRITICAL PATH: BACK TO OURS (MAY)**

|  |  |  |
| --- | --- | --- |
| **Detail** | **Date** | **Responsibility** |
| All non-programme specific copy updated and approved | 10-13 Apr | LM |
| Version sent to partners for approval | Wed 12 Apr | LM/Partnerships |
| Confirmation of full programme | Mon 10 Apr | Programming |
| All final copy, images and event schedule received | Thurs 13 Apr – 10am | Touring companies/LM |
|  |  |  |
| Round one artwork | Tues 18 Apr | LM |
| First round sent to Hull 2017 | Tues 18 Apr | Bluestorm |
| Amends collated and sent back to Bluestorm | Tues 18 Apr | LM |
| Second round sent to Hull 2017 for final amends. | Wed 19 Apr | Bluestorm |
| Print sent to companies for approval | Wed 19 Apr PM |  |
| Sent to print deadline | Thurs 20 Apr | Bluestorm |
| Delivery of print to Lowgate House | Wed 26 Apr AM | Bluestorm |
| Tickets go on sale | Thurs 27 April | Digital |