## Sheet1
ACTIVITY & STAGE | WEEK COMMENCING | 17 APRIL | 22 APRIL | 1 MAY | 8 MAY | 15 MAY | 22 MAY | 29 MAY | 5 JUNE | 12 JUNE | 19 JUNE | 26 JUNE | 3 JULY | 10 JULY | 17 JULY | 24 JULY | 31 JULY | 7 AUG | 14 AUG | 21 AUG | 28 AUG | 4 SEP | 11 SEP | 18 SEP | 25 SEP | 2 OCT | 9 OCT | 16 OCT | 23 OCT | 30 OCT | 6 NOV
Design & develop Cardboard City - favela & cityscape
Design primary vignettes (minimum of 5)
Laser cut induction & tests
Laser cut details & vignette elements
Green screen shoot preparation
Green scren shoots
Plan structure with joiner/carpenter
Construct vignettes (primary batch)
Edit & key green screen footage
Design additional vignettes
Projection map all vignettes
Construct additional vignettes
Build Cardboard City structure (external)
Deliver all laser cut boxes to site
Get in Pumping Station - assemble & dress models
Get in Pumping Station - projection mapping
Heralding - crate, invites, tiny clothes etc
Cardboard City runtime
Get out