|  |  |
| --- | --- |
| Tue 20th June | UoH to provide lawnmower measurementsCraig to provide lawnmower/text dimensions and positioning on wall |
| Wed 21st June | Appoint Assistant Curator – Hannah Lupkin (Assemble) / Sophie Thompskin (SM) |
| Thu 22nd June | Bracket mower to wall and removeEthan/Nina/Helen Fitchett (ref Tim)/Katy Morris/Rachel Buffy (Ties and Install volunteers, schedule subject to appointment of Assistant Curator)Appointment of scenic artist to trace lawnmower text |
| Fri 23rd June | Lawnmower text tracing. Lawnmower back up. Tree of Ties install too. |
| Sat 24th June | Lawnmower text tracing |
| Sun 25th June |  |
| Mon 26th June | Start install* UoH floorplates for shelving
 |
| Tue 27th June | Shelving install |
| Wed 28th June | Start final stages of install* Graphics install
* Lighting install
* Book move
* Move objects on to shelves
* Lawnmower
* Tree of Ties
* Shelf install, book install, power install, light install in that order
 |
| Thu 29th June | Objects installed1 accurate volunteer for list-making of items for handsheet until Mon 3rd working with Anna. Trolleys and Perspex glass installed.  |
| Fri 30th June | Object install |
| Sat 1st July | Object install |
| Sun 2nd July | Fishing wire install |
| Mon 3rd July | Audience Testing FixesSchedule Exhibition Operational Handover meeting Hull 2017/Anna to UoHConfirm capacity with UoH fire safety officer |
| Tue 4th July | 11am TBC Press Preview6.30-8.30pm Private View |