## Sheet1
PLAN | TG EVENTS LTD
CLIENT - Hull UK City of Culture 2017
PRINCIPAL DESIGNER - Cirk VOST
JOB - Epicycle
IS THERE ANYTHING THE CLIENT HAS MADE YOU AWARE OF? Nothing specific
KEY DATES: START: 7/8/17 FINISH: 15/8/17 OTHER:
WASHING, TOILET AND REST FACILITIES ARE: In the production area
WORKING TOGETHER | WHO ELSE IS ON SITE, INCLUDE DETAILS: The park is used by the public, on Sat 12th there is also a football match at the adjacent stadium. There will also be lighting, sound and plant contractors and a generator supplier
PRINCIPAL CONTRACTOR: TG Events are the principle contractor
HOW WILL YOU KEEP EVERYONE ON SITE UPDATED DURING THE JOB? Daily induction briefings for new contractors and toolbox talks as and when necessary
ORGANISE | WHAT ARE THE MAIN DANGERS ON SITE, eg: | HAZARD IS PRESENT | WHAT CONTROLS DO YOU HAVE
Uneven floor surfaces, trip hazards etc
|  | usual public park conditions | identify trip hazards, mark them and make other contractors aware
| Traffic on roads/paths where we will work | Conflict with traffic and pedestrians | Create safe working area's with barriers
| Electricity from generators | Electrocution | Use competent generator company and suitable person to install power to BS 7909 2011
| Working with contractors | Conflict of work with other contractors | Work out and agree a schedule and have daily briefings to check work schedules and areas
| Working with plant and crane | Working with telehandler and crane | Ensure staff are trained and competent to use plant. Use contract lift for crane