**HULL UK CITY OF CULTURE 2017**

CREATIVE COMMUNITIES PROGRAMME | PROJECT TIMELINE

|  |  |
| --- | --- |
| **Name of Individual / Organisation** | Butterflies Memory Loss Support Group |
| **Name of Project** | The Butterfly Effect |

Please provide a breakdown of key activities /tasks for your project from start to finish. Please include your preparation and planning activity as well as start / end dates of your public activity (eg. public performance, exhibitions, festival).

|  |  |  |  |  |
| --- | --- | --- | --- | --- |
| **START DATE** | **END DATE** | **ACTIVITY / TASK** | **STATUS** | **NOTES** |
| Sept 2016 | November 2017 | Working on social media presence, blog, twitter etc throughout the whole project. | COMPLETE / ON-TIME / BEHIND |  |
| Sept 2016 | November 2016 | Preparation Workshops and planning |  |  |
| January 2017 | March 2017 | **Hull, We Made it ,We Did**! - Poetry workshops and exhibition MADE IN HULL |  |  |
| March 2017 | June 2017 | **Reflections** - Glass workshops and glass percussion workshops & performance – ROOTS AND ROUTES |  |  |
| April 2017  July 2017 | June 2017  September 2017 | **It’s All A Balancing Act** - Saturday and evening workshops looking at balances of life when living with dementia for the person, their carers and extended family  Circus Skills Day open to the public. FREEDOM |  |  |
| October 2017 | November 2017 | **Hear Our Voice – Celebrate With Us** – celebratory event where all the art work produced throughout the year will be displayed and shared across the country and world via Skype TELL THE WORLD |  |  |

Activity Examples: Planning Meeting, Auditions, Contracting, Rehearsal, Costume Design, Performances