**CREATIVE PARTNERS**
**PROJECT UPDATE REPORT**

**GENERAL INFORMATION**

|  |  |
| --- | --- |
| **ORGANISATION NAME:** | Hull Truck Theatre |
| **PROJECT NAME:** | RYAE Project 2017 |
| **MAIN CONTACT:** | Janthi Mills-Ward & Mark Babych |
| **REPORTING PERIOD:** | 20 – 27 August 2017 |
| **REPORT SUBMISSION DATE:** | 10 November 2017 |

**INTRODUCTION**

Everyone who receives funding from Hull UK City of Culture 2017 Ltd. must complete one or more Project Update Reports, to keep us informed of how they are doing against the deliverables in their Agreement and Project Schedule. We recommend you read it straight away, as you will need to collect the information throughout the lifetime of your project.

We have done our best to ensure that the information being asked for already reflects the output data that you are collecting for other funders. However, due to the specific nature of this funding there are some additional outputs to be measured. This is due to the nature of our own funding agreements, and the need for us to provide certain evidence to these funders and track the performance of our organisation.

Please refer to your Agreement and Project Schedule when you complete this Project Update Report.

This Project Update Report tells us:

* What has happened over the reporting period;
* Your current income and expenditure figures against the agreed budget with Hull 2017;
* What you have learned so far and how you have adapted to these learnings.

We will send you a separate survey about your experience of Hull 2017 so far. We will process the information you give us to understand:

* The effect of our grant and support to date;
* The current effectiveness of our services and grants administration; and
* Where and how we need to make changes.

We will also use this information to provide progress reports to our funders.

Please email this activity report to: pippa.gardner@hull2017.co.uk.

**NB: Please note that these reporting templates have been designed to try and account for all different types of creative partner. As a result, there will be rows within the data tables that are not applicable to your organisation. If this is the case, please just leave these rows BLANK.**

**GLOSSARY OF TERMS**

* **Commission -** the hiring or payment to an artist / artistic company to create a new art work, project or performance. A commission can be wholly or partly funded by you / your organisation.
* **Participant opportunities** – workshops, classes, courses, engagement projects for members of the public (i.e. not including school’s engagement, artist development or staff training opportunities).
	+ **Workshops and classes**: individual occurrences of a workshop / class, even if it is the same one being delivered, e.g. the same contemporary dance workshop led by Hull Dance, delivered at 3 different venues or 3 times in a day, is 3 opportunities.
	+ **Courses and engagement projects**: a series of classes, workshops, activities, etc. where the same group of participants take part for the duration, and it is progressive in nature, e.g. a group of 8 circus skills classes to introduce participants to a range of acrobatic skills (once a week for 8 weeks), attended by the same 10 participants OR a community cast recruited to develop, rehearse and perform a drama.
* **School’s engagement opportunities –** as above, but organized formally with schools.
* **Artist development opportunities** – includes residencies, structured schemes, seed commissions, professional or industry advice, showcase opportunities, associate artist schemes, etc.
* **Staff training opportunities** – including formal training and development programmes, attendance at industry conferences and seminars, professional leave, work shadowing, mentoring, etc.
* **Audience** - those attending an exhibition or performance, and people getting access to work that is printed, recorded, broadcast or on the internet.
* **Participant** – those taking part in doing an activity.

**OTHER INFORMATION**

In addition to these reports, we will also send each project lead, links to an online survey:

* **Survey 1:** The first survey will be sent in April 2017 and will seek to ask a few key questions, linked to the outcome areas we are measuring within the overall evaluation for Hull 2017, as well as ones about how we are performing in our role as your partner. This is so we can learn from your feedback and make necessary changes where improvements need to be made.
* **Survey 2:** This will be sent at the end of the agreement period with you, and will again ask a few key questions linked to the outcome areas we are measuring within the overall evaluation for Hull 2017; as well as any key learnings for Hull’s cultural sector beyond 2018 and future cities of culture.

A number of partners will also be contacted by our external evaluators to take part in in-depth interviews, which seek to explore the above in more detail.

1. **PROJECT REPORT**

Please attach latest versions of the listed documents (where applicable to your project). Please check the box to indicate that the document has been provided:

|  |  |  |
| --- | --- | --- |
| **DOCUMENTS** | **PROVIDED** | **N/A** |
| * Delivery Plan
 | [ ]  |  |
| * Budget
 | [ ]  |  |
| * Marketing & Communications Plan
 | [ ]  | [ ]  |
| * Learning & Engagement Plan
 | [ ]  | [ ]  |
| * Risk Register
 | [ ]  | [ ]  |

**PROJECT UPDATE**

30 young actors between the ages of 18 – 25 were recruited across three partner venues (Hull Truck Theatre, Derby Theatre and Live Theatre) to form a new Regional Young Actors Ensemble.

The actors were recruited via an audition process that particularly targeted people who had not been able to pursue traditional routes into the industry for a variety of reasons, including cost.

After a week’s intensive training at each venue the full cohort came together to create for a week in Hull to continue this training and create Without Borders, a piece of street theatre performed 3 times to the public in Victoria Square. This piece was directed by Sarah Brigham, Artistic Director of Derby Theatre.

In the box below, please highlight any key changes that have been made to the above documents, why these changes have been made, and whether these changes will affect your ability to deliver the project on time and on budget:

1. **MONITORING & EVALUATION REPORT**
2. **ACTIVITY**

**To date, how are you currently doing on reaching the targets laid out in your agreement? Where the row is not applicable, please leave BLANK.**

**\*Target: target(s) listed within your agreement with Hull UK City of Culture 2017**

**\*Actual: final project figures**

|  |  |  |
| --- | --- | --- |
|  | **TARGET\*** | **ACTUAL TO DATE\*** |
| **ACTIVITY** |
| **COMMISSIONS** |
| No. of commissions | 0 | 0 |
| No. of commissions inspired by history / heritage | 0 | 0 |
| **PRODUCTIONS AND PERFORMANCES** |
| No. of productions or co-productions | 1 | 1 |
| No. of productions or co-production performances | 1 | 1 |
| No. of productions or co-productions on tour | 0 | 0 |
| No. of visiting company productions | 0 | 0 |
| No. of visiting company production performances | 0 | 0 |
| No. of productions inspired by history / heritage | 1 | 1 |
| No. of accessible performances | 1 | 1 |
| **EXHIBITIONS AND SCREENINGS** |
| No. of exhibitions |  | N/A |
| No. of exhibitions on tour |  | N/A |
| No. of exhibition days |  | N/A |
| No. of exhibitions inspired by history / heritage |  | N/A |
| No. of access provisions |  | N/A |
| **FILMS** |
| No. of films |  | N/A |
| No. of films on tour |  | N/A |
| No. of screenings |  | N/A |
| No. of films inspired by history / heritage |  | N/A |
| No. of accessible screenings |  | N/A |

|  |  |  |
| --- | --- | --- |
|  | **TARGET\*** | **ACTUAL TO DATE\*** |
| **ACTIVITY** |
| **FESTIVALS & MUSIC EVENTS** |
| No. of festival days  |  | N/A |
| No. of artists / groups / companies programmed |  | N/A |
| No. of performances |  | N/A |
| No. of shows inspired by history / heritage |  | N/A |
| No. of accessible performances during festival |  | N/A |
| **LEARNING AND PARTICIPATION** |
| No. of participant opportunities\* (in-house) |  |  |
| No. of participant opportunities\* (outreach) |  |  |
| No. of school’s engagement opportunities\* (in-house) |  |  |
| No. of school’s engagement opportunities\* (outreach) |  |  |
| No. of artist development opportunities\* (in-house) | 1 | 1 |
| No. of artist development opportunities\* (outreach) |  |  |
| No. of staff training opportunities\* (in-house) |  | 0 |
| No. of staff training opportunities\* (outreach) |  | 0 |
| No. of opportunities exploring history / heritage |  | 0 |
| No. of opportunities to build historical / heritage-based skills or knowledge |  | 0 |
| No. of accessible learning and participation activities |  |  |

|  |  |  |
| --- | --- | --- |
|  | **TARGET\*** | **ACTUAL TO DATE\*** |
| **ACTIVITY VENUES/LOCATIONS** |
| No. of activities delivered in HU1 – HU9 | 1 | 1 |
| No. of activities delivered outside of HU1 – HU9 | 0 | 0 |

Please provide a short description of the activities delivered for this reporting period in the box below:

* The three partners ran five auditions each across their regions, each recruiting an ensemble of 10 performers.
* Each partner ran an intensive week for their own ensemble, delivering a mixture of actor training, masterclasses and professional development
* The full ensemble came to Hull for a week to participate in further training and create a short devised street performance.

If any of the activity for this reporting period has been inspired by, explored, or built skills and knowledge in history / heritage (especially that linked to Hull’s past), please briefly explain how below.

* The performance was well attended, with many audience members ‘discovering’ the show and staying to watch it. There was a very positive reaction from the audience.
* Strong feedback from participants about the affect the project is having on their professional development

For this reporting period, what would you say have been the **main successes** of the activity delivered?

For this reporting period, what would you say have been the **main challenges** of the activity delivered?

*
1. **ADDITIONAL CAPACITY TO DELIVER YOUR PROJECT**

**In the table below, please enter the number of additional people contracted by your organisation to date, to make this project happen. The totals provided below should not include your core team who will be accounted for in the ORGANISATIONAL END OF YEAR REPORT (where applicable).**

**Some roles / work areas have been provided. However, please insert new roles into the table for anything not accounted for.**

|  |  |  |  |
| --- | --- | --- | --- |
|  | **TOTAL NO. OF INDIVIDUALS TO DATE**  | **TOTAL NO. WHO ARE HULL RESIDENTS** | **TOTAL NUMBER OF DAYS WORKED TO DATE** |
| **CATEGORY OR ROLE** |
| **CORE CREATIVE TEAM (PRODCUTION / EXHIBITION SPECIFIC)** |
| Co-Director | 0 | 0 |  |
| Co-Producer | 1 | 1 |  |
| Other Production  | 3 | 1 |  |
| Artist / Performer |  |  |  |
| Other Creative (specify below) | 2 | 0 |  |
| Co-Curator |  |  |  |
| Other Curatorial (specify below) |  |  |  |
| Please specify: Other creative Director, Composer[Insert other production, creative and curatorial roles here] |
| **OTHER** |
| Other (specify below) |  |  |  |
| Please specify:[Insert other roles here] |

**In the tables on this and the following page, please enter the number of people contracted to make this project happen, who fall into each of the equal opportunities categories listed. If you do not know please leave this blank.**

|  |  |  |  |  |
| --- | --- | --- | --- | --- |
|  | **TOTAL TO DATE** |  |  | **TOTAL TO DATE** |
| **AGE GROUPS – DELIVERY TEAM** |  | **DISABILITY/LONG TERM ILLNESS – DELIVERY TEAM** |
| 16-17 years |  |  | Yes – limited a lot | 2 |
| 18-19 years |  |  | Yes – limited a little |  |
| 20-24 years | 2 |  | No |  |
| 25-29 years | 2 |  | Prefer not to say |  |
| 30-34 years | 1 |  | **CONDITIONS – DELIVERY TEAM (NON-MANDATORY)** |
| 35-39 years | 2 |  | Learning disability | 2 |
| 40-44 years |  |  | Long-term illness/condition |  |
| 45-49 years |  |  | Sensory impairment |  |
| 50-54 years | 2 |  | Mental Health condition |  |
| 55-59 years |  |  | Physical impairment |  |
| 60-64 years |  |  | Cognitive impairment |  |
| 65-69 years |  |  | Other |  |
| 70-74 years |  |  | **ETHNICITY – DELIVERY TEAM** |  |
| 75+ years |  |  | Welsh/English/Scottish/Northern Irish/British | 9 |
| Prefer not to say |  |  | Irish |  |
| **GENDER - DELIVERY TEAM** |  | Gypsy or Irish Traveller |  |
| Male | 4 |  | Any other White background |  |
| Female | 5 |  | White and Black Caribbean |  |
| Transgender |  |  | White and Black African |  |
| Gender non-conf |  |  | White and Asian |  |
| Prefer not to say |  |  | Any other Mixed/multiple ethnic background  |  |
|  |  |  | Indian |  |
|  | **In the tables on this page, please enter the number of additional people contracted to make this project happen, who fall into each of the equal opportunities categories listed. If you do not know please leave blank. We recommend using the Equal Opportunities form provided in the Hull 2017 Reporting Toolkit to collect this information.** |  | Pakistani |  |
|  |  |  | Bangladeshi |  |
|  |  |  | Chinese |  |
|  |  |  | Any other Asian background |  |
|  |  |  | African |  |
|  |  |  | Caribbean |  |
|  |  |  | Any other Black/African/Caribbean background  |  |
|  |  |  | Arab |  |
|  |  |  | Any other ethnic group  |  |
|  |  |  | Prefer not to say |  |

For this reporting period, what would you say have been the **main successes** in terms of the additional capacity brought in to deliver your activity? (e.g. contracting certain individuals; capacity building by these individuals with your core staff team, capacity building of these individuals by your core staff team)

* Having a high profile director of the August production gave the project a professional weight and meant that the ensemble were working with a director who was able to share their experience of the professional world.

For this reporting period, what would you say have been the **main challenges** in terms of the additional capacity brought in to deliver your activity? (e.g. staff turnover, contracting failures, skills gaps)

1. **AUDIENCES**

**To date, how many people have attended your activity?**

|  |  |  |
| --- | --- | --- |
|  | **TOTAL TO DATE** | **% FROM HU1-HU9\*** |
| Number of audience members\* (in-house) |  |  |
| Number of audience members on tour | N/A | N/A |

**\*The % from HU1-HU9 can be taken from the results of audience surveys or your box office reports.**
 **Please complete the Total column within the tables below.**

|  |  |  |  |  |
| --- | --- | --- | --- | --- |
|  | **% TO DATE** |  |  | **% TO DATE** |
| **AGE GROUPS - AUDIENCES** |  | **DISABILITY/LONG TERM ILLNESS - AUDIENCES** |
| 0-2 years |  |  | Yes – limited a lot |  |
| 3-5 years |  |  | Yes – limited a little |  |
| 6-10 years |  |  | No |  |
| 11-15 years |  |  | Prefer not to say |  |
| 16-17 years |  |  | **CONDITIONS – AUDIENCES (NON-MANDATORY)** |
| 18-19 years |  |  | Learning disability |  |
| 20-24 years |  |  | Long-term illness/condition |  |
| 25-29 years |  |  | Sensory impairment |  |
| 30-34 years |  |  | Mental Health condition |  |
| 35-39 years |  |  | Physical impairment |  |
| 40-44 years |  |  | Cognitive impairment |  |
| 45-49 years |  |  | Other |  |
| 50-54 years |  | **Please enter the % of your audience for the project in each of the equal opportunities categories shown in the tables on this and the following page. We recommend asking a sample of your audience the Equal Opportunities questions from the Audience Question Bank, provided in the Hull 2017 Reporting Toolkit.**  |  |  |
| 55-59 years |  |  |  |  |
| 60-64 years |  |  |  |  |
| 65-69 years |  |  |  |  |
| 70-74 years |  |  |  |  |
| 75+ years |  |  |  |  |
| Prefer not to say |  |  |  |  |
| **GENDER - AUDIENCES** |  |  |  |
| Male |  |  |  |  |
| Female |  |  |  |  |
| Transgender |  |  |  |  |
| Gender non-conf |  |  |  |  |
| Prefer not to say |  |  |  |  |

|  |  |
| --- | --- |
|  | **% TO DATE** |
| **ETHNICITY - AUDIENCES** |
| Welsh/English/Scottish/Northern Irish/British |  |
| Irish |  |
| Gypsy or Irish Traveller |  |
| Any other White background |  |
| White and Black Caribbean |  |
| White and Black African |  |
| White and Asian |  |
| Any other Mixed/multiple ethnic background  |  |
| Indian |  |
| Pakistani |  |
| Bangladeshi |  |
| Chinese |  |
| Any other Asian background |  |
| African | 3 |
| Caribbean |  |
| Any other Black/African/Caribbean background  | 1 |
| Arab |  |
| Any other ethnic group |  |
| Prefer not to say |  |

For this reporting period, what would you say have been the **main successes** in terms of audience engagement and feedback for your project?

* Feedback has been incredibly strong from the ensemble, with particular praise for the artistic program of work and the support network that the participants feel has been created.
* The relationships forged by the group have been very strong and lead to the creation of a supportive community, who are meeting outside of the project and supporting each other.
* At least three members of the ensemble have recently found paid work as actors and have said their participation in RYAE was a major contributing factor.

For this reporting period, what would you say have been the **main challenges** in terms of audience engagement and feedback for your project?

1. **TICKETS**

**To date, how many tickets have you sold? If Hull 2017 are providing your Box Office function, please highlight this and we will download and complete this data.**

|  |  |  |  |
| --- | --- | --- | --- |
|  | **ACTUAL IN THIS REPORTING PERIOD** | **ACTUAL TO DATE** | **% TO** **HU1 – HU9 RESIDENTS** |
| **TICKET SALES** |
| Number of full price tickets sold |  |  |  |
| Number of concessionary tickets sold |  |  |  |
| Number of free tickets issued |  |  |  |
| Value of all ticket sales |  |  |  |
| **BOOKING TRENDS %** |
| Telephone |  |  |  |
| Counter  |  |  |  |
| Website |  |  |  |
| Post |  |  |  |
| Agency (Hull2017 included in online) |  |  |  |
| ONLINE TICKET SALES |
| Number of tickets sold online |  |  |  |
| Value of tickets sold online |  |  |  |
| FRIENDS/MEMBERSHIP |
| New memberships |  |  |  |
| Membership renewals |  |  |  |
| Tickets purchased by members |  |  |  |
| Value of tickets bought by members | £ | £ |  |

1. **PARTICIPANTS**

 **To date, how many people have participated in your activities?**

|  |  |  |
| --- | --- | --- |
|  | **TOTAL TO DATE** | **% FROM HU1-HU9** |
| Number of participants\* (in-house) | 2 | 50 |
| Number of outreach participants | 27 |  |
| **TOTAL PARTICIPANTS** |  |  |

**\*The % from HU1-HU9 can be taken from the results of participant surveys or registration**

|  |  |  |  |  |
| --- | --- | --- | --- | --- |
|  | **% TO DATE** |  |  | **% TO DATE** |
| **AGE GROUPS - PARTICIPANTS** |  | **DISABILITY/LONG TERM ILLNESS - PARTICIPANTS** |
| 0-2 years |  |  | Yes – limited a lot |  |
| 3-5 years |  |  | Yes – limited a little | 1 |
| 6-10 years |  |  | No |  |
| 11-15 years |  |  | Prefer not to say |  |
| 16-17 years |  |  | **CONDITIONS - PARTICIPANTS** |
| 18-19 years |  |  | Learning disability |  |
| 20-24 years | 25 |  | Long-term illness/condition | 1 |
| 25-29 years | 4 |  | Sensory impairment |  |
| 30-34 years |  |  | Mental Health condition |  |
| 35-39 years |  |  | Physical impairment |  |
| 40-44 years |  |  | Cognitive impairment |  |
| 45-49 years |  |  | Other |  |
| 50-54 years |  | **Please enter the % of your participants in each of the equal opportunities categories shown in the tables on this and the following page. We recommend asking a sample of your audiences across the year the Equal Opportunities questions form the Participant Question Bank, provided in the Hull 2017 Toolkit.**  | **Please enter the % of your participants for the project in each of the equal opportunities categories shown in the tables on this and the following page. We recommend asking participants to complete the Equal Opportunities questions from the Participant Question Bank, provided in the Hull 2017 Reporting Toolkit. If participants need to register to take part, this could be part of the registration process.**  |  |
| 55-59 years |  |  |  |  |
| 60-64 years |  |  |  |  |
| 65-69 years |  |  |  |  |
| 70-74 years |  |  |  |  |
| 75+ years |  |  |  |  |
| Prefer not to say |  |  |  |  |
| **GENDER - PARTICIPANTS** |  |  |  |
| Male | 11 |  |  |  |
| Female | 18 |  |  |  |
| Transgender |  |  |  |  |
| Gender non-conf |  |  |  |  |
| Prefer not to say |  |  |  |  |
|  |  |  |  |  |
|  | **% TO DATE** |
| **ETHNICITY - PARTICIPANTS** |  |
| Welsh/English/Scottish/Northern Irish/British | 25 |
| Irish |  |
| Gypsy or Irish Traveller |  |
| Any other White background |  |
| White and Black Caribbean |  |
| White and Black African |  |
| White and Asian |  |
| Any other Mixed/multiple ethnic background  |  |
| Indian |  |
| Pakistani |  |
| Bangladeshi |  |
| Chinese |  |
| Any other Asian background |  |
| African | 3 |
| Caribbean |  |
| Any other Black/African/Caribbean background  | 1 |
| Arab |  |
| Any other ethnic group |  |
| Prefer not to say |  |

For this reporting period, what would you say have been the **main successes** in terms of participant engagement and feedback for your project?

* All those who took part in the survey said that their main reason for taking part was due to an interest in a career in the theatre or that they felt it was a unique experience not to be missed
* All the participants felt this experience had given them the opportunity to interact with other people they wouldn’t normally interact with
* 100% strongly agreed that it had been an enjoyable experience
* 90% felt being involved in the project had provided a different experience of Hull
* There was a strong feeling that everyone in the group supported each other
* 80% said they came away from the experience with further creative ambitions
* 90% felt that by taking part in the project they had improved their artistic skills
* 90% said that since taking part in the Regional Young Actors Ensemble, they felt that their self-esteem and/or confidence that is directly linked to your participation?
* Although 80% of participants were not Hull based, (78% had not previously been to Hull) 100% said they were planning to take part in or attend other events and activities programmed for Hull 2017
* Feedback has been incredibly strong from the ensemble, with particular praise for the artistic program of work and the support network that the participants feel has been created.
* The relationships forged by the group have been very strong and lead to the creation of a supportive community, who are meeting outside of the project and supporting each other.
* At least three members of the ensemble have recently found paid work as actors and have said their participation in RYAE was a major contributing factor.

For this reporting period, what would you say have been the **main challenges** in terms of participant engagement and feedback for your project?

* The audition process had mixed attendance, with very strong numbers in some locations but some locations needing to be cancelled. The support in encouraging attendance from the local venues we auditioned in was varied.
1. **DIGITAL**

**To date, how has your project impacted upon your online presence?**

|  |  |  |
| --- | --- | --- |
| **WEBSITE** | **TOTAL PAGE VIEWS TO DATE** | **UNIQUE PAGE VEIWS TO DATE** |
| [Insert URL] |  |  |
| Average time on website pages linked to project: |  |  |

|  |  |  |  |
| --- | --- | --- | --- |
|  | **SUBSCRIBERS AT START OF PROJECT** | **SUBSCRIBERS AT END OF THIS REPORTING PERIOD** | **CLICK THROUGHS TO DATE** |
| E-newsletter subscribers via project routes | N/A | N/A | N/A |
| SMS subscribers via project routes | N/A | N/A | N/A |

|  |  |  |  |  |
| --- | --- | --- | --- | --- |
|  | **LIKES/FOLLOWERS/SUBCRIBERS AT START OF PROJECT** | **LIKES/FOLLOWERS/SUBSCRIBERS AT END OF THIS REPORTING PERIOD** | **IMPRESSIONS ON POSTS RELATING TO THE PROJECT** | **ENGAGEMENTS WITH POSTS RELATING TO THE PROJECT** |
| Facebook |  |  |  |  |
| Twitter |  |  |  |  |
| Instagram |  |  |  |  |
| Other |  |  |  |  |

**DEFINITIONS**

* **Followers include:** Facebook Page Likes / Profile Friends; Twitter Followers; YouTube Subscribers; etc.
* **Impressions:** impressions (“views”) of Facebook posts linked to project; impressions (“views”) of Twitter tweets linked to project; views of YouTube videos linked to project; etc.
* **Engagements:** Facebook posts, likes, shares, comments; Twitter tweets, retweets, likes; YouTube shares, comments; etc.

**In the boxes below, please share a selection of audience comments or quotes from social media made about your project:**

1. **PARTNERS**

**To date, how many partners are involved with your activity?**

|  |  |  |
| --- | --- | --- |
|  | **TOTAL TO DATE BASED IN** **HU1 – HU9** | **TOTAL TO DATE BASED OUTSIDE** **HU1 – HU9** |
| **PARTNER TYPE**  |
| Artistic partner (e.g. theatre, art gallery, music venue) | 1 | 1 |
| Heritage partner (e.g. museum, archive) |  |  |
| Funder (e.g. Arts Council England, business, private trust) | 2 | 2 |
| Public Sector partner (e.g. libraries, GPs) |  |  |
| Voluntary sector partner (e.g. community group, charity) |  |  |
| Education (e.g. school, college, university) |  |  |
| Other  |  |  |
| **PARTNERSHIP STAGE** |
| Number of new partnerships established via this project | 0 |  |
| Number of existing partners involved in this this project | 1 |  |

For this reporting period, what would you say have been the **main successes** in terms of your partnerships on this project? (e.g. new partnerships created, new projects developed in partnership, new funding secured)

* The project has strengthened already existing links between the three partners, who have a shared set of values in this area.

For this reporting period, what would you say have been the **main challenges** in terms of your partnerships on this project? (e.g. communications, skills gaps)

* Two of the partners have recently had changes in senior positions which has meant planning the next stage of the project has been somewhat delayed.
* The different staffing structures in the three partners has meant that the project has had to run slightly differently in each region.