## Budget Summary
Hull City of Culture
Macnas Budget 2017
Pre-Production | 28540
Fees: Artists, Costume, Director, Production & Post Production | 53043
Freight, Flights, Travel, Accomm and PD's | 47270
Event Staging | 39000
Marketing | 1050
Total | 168903
contingency 2 % less on CI travel | 1769 | Fixed from previous budget
management fee 6 % | 7857 | Fixed from previous budget
Total including contingency and mgt | 178529
Culture Ireland | 38000
140529
Fee agreed provisionally with Hull | 98913.44

## Prep
Macnas @ Hull Festival 2017
Schedule
Prep Trip to Hull # 1 | Site visit and spec
Artistic Director, Production Manager | 2 pax
2 days
Prep Trip to Hull # 2 | Meet volunteers for performance, puppetry, operators, crew
Artistic Director, Production Manager, Performance Facilitator | 3 pax
2 days
Prep trip to Hull # 3 | Artistic Direction and facilitation with volunteers in Hull
Artistic Director | Noeline arrive 1st Nov
12 days | 1/2/3/4/5/6/7/8 Nov
Team arrives 8th Nov
Event Schedule
Wed 8th Nov | Macnas crew travel / site visit / costume room set up
Thurs 9th Nov | costume fittings / Make up set up / tech crew unpack
Fri 10th Nov | Tech run
Sat 11th Nov | Show
Sun 12th Nov | Packing day / Trailers leave
Pre Production Costs
Prep Work at Macnas workshop Liosban repairs, packing, loading
Design and Construction | team and materials | 20000 | Costs allocated to Galway re-allocated
production kit | 1 crew @ 750 | 750
costume | 1 crew @ 150 x 6 days | 900
make up | 1 crew @ 150 x 2 days | 300
container pack | 7 crew @ 150 per day x 1 day | 1050
| Total Prep Costs Crew | 23000 | 23000 | prep including key personnel
Travel and accommodation Prep trip 1 August
flights | 2 return flights @ €200 per flight | 400
hotel nights | 4 hotel nights @ €100 per night | 400
per diems | 4 nights @ €60 per night | 240
bus from galway, taxi, travel and misc costs | Bus to Dublin, Parking, Petrol €140 Uk side €220 pp | 440
travel and accommodation Prep trip 2 - Sep
flights | 3 return flights @ €200 per flight | 600
hotel nights | 6 hotel nights @ €100 per night | 600
per diems | 6 nights @ €60 per night | 360
bus from galway, taxi, travel and misc costs | €220 pp | 660
travel and accommodation Noeline from 6th Nov | Noeline Show time in with Show budget (5 days)
flights | Flight added to show flight
hotel nights 1/2/3/4/5/6/7 Nov | 9 hotel nights @ €100 per night | 900
per diems | 9 nights @ €60 per night | 540
bus from galway, taxi, travel and misc costs |  | 400
| Total Travel and Accomm Prep | 5540 | Travel for Creation ineligible for CI support

## Show
Macnas Personnel
Show Team/Crew
Macnas Prep and Show Team | All in to include PRSI and other payroll costs | Reh |  |  | 35000
7 core team
Artistic Director fee | 23 days |  |  |  | 4600
Stage Manager | 5 days |  |  |  | 1000
Produciton Manager | 15 days |  |  |  | 3300
Musical Director | 10 days |  |  |  | 1750
Performance Facilitator | 7 days |  |  |  | 1400
Company manager | 15 days |  |  |  | 2250
Lightening Designer |  |  |  |  | 1793
Travel, Accommodation and Freight |  | Pax | PPU € | no Nights | 51093
Freight | 3 x 40 ft containters @ 5,000 each ex VAT |  |  |  | 23750 | 4 x Containers
Extra Luggage |  | 4 | 60 |  | 240
Flights and travel | 30 x crew @ 200 each approx | 30 | 200 |  | 6000
travel insurance | 30 x €12 | 30 | 12 |  | 360
Taxis Hull |  | 30 | 15 |  | 450
Coach Transfers |  | 30 | 40 |  | 1200
Bus Transfer Galway to Dublin | Citylink/Go bus | 30 | 29 |  | 870
accommodation | €70 per night per crew member | 30 | 70 | 4 | 8400
per diem | @60 per night per crew member | 30 | 50 | 4 | 6000
Staging |  |  |  |  | 47270
Lighting /Sound/ Effects |  |  |  |  | 30000 | Needs to be checked with Pete
make up and hair materials |  |  |  |  | 500
Production hardware |  |  |  |  | 8500
Volunteer list | community cast co-ordinator
stage management interns
costume interns
make up assistants
hair
volunteer puppeteers
volunteer performers
volunteer stewards
volunteer pushers
39000
Marketing
marketing | Social media marketing |  |  |  | 1050
1050
Total Post Production
post production
3 unpack crew | 3 days x3 Days |  |  |  | 1350
Costume Unpack | 3 Days x 1 will need to be worked into contingency |  |  |  | 450
Make-up Unpack | 1 Day x 1 |  |  |  | 150
1950

## Summary
Summary |  | contingency | Includes contin
Total Prep Costs/Artists Fees | 23000 | 460 | 23460
Total Travel and Accomm Prep | 5540 | 110.8 | 5650.8
total crew fees | 51093 | 1021.86 | 52114.86
total travel , accomm, freight | 47270 |  | 47270
total staging | 39000 | 780 | 39780
total marketing | 1050 | 21 | 1071
total post production fees | 1950 | 39 | 1989
total costs | 168903 | 2432.66 | 171335.66
management fee 6 % | 10134.18 |  | 10134.18
Total including contingency and mgt |  |  | 181469.84