|  |  |
| --- | --- |
| **Name of Individual / Organisation** | My Pockets Ltd |
| **Name of Project** | Fuzzfeed |

Please provide a breakdown of key activities /tasks for your project from start to finish. Please include your preparation and planning activity as well as start / end dates of your public activity (eg. public performance, exhibitions, festival).

|  |  |  |
| --- | --- | --- |
| **START DATE** | **END DATE** | **ACTIVITY / TASK** |
| 1/9/2016 | 15/10/2016 | Prep and workshops with young people in schools. Working with them to record conversations, improvise and develop ideas for the films. |
| 16/10/2016 | 16/10/2016 | Casting meeting to cast the young people who we want to voice the films. This will be based on the performances in the workshops. |
| 17/10/2016 | 17/11/2016 | 3 recording sessions in schools. Working with the young people we have cast, as well as other young people who will help develop ideas and record material for the conversations in the films. |
| 1/11/2016 | 10/11/2016 | 1st shoot day. 1 day of prep and 1 days shooting plus edit. |
| 1/1/2017 |  | Upload of first episode as part of the Made In Hull season. The young people in all three schools will work with us to market and promote the film on their social networks. |
| Jan 2017 | March 2017 | Upload of the next three films. |
| 1/3/2017 | 15/3/2017 | Workshops in all three schools. The voice performers will respond to comments from the first 4 films and develop and progress with ideas and conversations.  |
| 20/3/2017 | 30/3/2017 | 2nd shoot day. 1 day of prep and 1 days shooting plus edit. |
| April 2017 | July 2017 | Upload of the next four films. |
| 1/6/2017 |  | Review of the projects progress and the success of the first 8 films in reaching an audience and reaching our target outcomes. |
| 1/7/2017 | 10/7/2017 | Workshops in all three schools. The voice performers will respond to comments from the first 4 films and develop and progress with ideas and conversations. |
| 25/7/2017 | 5/8/2017 | 3rd shoot day. 1 day of prep and 1 days shooting plus edit. |
| August 2017 | October 2017 | Upload of the next four films. |
| 1/10/2017 | 15/10/2017 | Workshops in all three schools. The voice performers will respond to comments from the first 4 films and develop and progress with ideas and conversations. |
| 20/10/2017 | 28/10/2017 | 4th shoot day. 1 day of prep and 1 days shooting plus edit. |
| October 2017 | December 2017 | Upload of the next 2 films. |
| 15/12/2017 |  | Planning meeting to evaluate and look at continuing the project and new opportunities for income. |
| 31/12/2017 |  | Project end. |

Activity Examples: Planning Meeting, Auditions, Contracting, Rehearsal, Costume Design, Performances