## Summary (hidden)
Tab name: | 1 |  | Tab name: | Tab name: | Tab name:
#REF! | #REF!
#REF! | #REF!
#REF! | #REF!
#REF! | #REF! | #REF!
#REF! | #REF! | #REF!
#REF! | #REF! | #REF!
#REF! | #REF! | #REF!
#REF! | #REF! | #REF!

## Timeline
[10 empty] | JAN |  |  |  |  | FEB |  |  |  | MAR |  |  |  | APR |  |  |  | MAY |  |  |  |  | JUN |  |  |  | JUL |  |  |  |  | AUG |  |  |  | SEP |  |  |  | OCT |  |  |  |  | NOV |  |  |  | DEC
REF | STATUS | ACTIVITY | ACTIVITY DETAIL | PROJECT | FROM | TO | LOCALE | VENUE | ACTION | [53 empty] | NOTES | time axis 2017-01-02 to 2018-01-01
11492 | Complete | Milestones | Revised 2017 proposal submitted | 1. Periplum - 7 Alleys | 2017-01-09 | 2017-01-09 | *Milestones | *Milestones | Periplum | bar: 2017-01-09
12229 | Complete | Milestones | House: contract signed | Land of Green Ginger (Umbrella) | 2017-01-10 | 2017-01-10 | *Milestones | *Milestones | EB | bar: 2017-01-09
12230 | Complete | Milestones | House: keys received | Land of Green Ginger (Umbrella) | 2017-01-11 | 2017-01-11 | *Milestones | *Milestones | EB | bar: 2017-01-09
12233 | Complete | Milestones | House: order supplies & extra furniture | Land of Green Ginger (Umbrella) | 2017-01-13 | 2017-01-13 | *Milestones | *Milestones | EB | bar: 2017-01-09
11373 | Complete | Creative | final proposal and budget agreed | 2. Joshua Sofaer's Nobody Nose | 2017-01-16 | 2017-01-16 | *Milestones | *Milestones | JS KF | bar: 2017-01-16
10491 | Pending | Milestones | Draft artist contracts sent out | Land of Green Ginger (Umbrella) | 2017-01-16 | 2017-01-16 | *Milestones | *Milestones | KF MM | bar: 2017-01-16
11375 | Complete | Production | Confirmation of shop unit and contracted | 2. Joshua Sofaer's Nobody Nose | 2017-01-23 | 2017-01-23 | *Milestones | *Milestones | LY/GH | bar: 2017-01-23
11376 | Complete | Contracting | Contract draft sent | 2. Joshua Sofaer's Nobody Nose | 2017-01-23 | 2017-01-23 | *Milestones | *Milestones | KF | bar: 2017-01-23
12226 | Pending | Contracting | Final 2017 proposal deadline | 4. Aswarm - Re-Rediffussion | 2017-01-23 | 2017-01-23 | *Milestones | *Milestones | TB-M / LY | bar: 2017-01-23
12227 | Pending | Milestones | Final proposal deadline | 6. Macnas title TBC | 2017-01-30 | 2017-01-30 | *Milestones | *Milestones | Macnas | bar: 2017-01-30
12231 | Complete | Milestones | House: contract cleaner | Land of Green Ginger (Umbrella) | 2017-01-30 | 2017-01-30 | *Milestones | *Milestones | EB | bar: 2017-01-30
7826 | Complete | Crates | Heralding Brief prepared | Land of Green Ginger (Umbrella) | 2017-01-31 | 2017-01-31 | *Milestones | *Milestones | GH | bar: 2017-01-30
7829 | Pending | Marcomms | MAR/COMMS: Brand guidelines sent out to artists | Land of Green Ginger (Umbrella) | 2017-01-31 | 2017-01-31 | *Milestones | *Milestones | CL | bar: 2017-01-30
10489 | Complete | Budget | Update budget | Land of Green Ginger (Umbrella) | 2017-01-31 | 2017-01-31 | *Milestones | *Milestones | KF / MM | bar: 2017-01-30
11377 | Complete | Creative | JSP recruits and contracts team | 2. Joshua Sofaer's Nobody Nose | 2017-02-01 | 2017-02-01 | *Milestones | *Milestones | JS | bar: 2017-01-30
12232 | Complete | House | House: set up furniture | Land of Green Ginger (Umbrella) | 2017-02-03 | 2017-02-03 | *Milestones | *Milestones | EB | bar: 2017-01-30
11378 | Complete | Creative | final proposal and budget agreed | 2. Joshua Sofaer's Nobody Nose | 2017-02-06 | 2017-02-06 | *Milestones | *Milestones | KF / LY | bar: 2017-02-06
11384 | Pending | Production | Tech rider developed & confirmed | 2. Joshua Sofaer's Nobody Nose | 2017-02-06 | 2017-02-06 | *Milestones | *Milestones | JS / GH / AL | bar: 2017-02-06
2425 | Pending | Milestones | 2017 Proj Proposals Sign-off | Land of Green Ginger (Umbrella) | 2017-02-06 | 2017-02-06 | *Milestones | *Milestones | KF | bar: 2017-02-06
12234 | Complete | Event Management | Draft outline for ESAG [T&O] | 1. Periplum - 7 Alleys | 2017-02-07 | 2017-02-07 | *Milestones | *Milestones | GH | bar: 2017-02-06
7819 | Pending | Milestones | MAR/COMMS: 2017 Individual Artists Mar/Comms plan | Land of Green Ginger (Umbrella) | 2017-02-07 | 2017-02-07 | *Milestones | *Milestones | CL | bar: 2017-02-06
11359 | Complete | Milestones | Contract draft sent | 1. Periplum - 7 Alleys | 2017-02-10 | 2017-02-10 | *Milestones | *Milestones | KF | bar: 2017-02-06
11374 | Complete | Contracting | Contract signed | 2. Joshua Sofaer's Nobody Nose | 2017-02-13 | 2017-02-13 | *Milestones | *Milestones | JS | bar: 2017-02-13
7818 | Complete | Marcomms | MAR/COMMS: 2017 Mar/Comms Framework | Land of Green Ginger (Umbrella) | 2017-02-16 | 2017-02-16 | *Milestones | *Milestones | CL | bar: 2017-02-13
7828 | Complete | Book | THE BOOK: Print, distribution & costs looked into for the book | Land of Green Ginger (Umbrella) | 2017-02-16 | 2017-02-16 | *Milestones | *Milestones | bar: 2017-02-13
11362 | Pending | Production | Production personnel contracted [T&O] | 1. Periplum - 7 Alleys | 2017-02-20 | 2017-02-20 | *Milestones | *Milestones | GH / AL / Periplum | bar: 2017-02-20
12236 | Complete | Production | Site layout finalised [T&O] | 1. Periplum - 7 Alleys | 2017-02-20 | 2017-02-20 | *Milestones | *Milestones | GH / AL / Periplum | bar: 2017-02-20
11389 | Pending | Event Management | Venue confirmed & contracted | 5. Davy & Kristin McGuire's Cardboard City | 2017-02-20 | 2017-02-20 | *Milestones | *Milestones | MM | bar: 2017-02-20
11390 | Pending | Production | Tech rider developed & confirmed | 5. Davy & Kristin McGuire's Cardboard City | 2017-02-27 | 2017-02-27 | *Milestones | *Milestones | DM / GH / AL | bar: 2017-02-27
2426 | Pending | Production | 2017 Pre-Production Begins (TBC) | Land of Green Ginger (Umbrella) | 2017-03-01 | 2017-03-01 | *Milestones | *Milestones | All | bar: 2017-02-27
11206 | Pending | Marcomms | DRAFT detailed MarComms Plan | Land of Green Ginger (Umbrella) | 2017-03-01 | 2017-03-01 | *Milestones | *Milestones | CL | bar: 2017-02-27
12237 | Complete | Event Management | 1st draft EMP for ESAG [T&O] | 1. Periplum - 7 Alleys | 2017-03-02 | 2017-03-02 | *Milestones | *Milestones | GH | bar: 2017-02-27
12239 | Complete | Event Management | Premise license app deadline [T&O] | 1. Periplum - 7 Alleys | 2017-03-03 | 2017-03-03 | *Milestones | *Milestones | GH | bar: 2017-02-27
11391 | Complete | Creative | Initial storyboard shared | 5. Davy & Kristin McGuire's Cardboard City | 2017-03-06 | 2017-03-06 | *Milestones | *Milestones | DM | bar: 2017-03-06
| Complete | Production | Air Quality Test Results: Aspestos | 5. Davy & Kristin McGuire's Cardboard City | 2017-03-07 | 2017-03-07 |  |  | AL | bar: 2017-03-06
12241 | Complete | Event Management | Take project to ESAG [T&O] | 1. Periplum - 7 Alleys | 2017-03-09 | 2017-03-09 | *Milestones | *Milestones | GH | bar: 2017-03-06
| Pending | Crates | Heralding delivery team comtracted | Land of Green Ginger (Umbrella) | 2017-03-09 | 2017-03-09 |  |  | GH | bar: 2017-03-06
11363 | Pending | Marcomms | Marcomms plan developed/drafted | 1. Periplum - 7 Alleys | 2017-03-06 | 2017-03-10 | *Milestones | *Milestones | CL | bar: 2017-03-06
11354 | Complete | Community Engagement | Engagement plan drawn up | 1. Periplum - 7 Alleys | 2017-03-06 | 2017-03-10 |  |  | Periplum / LY | bar: 2017-03-06
11364 | Complete | Production | Tech rider confirmed [T&O] | 1. Periplum - 7 Alleys | 2017-03-10 | 2017-03-10 | *Milestones | *Milestones | Periplum / AL / GH | bar: 2017-03-06
11360 | Complete | Contracting | Contract signed | 1. Periplum - 7 Alleys | 2017-03-10 | 2017-03-10 | *Milestones | *Milestones | Periplum / KF / MM | bar: 2017-03-06
| Complete | Volunteers | Volunteer requirements finalised | 1. Periplum - 7 Alleys | 2017-03-10 | 2017-03-10 |  |  | GH / EB / Periplum | bar: 2017-03-06
12235 | Complete | Production | Tech rider quotations [T&O] | 1. Periplum - 7 Alleys | 2017-03-09 | 2017-03-16 | *Milestones | *Milestones | AL | bar: 2017-03-06 to 2017-03-13
11356 | Pending | Creative | Set design developed | 1. Periplum - 7 Alleys | 2017-03-06 | 2017-03-17 | *Milestones | *Milestones | Periplum | bar: 2017-03-06 to 2017-03-13
11357 | Pending | Creative | Costume design developed | 1. Periplum - 7 Alleys | 2017-03-06 | 2017-03-17 | *Milestones | *Milestones | Periplum | bar: 2017-03-06 to 2017-03-13
11358 | Pending | Creative | Visual installation developed | 1. Periplum - 7 Alleys | 2017-03-06 | 2017-03-17 | *Milestones | *Milestones | Periplum | bar: 2017-03-06 to 2017-03-13
11355 | Pending | Community Engagement | Engagement begins | 1. Periplum - 7 Alleys | 2017-03-10 | 2017-03-17 | *Milestones | *Milestones | Periplum / LY | bar: 2017-03-06 to 2017-03-13
| Provisional | Community Engagement | Recruitment of Guild | 3. Lone Twin's The Guild of Commoners | 2017-03-10 | 2017-04-30 |  |  | Lone Twin / MM | bar: 2017-03-06 to 2017-04-24
11407 | Pending | Contracting | Final budget & proposal finalised | 3. Lone Twin's The Guild of Commoners | 2017-03-31 | 2017-03-31 | *Milestones | *Milestones | Lone Twin / MM | bar: 2017-03-13
11408 | Pending | Contracting | Contract draft sent | 3. Lone Twin's The Guild of Commoners | 2017-04-10 | 2017-04-17 | *Milestones | *Milestones | MM / KF | bar: 2017-03-13
11386 | Pending | Contracting | Final budget & proposal confirmed | 5. Davy & Kristin McGuire's Cardboard City | 2017-03-25 | 2017-03-25 | *Milestones | *Milestones | DM / MM | bar: 2017-03-13
11387 | Complete | Contracting | Contract draft sent | 5. Davy & Kristin McGuire's Cardboard City | 2017-03-13 | 2017-03-13 | *Milestones | *Milestones | MM / KF | bar: 2017-03-13
11392 | Pending | Community Engagement | Engagement plan drawn up | 5. Davy & Kristin McGuire's Cardboard City | 2017-04-10 | 2017-04-10 | *Milestones | *Milestones | DM / MM | bar: 2017-03-13
11207 | Pending | Marcomms | Approved detailed MarComms Plan | Land of Green Ginger (Umbrella) | 2017-03-15 | 2017-03-15 | *Milestones | *Milestones | CL | bar: 2017-03-13
11204 | Pending | Marcomms | DRAFT high level MarComms Plan | Land of Green Ginger (Umbrella) | 2017-03-16 | 2017-03-16 | *Milestones | *Milestones | CL | bar: 2017-03-13
| Pending | Volunteers | Volunteer recruitment | 1. Periplum - 7 Alleys | 2017-03-10 | 2017-03-17 |  |  | EB | bar: 2017-03-06 to 2017-03-13
| Complete | Crates | Director recruited | Land of Green Ginger (Umbrella) | 2017-03-17 | 2017-03-17 |  |  | MM | bar: 2017-03-13
11366 | Pending | Production | Installations confirmed & site layout finalised | 1. Periplum - 7 Alleys | 2017-03-20 | 2017-03-20 | *Milestones | *Milestones | Periplum | bar: 2017-03-20
11409 | Pending | Contracting | Contract drafted | 3. Lone Twin's The Guild of Commoners | 2017-04-03 | 2017-04-10 | *Milestones | *Milestones | Lone Twin / MM | bar: 2017-03-20
11388 | Pending | Contracting | Contract signed | 5. Davy & Kristin McGuire's Cardboard City | 2017-03-20 | 2017-03-31 | *Milestones | *Milestones | DM / MM | bar: 2017-03-20
11393 | Pending | Creative | Team recruited & contracted | 5. Davy & Kristin McGuire's Cardboard City | 2017-03-31 | 2017-04-07 | *Milestones | *Milestones | DM / MM | bar: 2017-03-20
11361 | Pending | Creative | Residency begins | 1. Periplum - 7 Alleys | 2017-03-24 | 2017-03-24 | *Milestones | *Milestones | Periplum | bar: 2017-03-20
12238 | Pending | Production | Tech items ordered [T&O] | 1. Periplum - 7 Alleys | 2017-03-24 | 2017-03-24 | *Milestones | *Milestones | AL | bar: 2017-03-20
11368 | Pending | Production | Set build begins [T&O] | 1. Periplum - 7 Alleys | 2017-03-27 | 2017-03-27 | *Milestones | *Milestones | Periplum | bar: 2017-03-27
| Complete | Production | Air Quality Test Results | 5. Davy & Kristin McGuire's Cardboard City | 2017-03-28 | 2017-03-28 |  |  | AL
| Complete | Marcomms / Crates | Vault photo shoot | Land of Green Ginger (Umbrella) | 2017-03-28 | 2017-03-28 |  |  | CL / GH / EB / MM
| Pending | Marcomms / Crates | GGF HQ filming | Land of Green Ginger (Umbrella) | 2017-03-10 | 2017-03-11 |  |  | CL / GH / EB / MM | bar: 2017-03-27
| Complete | Marcomms | HDM 1st and 2nd articles submitted | Land of Green Ginger (Umbrella) | 2017-03-27 | 2017-03-27 |  |  | CL
11365 | Pending | Creative | 2nd residency begins | 1. Periplum - 7 Alleys | 2017-03-31 | 2017-03-31 | *Milestones | *Milestones | Periplum
11367 | Pending | Event Management | MSRA draft submitted [T&O] | 1. Periplum - 7 Alleys | 2017-03-31 | 2017-03-31 | *Milestones | *Milestones | GH | bar: 2017-03-27
12240 | Pending | Event Management | Premise license consultation period [T&O] | 1. Periplum - 7 Alleys | 2017-03-31 | 2017-03-31 | *Milestones | *Milestones | GH | bar: 2017-03-27
12245 | Pending | Event Management | Final EMP produced & circulated to ESAG [T&O] | 1. Periplum - 7 Alleys | 2017-03-31 | 2017-03-31 | *Milestones | *Milestones | GH | bar: 2017-03-27
| Pending | Marcomms | HDM Discovery of Vault | Land of Green Ginger (Umbrella) | 2017-04-03 | 2017-04-03 |  |  | CL | bar: 2017-04-03
11205 | Pending | Marcomms | Approved high level MarComms Plan | Land of Green Ginger (Umbrella) |  | 2017-04-03 | *Milestones | *Milestones | CL | bar: 2017-04-03
11369 | Pending | Creative | Set build complete [T&O] | 1. Periplum - 7 Alleys | 2017-04-10 | 2017-04-10 | *Milestones | *Milestones | Periplum | bar: 2017-04-10
11371 | Pending | Creative | Costume & Visual Makes Completed | 1. Periplum - 7 Alleys | 2017-04-10 | 2017-04-10 | *Milestones | *Milestones | Periplum | bar: 2017-04-10
11379 | Pending | Creative | events, design and activities developed | 2. Joshua Sofaer's Nobody Nose | 2017-04-10 | 2017-04-10 | *Milestones | *Milestones | JS | bar: 2017-04-10
11372 | Pending | Creative | Production Rehearsals begin | 1. Periplum - 7 Alleys | 2017-04-10 | 2017-04-10 | *Milestones | *Milestones | Periplum | bar: 2017-04-10
12243 | Pending | Event Management | Feedback & final EMP circulated [T&O] | 1. Periplum - 7 Alleys | 2017-04-10 | 2017-04-10 | *Milestones | *Milestones | GH | bar: 2017-04-10
| Pending | Marcomms | HDM report on crate movement | Land of Green Ginger (Umbrella) | 2017-04-10 | 2017-04-10 |  |  | CL | bar: 2017-04-10
12244 | Pending | Event Management | Attendance at ESAG (final) [T&O] | 1. Periplum - 7 Alleys | 2017-04-13 | 2017-04-13 | *Milestones | *Milestones | GH | bar: 2017-04-10
11370 | Pending | Creative | Community workshops | 1. Periplum - 7 Alleys | 2017-04-17 | 2017-04-17 | *Milestones | *Milestones | Periplum / LY | bar: 2017-04-17
11382 | Pending | Marcomms | Marcomms plan developed & agreed | 2. Joshua Sofaer's Nobody Nose | 2017-04-17 | 2017-04-17 | *Milestones | *Milestones | CL / LY / MM | bar: 2017-04-17
11394 | Pending | Creative | Stage design & vignette ideas developed | 5. Davy & Kristin McGuire's Cardboard City |  | 2017-04-17 | *Milestones | *Milestones | DM | bar: 2017-04-17
|  | Heralding | LOGG stamps appear in East Park | 1. Periplum - 7 Alleys | 2017-04-17 | 2017-04-22 |  |  | CL | bar: 2017-04-17
12218 | Provisional | Heralding | Crates delivered [T&O] | 1. Periplum - 7 Alleys | 2017-04-20 | 2017-04-22 | Hull East | Freedom Centre | GH | bar: 2017-04-17
11426 | Pending | Production | PM, Directors, Musicians & performers arrive in Hull | 1. Periplum - 7 Alleys | 2017-04-22 | 2017-04-22 | *Milestones | *Milestones | Periplum / AL / GH | bar: 2017-04-17
| Provisional | Heralding | Invitations go to Preston and Holderness Rd residents | 1. Periplum - 7 Alleys | 2017-04-20 | 2017-04-24 |  |  | CL | bar: 2017-04-24
2427 | Pending | All | 2017 Projects Begin (TBC) | Land of Green Ginger (Umbrella) |  | 2017-04-24 | *Milestones | *Milestones | ALL | bar: 2017-04-24
11395 | Pending | Community Engagement | Locals recruited for filming | 5. Davy & Kristin McGuire's Cardboard City |  | 2017-04-24 | *Milestones | *Milestones | MM / DM | bar: 2017-04-24
|  | Heralding | Horse and Carriage invitation deliveries | 1. Periplum - 7 Alleys | 2017-04-24 | 2017-04-28 |  |  | Periplum / CL | bar: 2017-04-24
11427 | Provisional | Production | Periplum team arrive in Hull | 1. Periplum - 7 Alleys | 2017-04-28 | 2017-04-28 | Hull East | East Park | Periplum | bar: 2017-04-24
11397 | Pending | Creative | Film studio booked | 5. Davy & Kristin McGuire's Cardboard City |  | 2017-04-28 | *Milestones | *Milestones | MM / DM | bar: 2017-04-24
| Provisional | Production | Get In | 1. Periplum - 7 Alleys | 2017-04-28 | 2017-04-29 |  |  | AL / GH / Periplum | bar: 2017-04-24
11424 | Provisional | Heralding | Premonition performances | 1. Periplum - 7 Alleys | 2017-04-29 | 2017-04-30 | Hull East | East Park | Periplum | bar: 2017-04-24
11428 | Provisional | Rehearsal | Tech Rehearsals | 1. Periplum - 7 Alleys | 2017-04-30 | 2017-05-01 | Hull East | East Park | Periplum / AL / GH | bar: 2017-04-24 to 2017-05-01
11380 | Pending | Production | Take possession of shop unit | 2. Joshua Sofaer's Nobody Nose | 2017-05-01 | 2017-05-01 | *Milestones | *Milestones | JS / LY | bar: 2017-05-01
11396 | Pending | Creative | Filming schedule confirmed | 5. Davy & Kristin McGuire's Cardboard City |  | 2017-05-01 | *Milestones | *Milestones | DM / MM | bar: 2017-05-01
11429 | Provisional | Technical Rehearsal | Full Dress Rehearsal | 1. Periplum - 7 Alleys | 2017-05-02 | 2017-05-02 | Hull East | East Park | Periplum / AL / GH | bar: 2017-05-01
11398 | Pending | Creative | Prop making | 5. Davy & Kristin McGuire's Cardboard City |  | 2017-05-04 | *Milestones | *Milestones | DM / MM | bar: 2017-05-01
10494 | Provisional | Event | Project Live | 1. Periplum - 7 Alleys | 2017-05-03 | 2017-05-06 | Hull East | East Park | ALL | bar: 2017-05-01
11433 | Provisional | Production | Get Out | 1. Periplum - 7 Alleys | 2017-05-06 | 2017-05-08 | Hull East | East Park | Periplum / AL / GH | bar: 2017-05-01 to 2017-05-08
11399 | Pending | Creative | Filming begins | 5. Davy & Kristin McGuire's Cardboard City |  | 2017-05-08 | *Milestones | *Milestones | DM / MM | bar: 2017-05-08
| Provisional | Marcomms | Crates found marked 'GNGG Bransholme' | 2. Joshua Sofaer's Nobody Nose | 2017-05-08 | 2017-05-14 |  |  | CL | bar: 2017-05-08
11383 | Pending | Production | Set build | 2. Joshua Sofaer's Nobody Nose | 2017-05-08 | 2017-06-05 | *Milestones | *Milestones | JS / AL | bar: 2017-05-08 to 2017-06-05
| Provisional | Crates | Discovery of crate in Margaret's allotment | 3. Lone Twin's The Guild of Commoners | 2017-05-15 | 2017-05-21 |  |  | CL | bar: 2017-05-15
10615 | Provisional | Crates | Crates delivered [T&O] | 2. Joshua Sofaer's Nobody Nose | 2017-05-15 | 2017-05-21 | Hull North | North Point Shopping Centre | GH / CL | bar: 2017-05-15
| Provisional | Community Engagement | Recruitment of Guild | 3. Lone Twin's The Guild of Commoners | 2017-05-15 | 2017-06-23 |  |  | Lone Twin / MM | bar: 2017-05-15 to 2017-06-19
11401 | Pending | Creative | Set building begins | 5. Davy & Kristin McGuire's Cardboard City |  | 2017-06-12 | *Milestones | *Milestones | DM / AL | bar: 2017-06-12
| Provisional | Creative | Volunteer Training | 2. Joshua Sofaer's Nobody Nose | 2017-06-16 | 2017-06-16 |  |  | JS / EB | bar: 2017-06-12
10616 | Pending | Event | Opening ceremony | 2. Joshua Sofaer's Nobody Nose | 2017-06-17 | 2017-06-17 | Hull North | North Point Shopping Centre | ALL | bar: 2017-06-12
| Pending | Event | Project Live - Shop Open | 2. Joshua Sofaer's Nobody Nose | 2017-06-17 | 2017-08-19 |  |  | JS | bar: 2017-06-12 to 2017-08-14
| Provisional | Heralding | Initial heralding of VEARO apparatus | 4. Aswarm - Re-Rediffussion | 2017-06-24 | 2017-06-24 |  |  | CL | bar: 2017-06-19
11400 | Pending | Creative | Filming ends | 5. Davy & Kristin McGuire's Cardboard City |  | 2017-06-30 | *Milestones | *Milestones | DM / MM | bar: 2017-06-26
11402 | Pending | Creative | Editing, compositing & animation begins | 5. Davy & Kristin McGuire's Cardboard City |  | 2017-07-03 | *Milestones | *Milestones | DM | bar: 2017-07-03
| Provisional | Community Engagement | Voice Collection | 4. Aswarm - Re-Rediffussion | 2017-07-03 | 2017-07-31 |  |  | TB-M / LY | bar: 2017-07-03 to 2017-07-24
| Provisional | Event | Suite of Artworks Open | 3. Lone Twin's The Guild of Commoners | 2017-07-15 | 2017-07-23 |  |  | Lone Twin / MM | bar: 2017-07-10 to 2017-07-17
12768 | Provisional | Event | Finale | 3. Lone Twin's The Guild of Commoners | 2017-07-22 | 2017-07-23 | Hull East | Longhill Estate | Lone Twin / MM | bar: 2017-07-17
12769 | Provisional | Event | Finale | 3. Lone Twin's The Guild of Commoners | 2017-07-22 | 2017-07-23 | Hull East | Longhill Estate | Lone Twin / MM | bar: 2017-07-17
11403 | Pending | Creative | Set components made | 5. Davy & Kristin McGuire's Cardboard City |  | 2017-08-01 | *Milestones | *Milestones | DM | bar: 2017-07-31
10617 | Pending | Event | closing parade | 2. Joshua Sofaer's Nobody Nose | 2017-08-19 | 2017-08-19 | Hull North | North Point Shopping Centre | JS / LY | bar: 2017-08-14
| Pending | Production | Strike set and return shop to former state | 2. Joshua Sofaer's Nobody Nose | 2017-08-20 | 2017-09-03 |  |  | JS / AL | bar: 2017-08-14 to 2017-08-28
11404 | Pending | Creative | Editing complete | 5. Davy & Kristin McGuire's Cardboard City |  | 2017-08-31 | *Milestones | *Milestones | DM | bar: 2017-08-28
| Pending | Production | Return shop keys | 2. Joshua Sofaer's Nobody Nose | 2017-09-04 | 2017-09-04 |  |  | JS / AL | bar: 2017-09-04
| Provisional | Heralding | Second heralding | 4. Aswarm - Re-Rediffussion | 2017-09-09 | 2017-09-10 |  |  | CL | bar: 2017-09-04
11405 | Pending | Crates | Heralding activity begins | 5. Davy & Kristin McGuire's Cardboard City |  | 2017-09-18 | *Milestones | *Milestones | CL | bar: 2017-09-18
| Provisional | Event | Project Live | 4. Aswarm - Re-Rediffussion | 2017-09-23 | 2017-10-01 |  |  | TB-M / LY / AL | bar: 2017-09-18 to 2017-09-25
| Provisional | Event | Project Live | 5. Davy & Kristin McGuire's Cardboard City | 2017-10-09 | 2017-10-21 |  |  | DM / MM / AL | bar: 2017-10-09 to 2017-10-16
12766 | Provisional | Event |  | 6. Macnas title TBC |  | 2017-11-10 | Hull City Centre | Hull City Centre | Macnas / LY / GH / AL | bar: 2017-11-06
12767 | Provisional | Event |  | 6. Macnas title TBC |  | 2017-11-11 | Hull City Centre | Hull City Centre | Macnas / LY / GH / AL | bar: 2017-11-06
2428 | Pending | All | 2017 Projects End (TBC) | Land of Green Ginger (Umbrella) |  | 2017-11-30 | *Milestones | *Milestones | ALL | bar: 2017-11-27
7823 | Pending | Book | 2017 PLANNING: Writer/Illustrator Brief Prepared | Land of Green Ginger (Umbrella) |  | 2017-11-30 | *Milestones | *Milestones | ALL | bar: 2017-11-27
7822 | Pending | Book | 2017 PLANNING: Writer/Illustrator approached | Land of Green Ginger (Umbrella) |  | 2017-12-04 | *Milestones | *Milestones | ALL | bar: 2017-12-04
7824 | Pending | Book | 2017 PLANNING: Writer/Illustrator secured | Land of Green Ginger (Umbrella) |  | 2017-12-18 | *Milestones | *Milestones | ALL | bar: 2017-12-18
2429 | Pending | Milestones | Culmination Project Begins (TBC) | Land of Green Ginger (Umbrella) |  | 2018-01-02 | *Milestones | *Milestones | ALL | bar: 2018-01-01
2430 | Pending | Milestones | Culmination Project Ends (TBC) | Land of Green Ginger (Umbrella) |  | 2018-03-01 | *Milestones | *Milestones | ALL