## Agenda
THE LAST TESTAMENT OF LILLIAN BILOCCA
Project Team Meetings
AGENDA ITEM | NOTES / ACTIONS | INITIALS
PRODUCTION MANAGEMENT
CREATIVE / ARTIST
PRODUCTION / TECHNICAL
VENUE
STAFFING
BUDGET
ADMIN / CONTRACTS
MARCOMMS
COMMUNITY COMPANY
MISC

## 05.09.17
THE LAST TESTAMENT OF LILLIAN BILOCCA
Project Team Meetings
AGENDA ITEM | NOTES / ACTIONS | INITIALS
PROJECT MANAGEMENT | Final risk register, roles breakdown to be agreed | LA / EJ
| Organogram to be shared with LA, BP & AR | RA
CREATIVE / ARTISTIC | Check plans for first day of rehearsals with Sarah | LA
| Establish number of child performers per show, rehearsal model & audition process with Sarah | LA
| Conversation re JB role with community company & performance role with Sarah. Offer fee top up | LA
PRODUCTION / TECHNICAL | No notes
VENUE | Insurance feedback to EJ | AC / LA / PB
| New route to be confirmed with creative team and circulated to all | BP
| Unison still proving difficult to reach. PB to pick up this conversation. LA sourced email contact | PB
| Venue contract & deal negotiation to pick up next week | LA
| BP talking to venues adjacent re technical matters & lighting | BP
| Schedule to be added as outlook diary & info re weddings to be circulated to BP & AC | RA / LA
STAFFING | Volunteering - on next weeks agenda. Volunteering meeting next week. LA to arrange. | all / LA
| DSM recruitment was disappointing and no suitable candidates. BP to speak to SF re 2 ASMs | BP
BUDGET | Assistants & makers line has been ammended | EJ
| Factor in JB top up fee | EJ
| Accommodation to be reviewed with KN. Budget to be reviewed | EJ
| EJ & LA to discuss budget on Thurs | EJ / LA
ADMIN / CONTRACTS | Sarah & Fi's contracts have been issued
| Actor contracts & riders to be drafted by KN for input | KN / EJ / LA / AC
| Digs lists to be sent out asap . Completed subsequent to meeting. | KN / EJ
| Press contacts to be shared with KN for contact sheet | LA
MARCOMMS | Community cast tickets need to be released by 02.10.17 | AR / RP
| Staff category to be reviewed in project meeting next week | all
| Counsellors to be accommodated. HTT usually invite all 70 but low attendance. Agreed we can accommodate councellors somewhere 1 ticket each - dates TBC. Guildhall staff to attend dress. | RP
| Relationship to be explored with Kardomeh as production bar & hosting press night. In kind support for posters etc in return for custom | PB
| Access conversation taken place with George at Council. They can provide scooter & wheelchair. Audio description is happening. Captioned show is dependent on wifi. Ben leading on wifi conversation. Confirm details by end of Sept. | PB / BP
COMMUNITY COMPANY | Molly & Rach to support admin of applications on Fri as required. JB av all Sat should additional slots be required. AR to allocate slots on Fri. HTT to provide Ipad for filming. PB to cover fire evac and H&S info. JB to provide usual welcome briefing. AR to read all health forms, flag any issues with JB and sign. | PB / AR / RA / MS
| Letter to be reviewed by EJ and sent out | EJ / LA / AR
| Rehearsal space to be confirmed next week | EJ / AC
| Community engagement plan to be circulated next week | RP
MISC