## ACE report
Hull 2017
Turner Prize 2017 at Ferens Art Gallery | [5 empty] | Summary Project Budget & Expenditure to date until 7.11.17
Description | Projected Budget | Actual expenditure | Actual income | Projected expenditure | Projected income | Revised Budget | Difference | Comments
ARTS COUNCIL ENGLAND INCOME |  |  | 350000 |  | 150000
Core Project Team - Curator, Project Manager, Project Assistant | 78000 | 57330 |  | 6520 |  | 63850 | -14150 | Project Manager left project in October. Workload picked up by team.
Admin | 4500 | 12076 |  | 848 |  | 12924 | 8424 | Increased travel costs to view international nominated exhibitions. Andrea in Berlin.
Fees
Artist participation fees - winner | 25000 |  |  | 25000 |  | 25000 | 0
Artist participation fees | 15000 |  |  | 15000 |  | 15000 | 0
Education
Access Initiatives | 5000 | 360 |  | 710 |  | 1070 | -3930 | Access built into community project expenditure
Public community programme | 17000 | 1840 |  | 23538 |  | 25378 | 8378
Events & Activities | 21750 |  |  | 14600 |  | 14600 | -7150
Events & External Relations | 50000 | 8858 |  | 49762 |  | 58620 | 8620 | Balance with opening event
Press & Marketing
Press preview | 10500 | 4134 |  | 766 |  | 4900 | -5600 | Balance with opening event
Artists films | 8000 |  |  | 4750 |  | 4750 | -3250
Photography | 2000 |  |  | 3500 |  | 3500 | 1500
Print production | 6000 | 3789 |  |  |  | 3789 | -2211
Publication | 34000 | 5891 |  | 30 |  | 5921 | -28079 | This is exhibiton catalogue - other printing and publications costs in marketing budget below
Marketing & Advertising campaign | 15000 | 22210 |  | 30054 |  | 52264 | 37264 | Advertising campaign - Train stations, near galleries - Baltic, Hepworth, adverts in magazine
Production
Exhibition Build | 65000 | 99632 |  | 25209 |  | 124841 | 59841 | Cat - below
Logistics - transport in/out | 20000 | 16512 |  | 14283 |  | 30795 | 10795
Artwork production | 48244 | 1963 |  |  |  | 1963 | -46281 | Yellow wall - Andrea, cinema
Technicians install/de-install | 30000 | 11349 |  | 24846 |  | 36195 | 6195
Security / FOH / Maintenances incl volunteer costs | 38000 |  |  | 28490 |  | 28490 | -9510 | Paid v volunteers - key appointment of supervisor staff = saving.
TOTALS |  | 245944 | 350000 | 267906 | 150000 | 513850 | 513850

## Sheet3
Data
ACE reporting category | Sum of Actual spend | Sum of Projected spend | Sum of Amount
Access initiatives | 360 | 709.61 | 1069.61
Admin | 12076.03 | 847.92 | 12923.95
Artist participation fees |  | 15000 | 15000
Artist participation fees (Winner) | 0 | 25000 | 25000
Artwork production | 1962.5 | 0 | 1962.5
Events & activities | 0 | 14600 | 14600
Events & external relations | 8857.64 | 49762.4 | 58620.04
Exhibition build | 99631.68 | 25209.14 | 124840.82
Logistics | 16511.85 | 14283.07 | 30794.92
Marketing & Advertising campaign | 22209.5 | 30053.5 | 52263
Photography | 0 | 3500 | 3500
Press preview | 4134 | 766 | 4900
Print production | 3788.65 | 0 | 3788.65
Public community programme | 1840 | 23538 | 25378
Publication | 5891 | 30 | 5921
Security/FOH etc |  | 28493.12 | 28493.12
Technicians install/de-install | 11348.5 | 24845.89 | 36194.39
(empty) | 2.8422e-13 | -2.8422e-13 | 0
Artists films |  | 4750 | 4750
Total Result | 188611.35 | 261388.65 | 450000

## Budget as at 07.11.17
TURNER PRIZE WORKING BUDGET - C070 |  |  |  | 436150
[6 empty] | This to always be zero | -13850
VERSION 2
Cost Centre | Sub code | Analysis code | Item | Notes | Calculation | Amount | TOTAL BUDGET ALLOCATED | Actual spend | Projected spend | ACE reporting category
[5 empty] | Allocated budget |  | 436150
[5 empty] | Working budget |  | 450000
|  |  | ARTIST FEES |  |  |  | 40000
ZK101 | K207 | C070 | Artist Fees - WINNER | £25K paid to Tate |  | 25000 |  | 0 | 25000 | Artist participation fees (Winner)
ZK101 | K207 | C070 | Artist Fees - Runner Up | £5k paid to 3 nominated artists |  | 15000 |  |  | 15000 | Artist participation fees
|  |  | ARTIST EXPENSES |  |  |  | 10162.42
ZK103 | K226 | C070 | Accommodation Install |  |  | 0 |  | 2.8422e-13 | -2.8422e-13
ZK103 | K226 | C070 | Zest Apartments for Install and Opening - Daniel Pies, Jochen, Hurvin, Rosalind and Andrea |  |  | 2645 |  | 2645 | 0 | Exhibition build
ZK103 | K226 | C070 | Install/Opening Apartments for Lubaina and Assistants 17/09-20/09 and 24/09-27/09 |  |  | 900 |  | 900 | 0 | Exhibition build
ZK103 | K226 | C070 | Deposit on Apartments to be refunded |  |  | 900 |  | 900 | 0 | Exhibition build
ZK103 | K226 | C070 | Deposit on Apartments to be refunded |  |  | -900 |  | -900 | 0 | Exhibition build
ZK103 | K226 | C070 | Travel Install | 4 people @£100 each |  | 0 |  |  | 0 | Exhibition build
ZK103 | K226 | C070 | Jochen Schmidt Trains Manchester > Hull for Peace Library install |  |  | 60.18 |  | 60.18 | 0 | Exhibition build
ZK103 | K226 | C070 | Hurvin Train Huntingdon>Hull on Friday 8th September to choose paint colour |  |  | 57.78 |  | 57.78 | 0 | Exhibition build
ZK103 | K226 | C070 | Daniel Pies Trains Manchester Airport > Hull Return |  |  | 60.18 |  | 60.18 | 0 | Exhibition build
ZK103 | K226 | C070 | Lubaina Trains Preston > Hull Return x2 for Install and Opening |  |  | 128.56 |  | 128.56 | 0 | Exhibition build
ZK103 | K226 | C070 | Rosalind Trains London > Hull Return for Install and Opening (one trip) |  |  | 109.18 |  | 109.18 | 0 | Exhibition build
ZK103 | K226 | C070 | Rosalind Trains London > Hull Return for paint checking |  |  | 88.98 |  | 88.98 | 0 | Exhibition build
ZK103 | K226 | C070 | Arts Council Collection train Barnsley > Hull for Hurvin Install |  |  | 32.58 |  | 32.58 | 0 | Exhibition build
ZK103 | K226 | C070 | Rosalind trains to London return during Install |  |  | 83.08 |  | 83.08 | 0 | Exhibition build
ZK103 | K226 | C070 | Jochen Schmidt Flights Berlin > Manchester for Peace Library install |  |  | 119.25 |  | 119.25 | 0 | Exhibition build
ZK103 | K226 | C070 | Daniel Pies reimbursement of land travel in Frankfurt | 41 EUROS |  | 41.86 |  | 41.86 | 0 | Exhibition build
ZK103 | K226 | C070 | Daniel Pies Flight Frankfurt > Manchester Return, 11.09-16.09 for Andrea Install |  |  | 446.95 |  |  | 446.95 | Exhibition build
ZK103 | K226 | C070 | Hurvin Train Huntingdon>Hull for Install |  |  | 76.18 |  | 76.18 | 0 | Exhibition build
ZK101 | K245 | C070 | Translation of Simeone Weil’s Peace Library for Turner Prize exhibition | Andrea Buttner |  | 430.94 |  | 430.94 | 0 | Exhibition build
ZK101 | K245 | C070 | Lenders fee for Peace Library | 1000 euros |  | 883.34 |  |  | 883.34 | Exhibition build
ZK101 | K245 | C070 | Peace Library hand-writing fee for Freelancer | 550 euros |  |  |  |  | 0 | Exhibition build
ZK103 | K225 | C070 | Artists site visit-travel & accommodation |  |  | 0 |  | 1.9185e-13 | -1.9185e-13 | Exhibition build
ZK103 | K225 | C070 | 70023212 L Mellor |  |  | 2.55 |  | 2.55 | 0 | Exhibition build
ZK103 | K225 | C070 | Andrea Buttner (reservation number: 61303983) arriving 30th May and departing 1st June 2017. |  |  | 168.34 |  | 168.34 | 0 | Exhibition build
ZK103 | K225 | C070 | Andrea Buttner flights Frankfurt > London Return. Outbound 30th May, Return 2nd June 2017. Andrea Buttner trains London > Hull return. Outbound 30th May, return 1st June 2017. |  |  | 335.68 |  | 335.68 | 0 | Exhibition build
ZK103 | K225 | C070 | C Drury Credit Card May'17 |  |  | 21.78 |  | 21.78 | 0 | Exhibition build
ZK103 | K225 | C070 | Hurvin Anderson train Huntingdon > Hull return. |  |  | 81.78 |  | 81.78 | 0 | Exhibition build
ZK103 | K225 | C070 | Manchester Airport hotel for Rosalind Nashashibi, 1st June 2017 after artists' visit to Hull. |  |  | 122.5 |  | 122.5 | 0 | Exhibition build
ZK103 | K225 | C070 | Rosalind Nashashibi (reservation number: 61317266) Hurvin Anderson (reservation number: 61322994) Lubaina Himid (reservation number: 61330519). All arriving 31st May and departing 1st June 2017. |  |  | 252.5 |  | 252.5 | 0 | Exhibition build
ZK103 | K225 | C070 | Rosalind Nashashibi train London > Hull 31/05/2017. Rosalind Nashashibi train Hull > Manchester airport 01/06/2017. Lubaina Himid train London > Hull 31/05/2017. Lubaina Himid train Hull > Preston 01/06/2017. |  |  | 133.62 |  | 133.62 | 0 | Exhibition build
ZK103 | K225 | C070 | Trains for Sara Black - Truro to London Paddington 21st May |  |  | 43.98 |  | 43.98 | 0 | Exhibition build
ZK103 | K225 | C070 | Hurvin Anderson train Huntingdon > Hull for Ferens site visit, 25 July 2017 |  |  | 76.17 |  | 76.18 | -0.01 | Exhibition build
ZK103 | K227 | C070 | Artists hosting/liaison: |  |  | 0 |  | 0 | 0 | Exhibition build
ZK103 | K227 | C070 | Artists Dinner 24 Sept |  |  | 483.4 |  |  | 483.4 | Exhibition build
ZK103 | K227 | C070 | Per diems for Daniel Pies and Jochen Schmidt, £100 and £117.50 |  |  | 217.5 |  | 217.5 | 0 | Exhibition build
ZK103 | K227 | C070 | 70020672 K Fuller |  |  | 448.19 |  | 448.19 | 0 | Exhibition build
ZK103 | K227 | C070 | C Drury Credit Card May'17 |  |  | 228.5 |  | 228.5 | 0 | Exhibition build
ZK103 | K227 | C070 | Tech Petty Cash Claim 8 |  |  | 90 |  | 90 | 0 | Exhibition build
ZK103 | K227 | C070 | Expenses for Artists Lunch - Turner Prize |  |  | 296.74 |  | 296.74 | 0 | Exhibition build
ZK103 | K227 | C070 | Wine order (24 bottles) for Turner Prize artists drinks reception at Humber Street Gallery, 31 May 2017. | Actual spend as at 10.07.17 (to be entered via correcting journal) |  | 101.76 |  | 101.76 | 0 | Exhibition build
ZK103 | K227 | C070 | Lunch for BBC and Artists during Andrea filming |  |  | 31.55 |  | 31.55 | 0 | Exhibition build
ZK114 | K299 | C070 | Credit re House of Townend | Actual spend as at 10.07.17 (to be entered via correcting journal) |  | -38.16 |  | -38.16 | 0 | Exhibition build
|  |  | EXHIBITION PRODUCTION |  |  |  | 189731.19
ZK106 | K244 | C070 | Exhibition Design | DAVID KOHN ARCHITECT |  | 1 |  | 0 | 1 | Technicians install/de-install
ZK106 | K244 | C070 | Technicians Install |  |  | 0 |  |  | 0 | Technicians install/de-install
ZK106 | K244 | C070 | Gareth Fee for labour and materials (Lubaina plinth/wall, Andrea wall)-includes gallery 10 | To be paid to HCAL |  | 8823.77 |  |  | 8823.77 | Technicians install/de-install
ZK106 | K244 | C070 | WOOD | Paid on credit card |  | 925.33 |  |  | 925.33 | Technicians install/de-install
ZK106 | K244 | C070 | Additional wood order 06.09 |  |  | 364.73 |  |  | 364.73 | Technicians install/de-install
ZK106 | K244 | C070 | HCAL Technicians, Rehanging of Collection | To be paid to HCAL |  | 7124.74 |  |  | 7124.74 | Technicians install/de-install
ZK106 | K244 | C070 | HCAL Technician Simon Harvey |  |  | 2464.5 |  |  | 2464.5 | Technicians install/de-install
ZK106 | K244 | C070 | Extra HCAL techs for art handling / Andrea's wall rebuild - Harminder |  |  | 900 |  |  | 900 | Technicians install/de-install
ZK106 | K244 | C070 | HCAL Keyholders overtime |  |  | 491.82 |  |  | 491.82 | Technicians install/de-install
ZK106 | K244 | C070 | David Kohn Expenses inc. model making |  |  | 232.5 |  | 232.5 | 0 | Technicians install/de-install
ZK106 | K249 | C070 | ADI Fee for time and AV, Rosalind's room |  |  | 11116 |  | 11116 | 0 | Technicians install/de-install
ZK106 | K249 | C070 | ADI for screens and headphones for central court Bureau |  |  | 1930 |  | 1930 | 0 | Exhibition build
ZK106 | K245 | C070 | Exhibition Build |  |  |  |  | 3.7517e-12 | -3.7517e-12 | Exhibition build
ZK106 | K245 | C070 | Sewells Fee for time and materials (Rosalind room) |  |  | 39288.67 |  | 39288.67 | 0 | Exhibition build
ZK106 | K245 | C070 | Sewell Group - All works |  |  | 30137.68 |  | 30137.68 | 0 | Exhibition build
ZK106 | K245 | C070 | Litestructures building of Andrea tables x2 | Invoice 1 |  | 2292.5 |  | 2292.5 | 0 | Exhibition build
ZK106 | K245 | C070 | Petty Cash |  |  | 500 |  | 493.78 | 6.22 | Exhibition build
|  |  | Tech Petty Cash Claim 11 |  |  | 49.16 |  | 49.16 | 0 | Exhibition build
|  |  | Tech Petty Cash Claim 12 |  |  | 86.22 |  | 86.22 | 0 | Exhibition build
ZK106 | K245 | C070 | Surge Fabric/Curtains for film room | Supplier-J D McDougall |  | 344.58 |  | 344.58 | 0 | Exhibition build
ZK106 | K245 | C070 | Additional yellow fabric and courier |  |  | 309.48 |  | 309.48 | 0 | Exhibition build
ZK106 | K245 | C070 | Lily expenses - Posting of Crown colours and fabric samples to artists |  |  | 16.8 |  | 16.8 | 0 | Exhibition build
ZK106 | K245 | C070 | Andrea Blue Painting - JohnJones Stretcher |  |  | 648.07 |  | 648.07 | 0 | Exhibition build
ZK106 | K245 | C070 | John Jones-due credit as didn’t do all work |  |  | -110 |  |  | -110 | Exhibition build
ZK106 | K245 | C070 | Yellow and Blue Fabric for Andrea Install |  |  | 121.5 |  |  | 121.5 | Exhibition build
ZK106 | K245 | C070 | Molton Fabric x2 rolls |  |  | 989.28 |  |  | 989.28 | Exhibition build
ZK106 | K245 | C070 | Structural engineer costs for Rosalind's room - reimbursement for DKA |  |  | 1872.5 |  |  | 1872.5 | Exhibition build
ZK106 | K245 | C070 | Rick from Arts Council Collection train to Hull for Hurvin install |  |  | 32.48 |  |  | 32.48 | Exhibition build
ZK106 | K245 | C070 | Additional Insurance Premium |  |  | 609.67 |  |  | 609.67 | Exhibition build
ZK106 | K245 | C070 | Install materials bought by HCAL techs | To be paid to HCAL |  | 69.72 |  |  | 69.72 | Exhibition build
ZK106 | K245 | C070 | Vinyl's | [5 empty] | 0 | Exhibition build
ZK106 | K245 | C070 | Replacement vinyl in high tack (remaining artists) |  |  | 158 |  |  | 158 | Exhibition build
ZK106 | K245 | C070 | Lubaina replacement wall text, Ferens techs to install |  |  | 30 |  |  | 30 | Exhibition build
ZK106 | K245 | C070 | Rosalind high tack vinyl, print and install |  |  | 100 |  |  | 100 | Exhibition build
ZK106 | K245 | C070 | Catalogue for Sale door vinyl for G5/Café - TO BE REIMBURSED BY HCAL |  |  | 30 |  |  | 30 | Exhibition build
ZK106 | K245 | C070 | Catalogue for Sale door vinyl for G5/Café - TO BE REIMBURSED BY HCAL |  |  | -30 |  |  | -30 | Exhibition build
ZK106 | K245 | C070 | Catalogue for Sale door vinyl for G5/Café - TO BE REIMBURSED BY HCAL |  |  | 54 |  | 54 | 0 | Exhibition build
ZK106 | K245 | C070 | Catalogue for Sale door vinyl for G5/Café - TO BE REIMBURSED BY HCAL |  |  | -54 |  |  | -54 | Exhibition build
ZK106 | K245 | C070 | Re-prints and installation costs of Vinyl's with updates/mistakes |  |  | 304 |  | 304 | 0 | Exhibition build
ZK106 | K245 | C070 | Design of additional vinyl for Studio Foyer wall |  |  | 30 |  | 30 | 0 | Exhibition build
ZK106 | K245 | C070 | Print and install of additional vinyl for Studio Foyer wall |  |  | 252 |  | 252 | 0 | Exhibition build
ZK106 | K245 | C070 | Wall interpretation print |  |  | 2291 |  | 2291 | 0 | Exhibition build
ZK106 | K245 | C070 | Wall panels for interpretation text - Design |  |  | 420 |  |  | 420 | Exhibition build
ZK106 | K245 | C070 | Wall panels for interpretation text - Extra hours |  |  | 495 |  |  | 495 | Exhibition build
ZK106 | K245 | C070 | Vinyl for G4 new collection hang |  |  | 180 |  |  | 180 | Exhibition build
ZK106 | K245 | C070 | Install painting of Galleries 4-9 and Live Art Foyer |  |  | 5048 |  |  | 5048 | Exhibition build
ZK106 | K245 | C070 | Additional install paint costs |  |  | 2653.2 |  |  | 2653.2 | Exhibition build
ZK106 | K245 | C070 | More paint costs 06.10 |  |  | 1742.4 |  |  | 1742.4 | Exhibition build
ZK106 | K245 | C070 | Caroline Hooper, Copy editing of wall texts and broadsheet, £45 an hour @11.5 hours |  |  | 517.5 |  | 517.5 | 0 | Exhibition build
ZK106 | K245 | C070 | Postage of physical loan forms |  |  | 2.75 |  | 2.75 | 0 | Exhibition build
ZK106 | K245 | C070 | Seats for Rosalind's Cinema Install - Ten Rows of Five (50 Seats in Total) |  |  | 3000 |  | 3000 | 0 | Exhibition build
ZK106 | K245 | C070 | material for Turner Prize (SP PN Profabrics & Nochex) | Paid on credit card |  | 9 |  | 9 | 0 | Exhibition build
ZK106 | K258 | C070 | Jayhawk Shipment - all lenders to Hull | Includes 8.5% dicsount |  | 11195 |  | 11195.02 | -0.02 | Logistics
ZK106 | K258 | C070 | Border clearance costs for LA Andrea's tables (Outbound) |  |  | 413.33 |  |  | 413.33 | Logistics
ZK106 | K258 | C070 | DHL |  |  | 2690.63 |  | 2690.63 | 0 | Logistics
ZK106 | K258 | C070 | Martinspeed Hurvin Anderson shipment ACC |  |  | 2626.2 |  | 2626.2 | 0 | Logistics
ZK106 | K258 | C070 | Litestructures building of Andrea tables x2 | Invoice 2 |  | 1962.5 |  | 1962.5 | 0 | Artwork production
ZK106 | K281 | C070 | Exhibition Interpretation material |  |  | 0 |  | 0 | 0 | Exhibition build
ZK106 | K281 | C070 | Extra design costs for Broadsheet 1 |  |  | 180 |  |  | 180 | Exhibition build
ZK106 | K281 | C070 | Broadsheet 2 1x8 x20,000 |  |  | 3249 |  |  | 3249 | Exhibition build
ZK106 | K281 | C070 | 2000x badges for Opening, Volunteers |  |  | 980 |  | 980 | 0 | Exhibition build
ZK106 | K281 | C070 | Design of badges |  |  | 25 |  | 25 | 0 | Exhibition build
ZK106 | K281 | C070 | Broadsheet 1 1x8 x50,000 |  |  | 4760 |  | 4760 | 0 | Exhibition build
ZK106 | K281 | C070 | Marino Gamper Stools |  |  | 270 |  | 270 | 0 | Exhibition build
ZK106 | K281 | C070 | Resource Area Books |  |  | 250 |  |  | 250 | Exhibition build
ZK106 | K281 | C070 | Resource Area /paper for comments / all other interp costs | [5 empty] | 0 | Exhibition build
ZK106 | K281 | C070 | Paper for comments |  |  | 306.5 |  |  | 306.5 | Exhibition build
ZK106 | K224 | C070 | David Kohn Extra Hours |  |  | 3799.74 |  | 3799.75 | -0.01 | Exhibition build
ZK106 | K224 | C070 | Gallery Supervisors | To be paid to HCAL |  | 20113.05 |  |  | 20113.05 | Security/FOH etc
ZK106 | K224 | C070 | September 2017 Salaries |  |  | 1993.12 |  |  | 1993.12 | Security/FOH etc
ZK106 | K224 | C070 | October 2017 Salaries inc. overtime for TP Opening |  |  | 6386.95 |  |  | 6386.95 | Security/FOH etc
|  |  | MARKETING |  |  |  | 68648.25
ZK109 | K005 | C070 | Recharge for two frosted vinyls (from HCAL) |  |  | -84 |  | -84 | 0 | Exhibition build
ZK109 | K138 | C070 | Catalogue Print & Delivery |  |  | 4901 |  | 4901 | 0 | Publication
ZK109 | K138 | C070 | Catalogue Design |  |  | 360 |  | 360 | 0 | Publication
ZK109 | K138 | C070 | Caroline Hooper, Copy editing of Catalogue, £45 an hour @ 14 hours |  |  | 630 |  | 630 | 0 | Publication
ZK109 | K270 | C070 | Visual Identity Design - Turner Prize 2017 |  |  | 800 |  | 825 | -25 | Marketing & Advertising campaign
ZK109 | K270 | C070 | Digital Assets |  |  | 270 |  | 270 | 0 | Marketing & Advertising campaign
ZK109 | K270 | C070 | Design and Print of posters for Hull City Centre |  |  | 105.5 |  | 105.5 | 0 | Print production
ZK109 | K270 | C070 | Web add banner for VHEY |  |  | 15 |  | 15 | 0 | Marketing & Advertising campaign
ZK109 | K270 | C070 | Header and Footer for Word Template |  |  | 30 |  | 30 | 0 | Marketing & Advertising campaign
ZK109 | K270 | C070 | Redirection of Hollybush catalogues |  |  | 30 |  |  | 30 | Publication
ZK109 | K270 | C070 | Screen artwork for opening |  |  | 25 |  | 25 | 0 | Events & external relations
ZK109 | K270 | C070 | A5 advert for Marathon programme |  |  | 37.5 |  |  | 37.5 | Marketing & Advertising campaign
ZK109 | K302 | C070 | 48 sheet and 6 sheet outdoor and digital outdoor |  |  | 0 |  | 450 | -450 | Marketing & Advertising campaign
ZK109 | K302 | C070 | York Station |  |  | 2200 |  |  | 2200 | Marketing & Advertising campaign
ZK109 | K302 | C070 | Leeds Bradford Airport |  |  | 3500 |  |  | 3500 | Marketing & Advertising campaign
ZK109 | K302 | C070 | Client Media Buying (whole process) | Hull city council |  | 1500 |  |  | 1500 | Marketing & Advertising campaign
ZK109 | K302 | C070 | HCC 6 sheets |  |  | 1500 |  |  | 1500 | Marketing & Advertising campaign
ZK109 | K302 | C070 | Media Design & Artwork | [5 empty] | 0 | Marketing & Advertising campaign
ZK109 | K302 | C070 | Covering key sites in train stations and near galleries in: Sheffield, Leeds, Salford, Wakefield, Liverpool, Newcastle and York. |  |  | 19215 |  | 19215 | 0 | Marketing & Advertising campaign
ZK109 | K302 | C070 | Artwork for Execution of full media plan |  |  | 322 |  | 322 | 0 | Marketing & Advertising campaign
ZK109 | K302 | C070 | Design of artwork for Blast magazine |  |  | 25 |  | 25 | 0 | Marketing & Advertising campaign
ZK109 | K302 | C070 | Additional design costs for Turner Prize media adds |  |  | 300 |  | 300 | 0 | Marketing & Advertising campaign
ZK109 | K302 | C070 | Design of artwork for marathon programme |  |  | 37.5 |  | 37.5 | 0 | Marketing & Advertising campaign
ZK109 | K302 | C070 | Design of artwork for TPE sites |  |  | 75 |  | 75 | 0 | Marketing & Advertising campaign
ZK109 | K302 | C070 | Design of first 48 sheet |  |  | 120 |  | 120 | 0 | Marketing & Advertising campaign
ZK109 | K132 | C070 | Specialist Arts Publications |  |  | 0 |  | 0 | 0 | Marketing & Advertising campaign
ZK109 | K132 | C070 | The Skinny |  |  | 895 |  |  | 895 | Marketing & Advertising campaign
ZK109 | K132 | C070 | Art Monthly |  |  | 1195 |  |  | 1195 | Marketing & Advertising campaign
ZK109 | K132 | C070 | Frieze |  |  | 1930 |  |  | 1930 | Marketing & Advertising campaign
ZK109 | K132 | C070 | Art Review |  |  | 1300 |  |  | 1300 | Marketing & Advertising campaign
ZK109 | K132 | C070 | Newspaper/Magazine Advertising |  |  | 0 |  |  | 0 | Marketing & Advertising campaign
ZK109 | K132 | C070 | Beverley Advertiser |  |  | 376 |  |  | 376 | Marketing & Advertising campaign
ZK109 | K132 | C070 | Hull Daily Mail Website |  |  | 1000 |  |  | 1000 | Marketing & Advertising campaign
ZK109 | K132 | C070 | Hull Journal |  |  | 375 |  |  | 375 | Marketing & Advertising campaign
ZK109 | K132 | C070 | Grimsby/Scunthorpe Telegraph |  |  | 525 |  | 525 | 0 | Marketing & Advertising campaign
ZK109 | K132 | C070 | Yorkshire Post Magazine |  |  | 2000 |  |  | 2000 | Marketing & Advertising campaign
ZK109 | K132 | C070 | Yorkshire Vision |  |  | 800 |  |  | 800 | Marketing & Advertising campaign
ZK109 | K132 | C070 | York Press |  |  | 1050 |  |  | 1050 | Marketing & Advertising campaign
ZK109 | K132 | C070 | Harrogate Advertiser |  |  | 620 |  |  | 620 | Marketing & Advertising campaign
ZK109 | K272 | C070 | Social Media Ad Campaign |  |  | 4000 |  | 0 | 4000 | Marketing & Advertising campaign
ZK109 | K272 | C070 | Specialist Arts Websites |  |  | 0 |  |  | 0 | Marketing & Advertising campaign
ZK109 | K272 | C070 | Guardian |  |  | 4000 |  |  | 4000 | Marketing & Advertising campaign
ZK109 | K272 | C070 | Corridor 8 |  |  | 800 |  |  | 800 | Marketing & Advertising campaign
ZK109 | K272 | C070 | thisistomorrow |  |  | 1450 |  |  | 1450 | Marketing & Advertising campaign
ZK109 | K273 | C070 | MISC MARKETING COSTS
ZK109 | K273 | C070 | Ferens Outside Banners Design and Print |  |  | 625 |  | 375 | 250 | Exhibition build
ZK109 | K273 | C070 | Ferens Outside banners Install and Delivery | to pay to HCAL |  | 120 |  |  | 120 | Exhibition build
ZK109 | K273 | C070 | Printed Folders |  |  | 605 |  | 605 | 0 | Print production
ZK109 | K273 | C070 | Tote Bags |  |  | 817.75 |  | 817.75 | 0 | Print production
ZK109 | K158 | C070 | Exhibition Photography 22nd |  |  | 500 |  | 0 | 500 | Photography
ZK109 | K158 | C070 | Install Photography |  |  | 500 |  |  | 500 | Photography
ZK109 | K158 | C070 | Photography of Artists at Install |  |  | 500 |  |  | 500 | Photography
ZK109 | K159 | C070 | Video of Exhibition |  |  | 750 |  | 0 | 750 | Photography
ZK109 | K159 | C070 | Artist Films | Sodium |  | 4750 |  |  | 4750 | Artists films
ZK109 | K159 | C070 | Turner//Return Photography and Video, Voxpops |  |  | 1250 |  |  | 1250 | Photography
|  |  | COMMS & PR |  |  |  | 8400
ZK109 |  | C070 | B&Q Fee | INCLUDED IN CORE BUDGET NOT PROJECT SPECIFIC |  | 0 |  | 0 | 0 | Press preview
ZK109 | K289 | C070 | Press Preview Travel | TRAINS FOR PR TRIP 25/9 25 RETURNS @ £100 |  | 3130 |  | 3130 | 0 | Press preview
ZK109 | K289 | C070 | Press Preview Travel - Additional Train London > Hull Returning 15:12 |  |  | 104 |  | 104 | 0 | Press preview
ZK109 | K289 | C070 | Staff Media Training |  |  | 900 |  | 900 | 0 | Press preview
ZK109 | K289 | C070 | Press review hospitality | REFRESHMENTS AT FERENS ON ARRIVAL & LUNCH x35 |  | 766 |  |  | 766 | Press preview
ZK109 | K289 | C070 | Press awards travel & accommodation | 10 PRESS OVERIGHT @ £100 / 10 PRESS TRAVEL @ £100 |  | 1375 |  |  | 1375 | Events & external relations
ZK109 | K289 | C070 | Ibis hotel for 5x press, one night |  |  | 625 |  |  | 625 | Events & external relations
ZK109 | K325 | C070 | WIFI |  |  | 500 |  |  | 500 | Events & external relations
ZK109 | K299 | C070 | Press Association Photography, David Levene | £800 fee plus train tickets |  | 1000 |  | 0 | 1000 | Events & external relations
|  |  | LEARNING & ENGAGEMENT |  |  |  | 43308.01
ZK110 | K187 | C070 | M&E |  |  | 0 |  | 0 | 0 | Access initiatives
ZK110 | K187 | C070 | Design of M & E postcard |  |  | 60 |  | 60 | 0 | Access initiatives
ZK110 | K187 | C070 | Evaluation postcards |  |  | 240 |  | 240 | 0 | Access initiatives
ZK110 | K278 | C070 | Access | BSL, FACILIATATED TOURS |  | 0 |  | 0 | 0 | Access initiatives
ZK110 | K278 | C070 | BSL Tours x2 inc. fee and travel |  |  | 60 |  | 60 | 0 | Access initiatives
ZK110 | K278 | C070 | Audio Descriptive Tours x3 inc. fee and travel |  |  | 562.45 |  |  | 562.45 | Access initiatives
ZK110 | K278 | C070 | Ibis for Anne Hornsby, Minds Eye |  |  | 54.16 |  |  | 54.16 | Access initiatives
ZK110 | K278 | C070 | Amy Tomlinson BSL Tour x2 inc. fee and travel |  |  | 93 |  |  | 93 | Access initiatives
ZK110 | K280 | C070 | Teacher CPD |  |  | 0 |  | 0
ZK110 | K280 | C070 | Delivery costs, Artists Fee, Materials |  |  | 4000 |  |  | 4000 | Public community programme
ZK110 | K280 | C070 | Teacher bursary for follow up project |  |  | 2500 |  |  | 2500 | Public community programme
ZK110 | K281 | C070 | Secondary resource |  |  | 0 |  | 0 | 0 | Public community programme
ZK110 | K281 | C070 | Development Costs of Secondary resource |  |  | 750 |  |  | 750 | Public community programme
ZK110 | K281 | C070 | Design of Secondary resource |  |  | 110 |  |  | 110 | Public community programme
ZK110 | K281 | C070 | Print of Secondary resource |  |  | 278 |  |  | 278 | Public community programme
ZK110 | K282 | C070 | Day in the Life | HCAL |  | 4000 |  | 0 | 4000 | Public community programme
ZK110 | K283 | C070 | Adult Workshop: Curating |  |  | 0 |  | 0 | 0 | Public community programme
ZK110 | K283 | C070 | Guest fee |  |  | 250 |  |  | 250 | Public community programme
ZK110 | K283 | C070 | Travel and Accomm |  |  | 200 |  |  | 200 | Public community programme
ZK110 | K283 | C070 | Hospitality |  |  | 150 |  |  | 150 | Public community programme
ZK110 | K283 | C070 | Adult Workshop: Writing |  |  | 0 |  |  | 0 | Public community programme
ZK110 | K283 | C070 | Guest fee |  |  | 250 |  |  | 250 | Public community programme
ZK110 | K283 | C070 | Travel and Accomm |  |  | 100 |  |  | 100 | Public community programme
ZK110 | K283 | C070 | Hospitality |  |  | 100 |  |  | 100 | Public community programme
ZK110 | K283 | C070 | Materials |  |  | 200 |  |  | 200 | Public community programme
ZK110 | K283 | C070 | Adult Workshop: Film | Pay to HL |  | 500 |  |  | 500 | Public community programme
ZK110 | K283 | C070 | Adult Workshop: Drawing | Pay to HL |  | 500 |  |  | 500 | Public community programme
ZK110 | K232 | C070 | TURNER//RETURN | Separate breakdown |  | 14600 |  | 0 | 14600 | Events & activities
ZK110 | K233 | C070 | Meet me at the Blue Box |  |  | 8000 |  | 0 | 8000 | Public community programme
ZK110 | K233 | C070 | Mini Maserpieces | Pay to HL |  | 125 |  |  | 125 | Public community programme
ZK110 | K233 | C070 | Art Academy: Print | Pay to HL |  | 125 |  |  | 125 | Public community programme
ZK110 | K233 | C070 | Art Acedemy: Drawing | Pay to HL |  | 125 |  |  | 125 | Public community programme
ZK110 | K233 | C070 | Big Draw | Pay to HL |  | 125 |  |  | 125 | Public community programme
ZK110 | K233 | C070 | General Resource Budget | Pay to HL |  | 1000 |  |  | 1000 | Public community programme
ZK110 | K279 | C070 | Learning design & print |  |  | 0 |  | -4.5475e-13 | 4.5475e-13 | Public community programme
ZK110 | K279 | C070 | Design of Teacher Resource |  |  | 150 |  |  | 150 | Public community programme
ZK110 | K279 | C070 | Design of Secondary resource |  |  | 90 |  | 90 | 0 | Public community programme
ZK110 | K279 | C070 | Print of 20,000 x A5 flyers and 160 x A4 posters |  |  | 578 |  | 578 | 0 | Print production
ZK110 | K279 | C070 | Design of Turner Prize learning print - 8pp A5 die cut concertina fold leaflet. To go to schools ahead of 2017 summer holidays. |  |  | 400 |  | 400 | 0 | Print production
ZK110 | K279 | C070 | Print and postage of the learning comms for teachers re: Turner Prize 2017 programme. |  |  | 734 |  | 734 | 0 | Print production
ZK110 | K279 | C070 | Design of 2pp A5 leaflet for Public Programme + 1pp A4 Poster |  |  | 150 |  | 150 | 0 | Print production
ZK110 | K279 | C070 | Distribution of Public Programme leaflet and posters to 80 outlets |  |  | 398.4 |  | 398.4 | 0 | Print production
ZK110 | K279 | C070 | Hello Turner! Design and print |  |  | 1750 |  | 1750 | 0 | Public community programme
|  |  | HULL2017 TEAM COSTS |  |  |  | 10274.1
ZK114 | K115 | C070 | Travel & Accommodation |  |  | 267.25 |  | 4.3201e-12 | 267.25 | Admin
ZK114 | K115 | C070 | C Drury Credit Card Apr'17 |  |  | 1886.8 |  | 1886.8 | 0 | Admin
ZK114 | K115 | C070 | C Drury Credit Card Mar'17 |  |  | 886.8 |  | 886.8 | 0 | Admin
ZK114 | K115 | C070 | Sara Black train London > Hull for Turner Prize artist meetings |  |  | 50.98 |  | 50.98 | 0 | Admin
ZK114 | K115 | C070 | Flights for George Vasey - London to Berlin / Berlin to Athens - £260.13 Athens to Venice - £256.60 Flight for Sara Black London to Athens - £405.60 |  |  | 273.8 |  | 273.8 | 0 | Admin
ZK114 | K115 | C070 | Flights for George Vasey - London to Berlin / Berlin to Athens - £260.13 Athens to Venice - £256.60 Flight for Sara Black London to Athens - £405.60 |  |  | 507.8 |  | 507.8 | 0 | Admin
ZK114 | K115 | C070 | Sara Black train Truro > London on 29th May 2017 for Turner Prize (Lubaina work selection). |  |  | 66.68 |  | 66.68 | 0 | Admin
ZK114 | K115 | C070 | Flights for George Vasey - London to Berlin / Berlin to Athens - £260.13 Athens to Venice - £256.60 Flight for Sara Black London to Athens - £405.60 |  |  | 300.54 |  | 300.54 | 0 | Admin
ZK114 | K115 | C070 | Hotels for Turner Prize George Vasey: BLOC (Gatwick) 18th/19th May - £109 Berlin InnerCity 19th/20th May - £122 Athens Polis Grand 20th/24th May - £321 Sara Black: Athens Polis Grand 22nd/24th May - £243 |  |  | 135.32 |  | 135.32 | 0 | Admin
ZK114 | K115 | C070 | Hotels for Turner Prize George Vasey: BLOC (Gatwick) 18th/19th May - £109 Berlin InnerCity 19th/20th May - £122 Athens Polis Grand 20th/24th May - £321 Sara Black: Athens Polis Grand 22nd/24th May - £243 |  |  | 320.36 |  | 320.36 | 0 | Admin
ZK114 | K115 | C070 | Hotels for Turner Prize George Vasey: BLOC (Gatwick) 18th/19th May - £109 Berlin InnerCity 19th/20th May - £122 Athens Polis Grand 20th/24th May - £321 Sara Black: Athens Polis Grand 22nd/24th May - £243 |  |  | 111 |  | 111 | 0 | Admin
ZK114 | K115 | C070 | Hotels for Turner Prize George Vasey: BLOC (Gatwick) 18th/19th May - £109 Berlin InnerCity 19th/20th May - £122 Athens Polis Grand 20th/24th May - £321 Sara Black: Athens Polis Grand 22nd/24th May - £243 |  |  | 244.36 |  | 244.36 | 0 | Admin
ZK114 | K115 | C070 | Trains London > Hull Return on 5th July 2017 for David Kohn and Jennifer Dyne site visit. |  |  | 135.96 |  | 135.96 | 0 | Admin
ZK114 | K115 | C070 | 70020672 K Fuller |  |  | 116 |  | 116 | 0 | Admin
ZK114 | K115 | C070 | Ben McKnight trains Hull > London Return on Friday 16th June 2017 for BBC 6 Music meeting |  |  | 104.98 |  | 104.98 | 0 | Admin
ZK114 | K115 | C070 | George Vasey London Hotel, 15th June 2017 for Andrea Buttner filming and Hurvin Anderson studio visit |  |  | 127.96 |  | 127.96 | 0 | Admin
ZK114 | K115 | C070 | George Vasey Trains Friday 30th June Hull > London and London > Darlington for Rosalind Nashashibi Studio visit |  |  | 173.46 |  | 173.46 | 0 | Admin
ZK114 | K115 | C070 | George Vasey Trains, Hull > London 12th June 2017 and London > Darlington 16th June 2017. For Andrea Buttner filming and Hurvin Anderson studio visit. |  |  | 122.46 |  | 122.46 | 0 | Admin
ZK114 | K115 | C070 | George Vasey; HULL050517 expenses |  |  | 249.3 |  | 249.3 | 0 | Admin
ZK114 | K115 | C070 | Ian Read train Newcastle > Hull Return on 16th June 2017 for BBC FuzzFeed and Turner Prize meeting |  |  | 146.48 |  | 146.48 | 0 | Admin
ZK114 | K115 | C070 | Lily Mellor Train Hull > Newcastle Return on Wednesday 28th June for BALTIC Artists' Award Opening |  |  | 54.78 |  | 54.78 | 0 | Admin
ZK114 | K115 | C070 | Sacha Craddock train Hull > London Tuesday 11th July 2017 for Tate's 'Soul of a Nation' opening |  |  | 83.98 |  | 83.98 | 0 | Admin
ZK114 | K115 | C070 | Sacha Craddock Trains London > Preston and Preston > Hull on Monday 10th July for Lubaina Sodium filming. |  |  | 143.46 |  | 143.46 | 0 | Admin
ZK114 | K115 | C070 | Sara Black replacement train Hull > London 13th June 2017 for Himid V&A Research |  |  | 26.98 |  | 26.98 | 0 | Admin
ZK114 | K115 | C070 | Sara Black Train Hull > Leeds Return, Thursday 29th June 2017 for East Street Arts meeting, Turner Learning Programme |  |  | 24.98 |  | 24.98 | 0 | Admin
ZK114 | K115 | C070 | Sara Black train Hull > London Single, 2nd June 2017 |  |  | 53.98 |  | 53.98 | 0 | Admin
ZK114 | K115 | C070 | Sara Black Train Hull 14 June 2017 > London Return 19 June 2017 for Turner Prize artist filming and studio visits |  |  | 84.98 |  | 84.98 | 0 | Admin
ZK114 | K115 | C070 | Sara Black Train Truro > London Off-Peak Single, Sunday 16th June 2017 for Turner Prize artist (Andrea) filming with Sodium and BBC |  |  | 66.68 |  | 66.68 | 0 | Admin
ZK114 | K115 | C070 | Sara Black Trains Hull > London 9th June 2017 Return 12th June 2017 |  |  | 105.98 |  | 105.98 | 0 | Admin
ZK114 | K115 | C070 | Sara Black; SB1718161 Turner Prize Expenses |  |  | 309.14 |  | 309.14 | 0 | Admin
ZK114 | K115 | C070 | Sacha Craddock Train London > Preston Return for Lubaina Sodium Filming on Friday 21st July 2017 |  |  | 209.98 |  | 209.98 | 0 | Admin
ZK114 | K115 | C070 | Sara Black Train Hull > London Return 18th July for David Kohn Meeting with Rosalind and Lubaina |  |  | 124.98 |  | 124.98 | 0 | Admin
ZK114 | K115 | C070 | George Vasey Train Hull > London Return 26th July for David Kohn Meeting |  |  | 118.08 |  | 118.08 | 0 | Admin
ZK114 | K115 | C070 | Lily Mellor Train Hull>Preston Return, Friday 21st July for Lubaina filming |  |  | 55.13 |  | 55.13 | 0 | Admin
ZK114 | K115 | C070 | George Vasey Travelodge Hotel London, Thursday 3rd August for Rosalind filming and Media Training |  |  | 72.54 |  | 72.54 | 0 | Admin
ZK114 | K115 | C070 | Lily Mellor Train Hull > London Return, Friday 4th Aug for Media Training |  |  | 71.63 |  | 71.63 | 0 | Admin
ZK114 | K115 | C070 | George Vasey Train Hull>London on 3rd August and London>Darlington on 6th August for Rosalind filming and Media Training |  |  | 109.46 |  | 109.46 | 0 | Admin
ZK114 | K115 | C070 | Sara Black Train Hull>London Return on 2nd August for Media Training and Rosalind filming |  |  | 50.98 |  | 50.98 | 0 | Admin
ZK114 | K115 | C070 | George Vasey replacement train Hull>London on 2nd August for Andrea site visit |  |  | 26.98 |  | 26.98 | 0 | Admin
ZK114 | K115 | C070 | George Vasey Hotel at London City Airport, 2nd August for Andrea studio visit with DKA |  |  | 60.67 |  | 60.67 | 0 | Admin
ZK114 | K115 | C070 | Lily Mellor Taxi Park Grove > Train Station on 21st July for Lubaina filming |  |  | 4.7 |  | 4.7 | 0 | Admin
ZK114 | K115 | C070 | Lily Mellor Crown Paints > PXC for Hurvin samples |  |  | 6.1 |  | 6.1 | 0 | Admin
ZK114 | K115 | C070 | Taxi |  |  | 4.9 |  | 4.9 | 0 | Admin
ZK114 | K115 | C070 | George Vasey and Jennifer Dyne Flight London>Berlin 3rd August for Andrea studio visit |  |  | 511.68 |  | 511.68 | 0 | Admin
Sub total of actual travel costs above
ZK114 | K115 | C070 | George Train London > Darlington 27th June 2017 (to be credit noted) |  |  | 32.98 |  | 32.98 | 0 | Admin
ZK114 | K115 | C070 | George Train London > Darlington 27th June 2017 (to be credit noted) |  |  | -32.98 |  |  | -32.98 | Admin
ZK114 | K115 | C070 | George Vasey train Hull > London return on 17 August 2017 for curator meeting |  |  | 135.98 |  | 135.98 | 0 | Admin
ZK114 | K115 | C070 | Sacha Craddock replacement train for earlier filming Lubaina Himid on 10th July 2017 |  |  | 147.98 |  | 147.98 | 0 | Admin
ZK114 | K203 | C070 | Admin-Meeting costs |  |  |  |  | 0 | 0 | Admin
ZK114 | K203 | C070 | George Vasey expenses inc. Berlin Trip, Athens Trip and artist liaison. Oct 2017. |  |  | 554.66 |  | 554.66 | 0 | Admin
ZK114 | K203 | C070 | Katy expenses Oct 2017 |  |  | 78.25 |  | 76.43 | 1.82 | Admin
ZK114 | K203 | C070 | 70023212 L Mellor |  |  | 21.95 |  | 21.95 | 0 | Admin
ZK114 | K203 | C070 | C Drury Credit Card Apr'17 |  |  | 1.65 |  | 1.65 | 0 | Admin
ZK114 | K203 | C070 | Expenses for Turner Prize meetings - 20th April to 8th May |  |  | 19 |  | 19 | 0 | Admin
ZK114 | K203 | C070 | Petty Cash Claim 32 |  |  | 11.57 |  | 11.57 | 0 | Admin
ZK114 | K203 | C070 | SARA BLACK; SB1718164 Expenses for Turner Prize meetings - 20th April to 8th May |  |  | 249.75 |  | 249.75 | 0 | Admin
ZK114 | K203 | C070 | Katy and Ben Trains Hull > London return for BBC Meeting, 8th Sept |  |  | 214.44 |  | 214.46 | -0.02 | Admin
ZK114 | K203 | C070 | Lily train Hull > London Return for Hollybush/Jayhawk shipment, 8 Sept |  |  | 115.18 |  | 115.18 | 0 | Admin
ZK114 | K203 | C070 | Lily Expenses - Lubaina hosting during Sodium filming, Preston |  |  | 48.15 |  | 48.15 | 0 | Admin
ZK114 | K116 | C070 | Hotel & Accommodation | Breakfast David Sinclair/Anna Marshall/Kirsten Siminster(Park Plaza River Bank-03.05.17) |  | 64.5 |  | 64.5 | 0 | Admin
|  |  | OPENING EVENT |  |  |  | 11095.04
ZK104 | K136 | C070 | Radios x24 |  |  | 224.3 |  | 224.3 | 0 | Events & external relations
ZK104 | K136 | C070 | Ferens staff costs for 25th | £343.50 for Ferens staff, awaiting TP Supervisor costs |  | 1100 |  |  | 1100 | Events & external relations
ZK104 | K136 | C070 | Matt Lund AV Technician cost, on call for Opening |  |  | 100 |  |  | 100 | Events & external relations
ZK104 | K136 | C070 | x2 SIA |  |  | 112.5 |  | 112.5 | 0 | Events & external relations
ZK104 | K136 | C070 | x2 First Aiders |  |  | 100 |  | 100 | 0 | Events & external relations
ZK104 | K120 | C070 | Food, canopies x3 pp |  |  | 2232.92 |  | 2232.92 | 0 | Events & external relations
ZK104 | K120 | C070 | Corkage |  |  | 1470 |  | 1470 | 0 | Events & external relations
ZK104 | K120 | C070 | Buckets for wine |  |  | 24.92 |  | 24.92 | 0 | Events & external relations
ZK104 | K120 | C070 | Wine and Glass Hire |  |  | 929.72 |  | 929.72 | 0 | Events & external relations
ZK104 | K120 | C070 | Courier for wine and glass return |  |  | 85 |  | 85 | 0 | Events & external relations
ZK104 | K120 | C070 | After party costs inc. catering, security and DJ | drink, chilli, DJ, security |  | 1020 |  |  | 1020 | Events & external relations
ZK104 | K270 | C070 | Venue dressing / Furniture |  |  | 552.64 |  | 552.64 | 0 | Events & external relations
ZK104 | K245 | C070 | AV |  |  | 2643.04 |  | 2643.04 | 0 | Events & external relations
ZK104 | K158 | C070 | Photography |  |  | 500 |  | 0 | 500 | Events & external relations
|  |  | AWARDS NIGHT |  |  |  | 44000
ZK107 | K115 | C070 | Presenter train and per diems |  |  | 1000 |  | 0 | 1000 | Events & external relations
ZK107 | K115 | C070 | Artist travel |  |  | 1000 |  |  | 1000 | Events & external relations
ZK107 | K115 | C070 | Accommodation artists inc.goldie, karl, 4 artists |  |  | 1000 |  |  | 1000 | Events & external relations
ZK107 | K232 | C070 | Entertainment - Steve Cobby |  |  | 500 |  | 0 | 500 | Events & external relations
ZK107 | K120 | C070 | Catering |  |  | 13000 |  | 250 | 12750 | Events & external relations
ZK107 | K120 | C070 | Afterparty |  |  | 1000 |  |  | 1000 | Events & external relations
ZK107 | K245 | C070 | AV, Tech inc. Durham |  |  | 10000 |  | 0 | 10000 | Events & external relations
ZK107 | K133 | C070 | Invites |  |  | 139.46 |  | 0 | 139.46 | Events & external relations
ZK107 | K133 | C070 | Invites design and print and delivery to office |  |  | 1032 |  | 75 | 957 | Events & external relations
ZK107 | K133 | C070 | 204 x first class stamps for first tranch of invites £132.60 |  |  | 132.6 |  | 132.6 | 0 | Events & external relations
ZK107 | K133 | C070 | International invites |  |  | 22.34 |  |  | 22.34 | Events & external relations
ZK107 | K133 | C070 | Courier of Tate invites |  |  | 23.6 |  |  | 23.6 | Events & external relations
ZK107 | K136 | C070 | Venue dressing and build |  |  | 7500 |  | 0 | 7500 | Events & external relations
ZK107 | K136 | C070 | Security |  |  | 850 |  |  | 850 | Events & external relations
ZK107 | K136 | C070 | Photography |  |  | 500 |  |  | 500 | Events & external relations
ZK107 | K136 | C070 | Venue hire |  |  | 2500 |  |  | 2500 | Events & external relations
ZK107 | K136 | C070 | Portaloos |  |  | 1500 |  |  | 1500 | Events & external relations
ZK107 | K136 | C070 | First Aid |  |  | 200 |  |  | 200 | Events & external relations
ZK107 | K136 | C070 | Traffic Management |  |  | 1000 |  |  | 1000 | Events & external relations
ZK107 | K136 | C070 | Car for movement |  |  | 450 |  |  | 450 | Events & external relations
ZK107 | K136 | C070 | Wristbands |  |  | 300 |  |  | 300 | Events & external relations
ZK107 | K145 holding | C070 | POT-to be scoped |  |  | 350 |  |  | 350 | Events & external relations
|  |  | OTHER COSTS-PRE MARCH 2017 (detail below) |  |  |  | 2038
ZK102 | K115 | C070 | 70020672 K Fuller |  |  | 229.23 |  | 229.23 | 0 | Admin
ZK102 | K115 | C070 | Taxi services for May 2016. Programme Turner Prize ZK102 K115 C070 |  |  | 3.7 |  | 3.7 | 0 | Admin
ZK102 | K117 | C070 | 70020672 K Fuller |  |  | 21.29 |  | 21.29 | 0 | Admin
ZK102 | K117 | C070 | Petty Cash Claim 30 |  |  | 17.32 |  | 17.32 | 0 | Admin
ZK114 | K103 | C070 | Petty Cash Claim 30 |  |  | 14.85 |  | 14.85 | 0 | Admin
ZK114 | K299 | C070 | 70020672 K Fuller |  |  | 322.42 |  | 322.42 | 0 | Admin
ZK114 | K299 | C070 | Lunch for the Turner Prize meeting |  |  | 72.4 |  | 72.4 | 0 | Admin
ZK114 | K299 | C070 | Miranda Stacey; Interview Expenses |  |  | 70 |  | 70 | 0 | Admin
ZK114 | K299 | C070 | Raj Sandhu; Interview Expenses-Turner Prize |  |  | 84.05 |  | 84.05 | 0 | Admin
ZK114 | K299 | C070 | T Kagbala Credit Card Nov'16 |  |  | 115.77 |  | 115.77 | 0 | Admin
ZK114 | K299 | C070 | T Kagbala Credit Card Sept'16 |  |  | 1086.97 |  | 1086.97 | 0 | Admin
|  |  | DEINSTALL |  |  |  | 22295.76
ZK105 | K115 | C070 | Accommodation De-Install (train and hotel) | 1 assistants £70 per night x 1 nights |  | 150 |  | 0 | 150 | Exhibition build
Technicians/Materials
ZK105 | K244 | C070 | De-Install skips | Estimate |  | 1000 |  | 0 | 1000 | Exhibition build
ZK105 | K244 | C070 | Deinstall packing materials costs | Estimate |  | 336.04 |  |  | 336.04 | Exhibition build
ZK105 | K244 | C070 | Movement of Francis Bacon inc. Courier fee and travel | To be paid to HCAL |  | 130.1 |  |  | 130.1 | Exhibition build
ZK105 | K244 | C070 | Packing and conservation materials for all works, inc. Hurvin Anderson's un-shown works | To be paid to HCAL |  | 533.86 |  |  | 533.86 | Exhibition build
ZK105 | K244 | C070 | HCAL Technicians, Reinstating of Collection | To be paid to HCAL |  | 3750 |  |  | 3750 | Technicians install/de-install
Painting/Reinstatement
ZK105 | K245 | C070 | Deinstall painting of Galleries |  |  | 2336 |  | 0 | 2336 | Exhibition build
ZK105 | K245 | C070 | Gallery 5, 6 &9 replacement vinyl |  |  | 190 |  |  | 190 | Exhibition build
Transport
ZK105 | K258 | C070 | Jayhawk return transport to all lenders | Includes 8.5% discount |  | 8779.43 |  | 0 | 8779.43 | Logistics
ZK105 | K258 | C070 | Martin speed arts council courier |  |  | 1765 |  |  | 1765 | Logistics
ZK105 | K258 | C070 | DHL Oslo Hurvin Anderson |  |  | 1800 |  |  | 1800 | Logistics
ZK105 | K258 | C070 | Jayhawk return of Andrea's unshown works Oct 2017 |  |  | 1112 |  |  | 1112 | Logistics
ZK105 | K258 | C070 | Border clearance costs for LA Andrea's tables (Outbound) |  |  | 413.33 |  |  | 413.33 | Logistics
47.23
ZK114 | K225 | C070 | Exec pot - to be scoped |  |  | 611.85 |  |  | 611.85 | Admin
|  |  |  | TOTAL BUDGET |  | 450000 | 450000 | 188611.35 | 261388.65