**Blade Removal Draft Schedule**

**19th March 2017**

**16:00** Secure QVS

Set up cranes

Attach A Frame

Attach tip lifting cradle

**17:30** Lift Blade onto SPMTs

**19:00** Move Blade to Saville St and park

Dismantle tip & root supports

**20th March 2017**

**00:01** Blade departs Savile St

QVS clear

**01:30** Blade leaves Hull network, arrives on A63

**04:30** Blade leaves A63, arrives King George Dock

**05:30** A63 handover to Highways England