**CREATIVE PARTNERS**
**END OF PROJECT REPORT**

**GENERAL INFORMATION**

|  |  |
| --- | --- |
| **ORGANISATION NAME:** | LIFT |
| **PROJECT NAME:** | DEPART |
| **MAIN CONTACT:** | BONNIE SMITH |
| **REPORT SUBMISSION DATE:** | 08/06/17 |

**INTRODUCTION**

Everyone who receives funding from Hull UK City of Culture 2017 Ltd. must complete an end of project report, to inform us how they did against the agreed deliverables in their Agreement and Project Schedule. We recommend you read it straight away, as you will need to collect the information throughout your project.

We have done our best to ensure that the information being asked for already reflects the output data that you are collecting for other funders. However, due to the specific nature of this funding there are some additional outputs to be measured. This is due to the nature of our own funding agreements, and the need for us to provide certain evidence to these funders.

This end of project report tells us:

* What has happened during your project as a whole
* Your final income and expenditure figures
* What you have learned from the project, how you have adapted to these learnings, and what you plan to do with this learning in future.

We will send you a separate survey about the outcomes and impact of your Hull 2017 supported project separately. We will process the information you give us to understand:

* The overall effect of our grant and support;
* The overall effectiveness of our services and grants administration; and
* What the key things are that the city needs to be aware of in future, in terms of supporting the arts and culture sector.

We also use this information to report to our funders.

Please email this activity report to cian.smyth@hull2017.co.uk

**NB: Please note that these reporting templates have been designed to try and account for all different types of creative partner. As a result, there will be rows within the data tables that are not applicable to your organisation. If this is the case, please just leave these rows BLANK.**

**GLOSSARY OF TERMS**

* **Commission -** the hiring or payment to an artist / artistic company to create a new art work, project or performance. A commission can be wholly or partly funded by you / your organisation.
* **Participant opportunities** – workshops, classes, courses, engagement projects for members of the public (i.e. not including school’s engagement, artist development or staff training opportunities).
	+ **Workshops and classes**: individual occurrences of a workshop / class, even if it is the same one being delivered, e.g. the same contemporary dance workshop led by Hull Dance, delivered at 3 different venues or 3 times in a day, is 3 opportunities.
	+ **Courses and engagement projects**: a series of classes, workshops, activities, etc. where the same group of participants take part for the duration, and it is progressive in nature, e.g. a group of 8 circus skills classes to introduce participants to a range of acrobatic skills (once a week for 8 weeks), attended by the same 10 participants OR a community cast recruited to develop, rehearse and perform a drama.
* **School’s engagement opportunities –** as above, but organized formally with schools.
* **Artist development opportunities** – includes residencies, structured schemes, seed commissions, professional or industry advice, showcase opportunities, associate artist schemes, etc.
* **Staff training opportunities** – including formal training and development programmes, attendance at industry conferences and seminars, professional leave, work shadowing, mentoring, etc.
* **Audience** - those attending an exhibition or performance, and people getting access to work that is printed, recorded, broadcast or on the internet.
* **Participant** – those taking part in doing an activity.

 **OTHER INFORMATION**

In addition to these reports, we will also send each project lead, links to an online survey:

* **Survey 1:** The first survey will be sent in February 2017 and will seek to ask a few key questions, linked to the outcome areas we are measuring within the overall evaluation for Hull 2017, as well as ones about how we are performing in our role as your partner. This is so we can learn from your feedback and make necessary changes where improvements need to be made.
* **Survey 2:** This will be sent at the end of the agreement period with you, and will again ask a few key questions linked to the outcome areas we are measuring within the overall evaluation for Hull 2017; as well as any key learnings for Hull’s cultural sector beyond 2018 and future cities of culture.

A number of partners will also be contacted by our external evaluators to take part in in-depth interviews, which seek to explore the above in more detail.

1. **PROJECT REPORT**

Please attach the final versions of the listed documents (where applicable to your project). Please check the box to indicate that the document has been provided:

|  |  |  |
| --- | --- | --- |
| **DOCUMENTS** | **PROVIDED** | **N/A** |
| * Delivery Plan – ALREADY SUBMITTED
 | [x]  |  |
| * Budget
 | [x]  |  |
| * Marketing & Communications Plan – LED BY HULL 2017
 | [ ]  | [x]  |
| * Learning & Engagement Plan
 | [ ]  | [x]  |
| * Risk Register – ALREADY SUBMITTED AS PART OF DELIVERY PLAN
 | [x]  | [ ]  |

1. **MONITORING & EVALUATION REPORT**
2. **ACTIVITY**

**Overall, how did you do reaching the targets laid out in your agreement? Where the row is not applicable, please leave BLANK.**

**\* Target: target(s) listed within your agreement with Hull UK City of Culture 2017**

**\*Actual: final figures for your project**

|  |  |  |
| --- | --- | --- |
|  | **TARGET\*** | **ACTUAL TO DATE\*** |
| **ACTIVITY** |
| **COMMISSIONS** |
| No. of commissions | 1 | 1 |
| No. of commissions inspired by history / heritage |  |  |
| **PRODUCTIONS AND PERFORMANCES** |
| No. of productions or co-productions | 1 | 1 |
| No. of productions or co-production performances | 7 | 5 |
| No. of productions or co-productions on tour |  |  |
| No. of visiting company productions |  |  |
| No. of visiting company production performances |  |  |
| No. of productions inspired by history / heritage |  |  |
| No. of accessible performances |  |  |
| **EXHIBITIONS AND SCREENINGS** |
| No. of exhibitions |  |  |
| No. of exhibitions on tour |  |  |
| No. of exhibition days |  |  |
| No. of exhibitions inspired by history / heritage |  |  |
| No. of access provisions |  |  |
| **FILMS** |
| No. of films |  |  |
| No. of films on tour |  |  |
| No. of screenings |  |  |
| No. of films inspired by history / heritage |  |  |
| No. of accessible screenings |  |  |

|  |  |  |
| --- | --- | --- |
|  | **TARGET\*** | **ACTUAL TO DATE\*** |
| **ACTIVITY** |
| **FESTIVALS & MUSIC EVENTS** |
| No. of festival days  |  |  |
| No. of artists / groups / companies programmed |  |  |
| No. of performances |  |  |
| No. of shows inspired by history / heritage |  |  |
| No. of accessible performances during festival |  |  |
| **LEARNING AND PARTICIPATION** |
| No. of participant opportunities\* (in-house) |  |  |
| No. of participant opportunities\* (outreach) | 110 | 110 |
| No. of school’s engagement opportunities\* (in-house) |  |  |
| No. of school’s engagement opportunities\* (outreach) |  |  |
| No. of artist development opportunities\* (in-house) |  |  |
| No. of artist development opportunities\* (outreach) | 28 | 28 |
| No. of staff training opportunities\* (in-house) |  |  |
| No. of staff training opportunities\* (outreach) |  |  |
| No. of opportunities exploring history / heritage |  |  |
| No. of opportunities to build historical / heritage-based skills or knowledge |  |  |
| No. of accessible learning and participation activities |  |  |

|  |  |  |
| --- | --- | --- |
|  | **TARGET\*** | **ACTUAL TO DATE\*** |
| **ACTIVITY VENUES/LOCATIONS** |
| No. of activities delivered in HU1 – HU9 | 7 | 5 |
| No. of activities delivered outside of HU1 – HU9 |  |  |

Please provide a short description of the additional activities delivered, since your last update report in the box below:

Following the success of sales of Depart and the clear local demand an additional 5th performance was added to the final schedule. All performances sold out.

If any of the above has been inspired by, explored, or built skills and knowledge in history / heritage (especially that linked to Hull’s past), please briefly explain how below.

Thinking about your project as a whole, what would you say have been the **main successes** and **challenges** in terms of the activity delivered (approximately 500 words):

The delivery of Depart in Hull was an outstanding success:

* We achieved 5 sell out performances receiving positive press reviews and local audience feedback
* Evidence suggests that harder to reach audiences were engaged by Depart with attendance from local groups including Hull Homeless Housing Project, ReNew and People’s Awareness of Disability Discrimination group
* Depart created meaningful participatory and energumen opportunities for non-professionals, incorporated into the performance as either guides, circus performers (from NCCA), dancers (from Northern School of Contemporary Dance) and singers (from the Freedom and other local choirs).
* We delivered a show of high artistic quality that had significantly developed from its initial London run

The main challenges were:

* Negative initial press coverage and some negative local response to the use of a cemetery site for circus, became a comms, PR and stakeholder management challenge for all parties
* The initial communications between LIFT’s producing and technical teams and the Hull teams were difficult, but became much improved following the appointment of a new lead Depart producer at LIFT
* Depart took place in atrocious weather conditions that created problems for site management and performer safety.
1. **ADDITIONAL CAPACITY TO DELIVER YOUR PROJECT**

**In the table below, please enter the total number of additional people contracted by your organisation to make this project happen. The totals provided below should not include your core team who will be accounted for in the ORGANISATIONAL END OF YEAR REPORT (where applicable).**

**Some roles / work areas have been provided. However, please insert new roles into the table for anything not accounted for.**

|  |  |  |  |
| --- | --- | --- | --- |
|  | **TOTAL NO. INDIVIDUALS**  | **TOTAL NO. WHO ARE HULL RESIDENTS** | **TOTAL NUMBER OF DAYS WORKED** |
| **CATEGORY OR ROLE** |
| **CORE CREATIVE TEAM (PRODCUTION / EXHIBITION SPECIFIC)** |
| Co-Director | 2 | 0 | 40 |
| Co-Producer |  |  |  |
| Other Production (please specify) | 1 | 0 | 20 |
| Artist / Performer | 36 | 0 | 8 |
| Other Creative (please specify) | 4 | 0 | 32 |
| Co-Curator |  |  |  |
| Other Curatorial (please specify) |  |  |  |
| Please specify:[Insert other production, creative or curatorial here]  |
| **OTHER** |
| Other |  |  |  |
| Please specify: Other creatives include LX Designer, Choreographer, Composer, Video Designer[Insert other here] |

**In the tables on this and the following page, please enter the number of people contracted to make this project happen, who fall into each of the equal opportunities categories listed. If you do not know please leave this blank.**

|  |  |  |  |  |
| --- | --- | --- | --- | --- |
|  | **TOTAL** |  |  | **TOTAL** |
| **AGE GROUPS – DELIVERY TEAM** |  | **DISABILITY/LONG TERM ILLNESS – DELIVERY TEAM** |
| 16-17 years |  |  | Yes – limited a lot |  |
| 18-19 years |  |  | Yes – limited a little |  |
| 20-24 years | 28 |  | No |  |
| 25-29 years | 8 |  | Prefer not to say | 43 |
| 30-34 years |  |  | **CONDITIONS – DELIVERY TEAM** |
| 35-39 years | 1 |  | Learning disability |  |
| 40-44 years | 6 |  | Long-term illness/condition |  |
| 45-49 years |  |  | Sensory impairment |  |
| 50-54 years |  |  | Mental Health condition |  |
| 55-59 years |  |  | Physical impairment |  |
| 60-64 years |  |  | Cognitive impairment |  |
| 65-69 years |  |  | Other |  |
| 70-74 years |  |  | **ETHNICITY – DELIVERY TEAM** |  |
| 75+ years |  |  | Welsh/English/Scottish/Northern Irish/British |  |
| Prefer not to say |  |  | Irish |  |
| **GENDER - DELIVERY TEAM** |  | Gypsy or Irish Traveller |  |
| Male |  |  | White and Black Caribbean |  |
| Female |  |  | White and Black African |  |
| Transgender |  |  | White and Asian |  |
| Gender non-conf |  |  | Any other Mixed/multiple ethnic background  |  |
| Prefer not to say | 43 |  | Indian |  |
|  |  |  | Pakistani |  |
|  |  |  | Bangladeshi |  |
|  |  |  | Chinese |  |
|  |  |  | Any other Asian background |  |
|  |  |  | African |  |
|  |  |  | Caribbean |  |
|  |  |  | Any other Black/African/Caribbean background  |  |
|  |  |  | Arab |  |
|  |  |  | Any other ethnic group  |  |
|  |  |  | Prefer not to say |  |

**In the tables on this page, please enter the number of additional people contracted to make this project happen, who fall into each of the equal opportunities categories listed. If you do not know please leave blank. We recommend using the Equal Opportunities form provided in the Hull 2017 Reporting Toolkit to collect this information.**

Thinking about your project as a whole, what would you say have been the **main successes** and **challenges** in terms of the additional capacity brought in to deliver your activity? - **Please see the Artist and Creative Team Question Bank in the Hull 2017 Reporting Toolkit for the type of questions to ask**

Successes:

* Effective integration of multidisciplinary teams from different artistic and international backgrounds
* Effective engagement of local partners to deliver the large scale participatory work (Freedom Choir)
* Effective relationships with most local crew and suppliers

Challenges:

* Schedules and availability of lead artists made planning difficult at times
* Some poor quality local suppliers, particularly security contractors. Security of te site remained an ongoing issue
1. **AUDIENCES**

**In total, how many people have attended your activities?**

|  |  |  |
| --- | --- | --- |
|  | **TOTAL**  | **% FROM HU1-HU9\*** |
| Number of audience members\* (in-house) | 936 (from Spektrix report) | Require postcodes |
| Number of audience members on tour |  |  |

**\*The % from HU1-HU9 can be taken from the results of audience surveys or your box office reports.**
 **Please complete the Total column within the tables below.**

|  |  |  |  |  |
| --- | --- | --- | --- | --- |
|  | **%** |  |  | **%** |
| **AGE GROUPS - AUDIENCES** |  | **DISABILITY/LONG TERM ILLNESS - AUDIENCES** |
| 0-2 years |  |  | Yes – limited a lot | n/a (not on survey) |
| 3-5 years |  |  | Yes – limited a little |  |
| 6-10 years |  |  | No |  |
| 11-15 years |  |  | Prefer not to say |  |
| 16-17 years |  |  | **CONDITIONS - AUDIENCES** |
| 18-19 years |  |  | Learning disability |  |
| 20-24 years | 3.5% |  | Long-term illness/condition |  |
| 25-29 years | 14.1% |  | Sensory impairment |  |
| 30-34 years | 7.1% |  | Mental Health condition |  |
| 35-39 years | 9.4% |  | Physical impairment |  |
| 40-44 years | 10.6% |  | Cognitive impairment |  |
| 45-49 years | 9.4% |  | Other |  |
| 50-54 years | 9.4% |  |  |  |
| 55-59 years | 10.6% |  |  |  |
| 60-64 years | 9.4% |  | **Please enter the % of your audience for the project in each of the equal opportunities categories shown in the tables on this and the following page. We recommend asking a sample of your audience the Equal Opportunities questions from the Audience Question Bank, provided in the Hull 2017 Toolkit.**  |  |
| 65-69 years | 5.9% |  |  |  |
| 70-74 years | 2.4% |  |  |  |
| 75+ years | 0% |  |  |  |
| Prefer not to say | 3.5% |  |  |  |
| **GENDER** |  |  |  |
| Male | 24.7% |  |  |  |
| Female | 74.1% |  |  |  |
| Transgender | 0% |  |  |  |
| Gender non-conf | 0% |  |  |  |
| Prefer not to say | 1.2% |  |  |  |

|  |  |
| --- | --- |
|  | **%** |
| **ETHNICITY** |  |
| Welsh/English/Scottish/Northern Irish/British | 92.9% |
| Irish |  |
| Gypsy or Irish Traveller |  |
| White and Black Caribbean |  |
| White and Black African |  |
| White and Asian |  |
| Any other Mixed/multiple ethnic background  | 2.4% |
| Indian |  |
| Pakistani |  |
| Bangladeshi |  |
| Chinese |  |
| Any other Asian background |  |
| African |  |
| Caribbean |  |
| Any other Black/African/Caribbean background  |  |
| Arab |  |
| Any other ethnic group |  |
| Prefer not to say | 3.5% |

Thinking about your project as a whole, what would you say have been the **main successes** and **challenges** in terms of audience engagement and feedback for your project? - **Please see the Audience Question Bank in the Hull 2017 Reporting Toolkit for the type of questions to ask**

Successes:

Tickets sold out within 24 hours of going on sale despite it being the first time Circa have performed in Hull

47% attended because it was a unique experience not to be missed

62% of audience members had never attended a cultural event in a similar outdoor venue

Overwhelming positive audience response to both the show and also the location, despite the poor weather throughout the run:

*I felt it was done very tastefully. With consideration for the surroundings and empathy towards what the venue is*

*I felt that, although this created controversy, the performance was nothing but respectful and tasteful. Rather than being an insult to the dead, it was a beautiful tribute to death and life. The use of the Requiem emphasised this.*

*It was mind blowing. Having lived so close to the cemetry for several years it gave me the opportunity to see it in a different light*

*I was utterly captivated by the performance & my students have not stopped talking about it. Utterly transported: I felt a million miles away from my house (that backed onto the performance space!)*

We were really pleased with the amount of social media engagement from audiences post-show with many people using the correct hashtag – all down to the fantastic volunteers handing out the ‘tweet cards’ to everyone pre-show.

**Challenges**

Initial response to show post-launch, negative reaction from press and locals who felt use of cemetery was disrespectful.

Lack of capacity to manage press requests and requirements particularly with the higher number of requests due to the controversy around the show – lots of news teams wanted access for their photographers and film crews and we weren’t able to allow them all access

Lack of availability – due to low capacity and the fact it sold out, we could not meet demand for tickets which also caused some negative feedback

The weather was against us which made it difficult for audience members to travel around the site and also caused the show to be stopped early on one performance due to a thunderstorm.

1. **TICKETS**

**Overall, how many tickets did you sell?**

|  |  |  |
| --- | --- | --- |
|  | **TOTAL** | **% TO** **HU1 – HU9 RESIDENTS** |
| **TICKET SALES** |
| Number of full price tickets sold |  |  |
| Number of concessionary tickets sold |  |  |
| Number of free tickets issued |  |  |
| Value of all ticket sales | £ | £ |
| **BOOKING TRENDS %** |
| Telephone |  |  |
| Counter  |  |  |
| Website |  |  |
| Post |  |  |
| Agency |  |  |
| ONLINE TICKET SALES |
| Number of tickets sold online |  |  |
| Value of tickets sold online | £ | £ |
| FRIENDS/MEMBERSHIP |
| New memberships |  |  |
| Membership renewals |  |  |
| Tickets purchased by members |  |  |
| Value of tickets bought by members | £ | £ |

1. **PARTICIPANTS**

 **In total, how many people have participated in your activities? If Hull 2017 are providing your Box Office function, please highlight this and we will download and complete this data.**

|  |  |  |
| --- | --- | --- |
|  | **TOTAL**  | **% FROM HU1-HU9** |
| Number of participants\* (in-house) |  |  |
| Number of outreach participants |  |  |
| **TOTAL PARTICIPANTS** |  |  |

**\*The % from HU1-HU9 can be taken from the results of participant surveys or registration**

|  |  |  |  |  |
| --- | --- | --- | --- | --- |
|  | **%** |  |  | **%** |
| **AGE GROUPS - AUDIENCES** |  | **DISABILITY/LONG TERM ILLNESS – AUDIENCES** |
| 0-2 years |  |  | Yes – limited a lot |  |
| 3-5 years |  |  | Yes – limited a lot |  |
| 6-10 years |  |  | No |  |
| 11-15 years |  |  | Prefer not to say | x |
| 16-17 years |  |  | **CONDITIONS – AUDIENCES** |
| 18-19 years |  |  | Learning disability |  |
| 20-24 years |  |  | Long-term illness/condition |  |
| 25-29 years |  |  | Sensory impairment |  |
| 30-34 years |  |  | Mental Health condition |  |
| 35-39 years |  |  | Physical impairment |  |
| 40-44 years |  |  | Cognitive impairment |  |
| 45-49 years |  |  | Other |  |
| 50-54 years |  | **Please enter the % of your participants for the project in each of the equal opportunities categories shown in the tables on this and the following page. We recommend asking your participants the Equal Opportunities questions from the Participant Question Bank, provided in the Hull 2017 Toolkit, or making these questions part of the registration process.** |  |  |
| 55-59 years |  |  |  |  |
| 60-64 years |  |  |  |  |
| 65-69 years |  |  | **Please enter the % of your audience in each of the equal opportunities categories shown in the tables on this and the following page. We recommend asking a sample of your audiences across the year the Equal Opportunities questions form the Participant Question Bank, provided in the Hull 2017 Reporting Toolkit.**  |  |
| 70-74 years |  |  |  |  |
| 75+ years |  |  |  |  |
| Prefer not to say | 110 |  |  |  |
| **GENDER** |  |  |  |
| Male |  |  |  |  |
| Female |  |  |  |  |
| Transgender |  |  |  |  |
| Gender non-conf |  |  |  |  |
| Prefer not to say | 110 |  |  |  |
|  |  |  |  |  |
|  | **%** |
| **ETHNICITY** |  |
| Welsh/English/Scottish/Northern Irish/British |  |
| Irish |  |
| Gypsy or Irish Traveller |  |
| White and Black Caribbean |  |
| White and Black African |  |
| White and Asian |  |
| Any other Mixed/multiple ethnic background  |  |
| Indian |  |
| Pakistani |  |
| Bangladeshi |  |
| Chinese |  |
| Any other Asian background |  |
| African |  |
| Caribbean |  |
| Any other Black/African/Caribbean background  |  |
| Arab |  |
| Any other ethnic group |  |
| Prefer not to say | x |

Thinking about your project as a whole, what would you say have been the **main successes** and **challenges** in terms of participant engagement and feedback for your project? - - **Please see the Participant Question Bank in the Hull 2017 Reporting Toolkit for the type of questions to ask**

­­

The project was extremely successful in terms of participant engagement, working with 110 local people from Hull who were fully integrated into the performance, including people working as performative guides and as choir members. The Hull Freedom chorus were an exceptional partner and delightful to work with on the project.

The only challenge was meeting the audience demand for friends and family of participants: a factor which led to the decision to add one further performance not for general sale, but where tickets were sold to an invited guest list.

­­

1. **DIGITAL**

**Overall, how has your project impacted upon your online presence?**

<https://www.liftfestival.com/events/depart-on-tour/>

|  |  |  |
| --- | --- | --- |
|  | **TOTAL PAGE VIEWS** | **UNIQUE PAGE VEIWS** |
| Website views relating to project | **1965** | **1740** |
| Average time on website pages linked to project | 00:01:18 |  |

|  |  |  |  |
| --- | --- | --- | --- |
|  | **SUBSCRIBERS AT START OF PROJECT** | **SUBSCRIBERS AT END OF PROJECT** | **CLICK THROUGHS** |
| E-newsletter subscribers via project routes | **n/a** |  |  |
| SMS subscribers via project routes |  |  |  |

|  |  |  |  |  |
| --- | --- | --- | --- | --- |
|  | **LIKES/FOLLOWERS/SUBCRIBERS AT START OF PROJECT** | **LIKES/FOLLOWERS/SUBSCRIBERS AT END OF PROJECT**  | **IMPRESSIONS ON POSTS RELATING TO THE PROJECT** | **ENGAGEMENTS WITH POSTS RELATING TO THE PROJECT** |
| Facebook | **n/a (not show specific)** |  |  |  |
| Twitter | **n/a (not show specific)** |  |  |  |
| Instagram | **n/a (not show specific)** |  |  |  |
| Other | **n/a (not show specific)** |  |  |  |

**DEFINITIONS**

* **Followers include:** Facebook Page Likes / Profile Friends; Twitter Followers; YouTube Subscribers; etc.
* **Impressions:** impressions (“views”) of Facebook posts linked to project; impressions (“views”) of Twitter tweets linked to project; views of YouTube videos linked to project; etc.
* **Engagements:** Facebook posts, likes, shares, comments; Twitter tweets, retweets, likes; YouTube shares, comments; etc.

**In the boxes below, please share a selection of audience comments or quotes from social media made about your project:**

|  |
| --- |
| Amazing show by #departcircus for #hullcityofculture2017 with @ollybrown24. Great atmosphere and incredible acrobatics! |
| Had a great night watching #DEPARTcircus in #Hull tonight. Absolutely mesmerising. City of Culture status definitely suits us. #proud |
| Another week, another spectacular #Hull2017 event. #Departcircus was amazing |
|   |
|  |

**vii. PARTNERS**

**Overall, how many partners were involved with your project?**

|  |  |  |
| --- | --- | --- |
|  | **TOTAL BASED IN** **HU1 – HU9** | **TOTAL BASED OUTSIDE** **HU1 – HU9** |
| **PARTNER TYPE**  |
| Artistic partner (e.g. theatre, art gallery, music venue) | 1 | 7 |
| Heritage partner (e.g. museum, archive) (Cemetery site) | 1 | 0 |
| Funder (e.g. Arts Council England, business, private trust) | 0 | 1 |
| Public Sector partner (e.g. libraries, GPs) |  |  |
| Voluntary sector partner (e.g. community group, charity) | 2 | 0 |
| Education (e.g. school, college, university) | 1 | 0 |
| Other |  |  |
| **PARTNERSHIP STAGE** |
| Number of new partnerships established via this project | 4 | 0 |
| Number of existing partners involved in this this project | 0 | 6 |

Thinking about your project as a whole, what would you say have been the **main successes** and **challenges** in terms of your partnerships on this project? **-** - **Please see the Partner Question Bank in the Hull 2017 Reporting Toolkit for the type of questions to ask**

Successes:

* Cooperation and involvement of local groups, especially the Friends of the Cemetery and Hull Freedom Chorus
* Cooperation and facilities provision by local school greatly aided ten smooth running of the project

Challenges:

* None