## Events BUDGET & TIMELINE
2017 THEATRE SECTOR EVENTS
HJG
WHAT | ROUGH DATE | DETAIL | ESTIMATE | ACTUAL | Notes/Updates
PHOTOSHOOT | January | Coffee | 50 | 50 | Complete.
Image of Emerging theatre sector |  | Party Poppers | 1 | 3.03
|  | SUBTOTAL | 51 | 51
FEB THEATRE PARTY | February | Drinks | 69.25 | 69.25 | Complete.
Hull Arts get-together. Sarah Brigham/JOAN. |  | Taxi and Tickets | 92 | 92
|  | SUBTOTAL | 161.25 | 133.25
TARGET SESSION/PRODUCER GURU: Roaring Girls | March 17th | John Tomlinson Fee @2 Days | 200 | 100 | Complete.
Managing teams and Contracting Freelancers |  | John's Travel Manchester/Hull rtn | 120 | 41.52
|  | SUBTOTAL | 320 | 141.52
MASTERCLASS: ALT SPACES/PR | April | Kardomah Hire Fee | 60 | 60 | Complete.
2017 producers on making/presenting work in alt spaces |  | Consumables | 10 | 9.15
|  |  | 70 | 69.15
MAY 25th THEATRE PARTY: ALEX KELLY/THIRD ANGEL | May 25th | Fee | 250 | 250 | Complete.
On inviting conversations with audiences. |  | M&E Board | 22 | 22
|  | Room Hire and Snacks | 75 | 62.5
|  | Drinks | 200 | 85.1
|  | Travel | 60 | 60
|  | SUBTOTAL | 607 | 479.6
MASTERCLASS: Arts Council 1:1 | June 9th | Room Hire | 40 |  | He hasn’t invoiced, I've chased twice
Hannah Bentley |  | Travel | 0 | -
|  | SUBTOTAL | 40 | 0
MASTERCLASS: Audience Development | June 22nd | Audience Development Agency | 400 | 375 | Complete.
Oliver Bliss. |  | SUBTOTAL | 400 | 375
2 day MASTERCLASS: Sarah Sansom Strategy | September 28th & 29th | Sarah Sansom Fee | 700 | 700 | Complete.
Learning skills to plan strategic development. 4-5 x 2 hour sessions and an open workshop. |  | Travel | 0
|  | Accommodation (3 nights) | 200 | 200
|  | SUBTOTAL | 900 | 900
DEVOTED AND DISGRUNTLED | October 6th | See Separate Sheet | 1410 |  | HELEN EXPENSES TO PAY. See separate sheet.
Improbable Theatre, networking event.Run by Lee.Children's Library. |  | Rachael Assisting Fee | 150
|  | SUBTOTAL | 1632.5 | 1715.02
Hull MASH UP | November 15th | 50% of cost of Pizza | 67.5 | 67.5 | Complete.
With Lincoln OpenPlan. |  | SUBTOTAL | 67.5 | 67.5
DIRECTORS/WRITERS DAY | January 19th/Feb 7th | Speakers Fees | 1200
Tess Seddon directing and producing this event. |  | Curator/Producer/PM Fee | 1000
|  | Travel | 300
|  | Consumables | 373
|  | SUBTOTAL | 2873 | 2873
JANUARY 2018 THEATRE MASH UP | January TBC | Food/Drinks | 450
Roaring Girls |  | Roaring Girls | 300
|  | SUBTOTAL | 750 | 750
|  |  | CONTINGENCY | 400
TOTAL |  |  | 7804.75 | 7955.04
|  |  | Travel/Accomm Actual | 2045.73
|  |  | TOTAL SPEND | 10000.77
|  | SARAH TRAVEL @170 | bills to pay | 140
|  | GONE OUT | 4311
|  | TESS | 2873
|  | RGIRLS INVOICE | 360
|  | RGIRLS THEATRE MASH UP | 750
|  | CONTINGENCY | 400
|  | HELEN EXPENSES | 90.05
|  | SUBTOTAL | 8784.05
|  | BOOKS FROM COUNCIL/HELEN PRE BOOKKEEPING | 1061.44
|  | TOTAL | 9845.49

## TRAVEL, ACCOMM & TICKETS
HELEN GOODMAN: TRAVEL, ACCOMMODATION AND ENTRANCE FEES
|  | ESTIMATE | ACTUAL | +/- | Notes
13-18 Feb | NDT EMERGING SHOWCASE
| Travel (petrol) | 100 | 104.76 | -4.76 | Helen Expenses Paid
| Accommodation | 50 | 150 | -100 | Lola hasn’t invoiced for this?
2017-02-20 | MANCHESTER/YOU THE AUDIENCE SYMPOSIUM |  |  | 0
| Travel (petrol) | 75 | 75.95 | -0.95 | Helen Expenses Paid
| Ticket | 18 | 18 | 0 | Helen Expenses Paid
2017-03-23 | LONDON THEATRE UK NETWORKING EVENT
| Travel (train) | 60 | 69.5 | -9.5 | Paid on HIPI card 13/03/17/Receipt on email: helenage
| Ticket | 60 | 100 | -40 | TO PAY
2017-08-01 | EDINBURGH FESTIVAL
| Travel | 100 | 108.12 | -8.12 | Includes Taxis and Trains
| Other Expenses (coffees) |  | 23.8 | -23.8 | Hull Take Over Companies early morning meeting & meeting with paines plough
| Accommodation (1week) | 500 | 1375 | -875
OTHER TRAVEL/JOURNEYS
| Travel | 400 | 20.6 | 379.4 | Meeting in Leeds then Networking in York
| Accommodation | 200 |  | 200
| Tickets | 100 |  | 100
| TOTAL | 1663 | 2045.73 | -382.73

## D&D
D&D: capacity @120 people (12 comps, 8 free tix)
1 day only event
INCOME 1: £5 tickets |  |  |  | INCOME 2: free tickets
Ticket Sales | 100 people @£5/ticket | 500 |  | Ticket Sales | 100 people @£0/ticket | 0
EXPENDITURE |  |  |  | EXPENDITURE
Improbable Fee, Travel, Accomm | Fixed Fee | 900 | See below | Improbable Fee, Travel, Accomm | Fixed Fee | 900 | See below
Tea and Coffee | Provided by Library | 150 | Estimate TBC | Tea and Coffee | Provided by Roaring Girls | 360
Artist D&D Kit | Fixed Fee and Materials | 200 | Estimate TBC | Artist D&D Kit: Anna Bean | Fixed Fee and Materials | 360
|  |  |  | Wristbands |  | 12.5 | TO CLAIM
|  |  |  | Stationary Expenses | Helen Expenses | 82.52 | TO CLAIM
| TOTAL | 1250 |  |  | TOTAL | 1715.02
SUMMARY |  |  |  | SUMMARY
IN | 500 |  |  | IN | 0
OUT | 1250 |  |  | OUT | 1715.02
TOTAL | -750 |  |  | TOTAL | -1715.02
IMPROBABLE FEE BREAKDOWN
Fees 1 (facilitator) | in kind
Fees 2 (co-ordintaor) | 375
Travel 1 | 120
Travel 2 | 120
Accom 1 | 100
Accom 2 | 100
Per Diem 1 | 50
Per Diem 2 | 50

## Bookkeeping
| ACCOUNTS | BANK TRANSACTIONS
DATE | ITEM | OUT | IN | BALANCE | RECEIPT #
2017-03-01 | Opening Balance |  | 5000 | 5000
2017-03-13 | Travel for Touring Symposium Trainline | 69.5 |  | 4930.5 | 1
| Expenses Repaid: NDT Showcase Travel | 104.76 |  | 4825.74 | 2
| Expenses Repaid: Manchester Travel | 75.95 |  | 4749.79 | 3
| Expenses Repaid: Manchester Audience Ticket | 18 |  | 4731.79 | 4 | missing receipt - have emailed mrexchange
| Expenses Repaid: Photoshoot Coffee | 50 |  | 4681.79 | 5 | missing receipt - theiving harry's
| Expenses Repaid: Party Poppers | 3.03 |  | 4678.76 | 6
| Expenses Repaid: Feb Party Drinks | 69.25 |  | 4609.51 | 7
| Expenses Repaid: Feb Party Taxi | 12 |  | 4597.51 | 8
| John Tomlinson Fee @£100 + Expenses | 140.2 |  | 4457.31 | 9
2017-04-19 | Accommodation for London NDT Showcase | 150 |  | 4307.31
2017-04-24 | Travel to Manchester for YTR/Hull Network | 29.75 |  | 4277.56
2017-05-04 | BTOurs Tickets JOAN | 80 |  | 4197.56
2017-05-08 | S.Sansom Accommodation for Sept IBIS | 199 |  | 3998.56
2017-05-17 | Kardomah 94 Hire Alt Spaces Masterclass | 60 |  | 3938.56
|  |  |  | 1061.44 | TOTAL SPENT (from 5k)
From thereon, Hull2017 accounting.