## production schedule
DAY/DATE | TIME | DETAIL | NOTES | WHO | COMPANY | CREW REQD | VEHICLES
Sun 6th August | 1600 | Adam on site | Do Mark-up, photograph site, handover etc | AL | TGE | 0 | Van
Mon 7th August | 800 | Security on site |  | AL | Prestige | 0
| 800 | Begin Trakway install |  | AL | LIVE | 0
| 900 | Fencing delivered |  | AL | Actavo | 0
| 900 | Plant delivered | Forks & telehandler | AL | Nixons | 0
| am | Do Ground survey? |  | AL |  | 0
| am | build production compound |  | AL |  | 0
| am | toilets delivered |  | AL | Add Plant | 0
| pm | Distro delivered | Telehandler required | AL | IDE | 0
| 2000 | security changeover |  |  | Prestige | 0
| 2000 | Finish |  | AL |  | 0
Tues 8th August | 800 | security changeover |  |  | Prestige
| 800 | continue Trakway |  |  | LIVE
| am | cone off truck parking area |  | AL | TGE
| am | Comms delivered | to pacific exchange |  | 900 communications
| 900 | Generators delivered | fork in to position | AL | John F Hunts
| 1000 | Marquees delivered | Build production tent | AL | Nationwide
| am | Bins delivered | 2 x 1100l & 8 x 240l |  | Hull CC
| pm | collect comms | from 2017 office | AL | 900 communications
| pm | install backstage power | Test | AL
| 1600 | trakway handover |  | AL | LIVE
| pm | build show/build compound | ped barrier | AL
| pm | install production power | Test | AL
| 2000 | security changeover |  |  | Prestige
| 2000 | Finish |  | AL
Weds 9th August | 800 | security changeover |  |  | Prestige
| 900 | Trucks arrive | Adam to position (is there a possibility to turn the trucks easily at the end of the lane near the stadium, to unload the other side, or were branches of trees too low on that end?) if possible it would be great to have, if it helps for unloading, bench or litter bin removed | AL
| 1030 | Jan on site | Do mark-up | AL | Cirk Vost | 4 stage
| 1100 | Crew on site |  |  | TMC & freelancers | 4 stage
| 1100 | begin unload |  |  | Cirk Vost
| 1300 | LUNCH |  | ALL
| 1400 | finish unload and begin build |  | AL | Cirk Vost | 4 stage
| pm | Distribute fire extinguishers |  | AL | TGE
| 1900 | crew finish |  |  | TMC & freelancers | 4 stage
| 1900 | Continue and prepare for crane |  | AL
| 2000 | security changeover |  |  | Prestige
| 2200 | finish |  | ALL | Cirk Vost
Thurs 10th August | 800 | security changeover |  |  | Prestige
| 800 | On site |  | AL | Cirk Vost
| 800 | Crane on site & set-up | Jan to position | AL | Central cranes
| 900 | Crew on site | assist with build |  | TMC | 4 stage
| 900 | Crew on site | begin rig |  | Freelancers | 2 lx
| 900 | lighting stands delivered |  |  | 3d
| am | toilets serviced |  |  | Add Plant
| 1300 | Crane off site | booked for 8 hours |  | Central cranes
| 1300 | LUNCH
| 1400 | Continue |  | All | All | 4 stage, 2 lx
| pm | Production meeting | production tent/green room | AL, KF, HW-W, LM, GH, CT
| 1600 | Rig festoon |  | AL
| 1800 | crew finish |  |  | TMC & freelancers | 4 stage, 2 lx
| 1800 | Dinner |  | All | All
| 2000 | security changeover |  |  | Prestige
| 2200 | finish |  | ALL | Cirk Vost
Fri 11th August | 800 | security changeover |  |  | Prestige
| 800 | On site |  | AL | Cirk Vost
| 900 | Crew on site | Deckchairs and finalise |  | TMC | 4 stage
| 900 | Crew on site |  |  | Freelancers | 3 lx
| 900 | PA company on site | Set-up FOH PA | AL | 3d productions | 3d
| 900 | Rig lx |  |  | Cirk Vost | 3 lx
| am | toilets serviced |  |  | Add Plant
| am | Site safety walk round |  | AL, GH
| am | Set-up site lighting |  | AL | TGE
| 1300 | Lunch
| 1400 | Continue |  |  | ALL | 4 stage, 3 lx
| 1400 | Continue site lighting check |  | AL | TGE
| pm | soundchecks |  |  | 3d/Cirk Vost
| pm | Public toilets delivered | AL to site, crew to compound | AL | AddPlant | 4 stage
| pm | trucks off site |  |  | Cirk Vost
| 1800 | crew finish |  |  | TMC | 4 stage
| 1800 | Dinner |  |  | ALL
| 1900 | continue as required |  | AL | ALL
| 2100 | Focus & plot |  |  | Cirk Vost | 3 lx
| 2000 | security changeover |  |  | Prestige
| 2300 | Finish | Lighting will go later? | ALL | Cirk Vost
Sat 12th August | 800 | security changeover |  |  | Prestige
| 900 | Work as required |  |  | Cirk Vost
| 900 | build heras compound | for football match | AL | TMC | 6 x crew
| 900 | tidy site | Inc. site dressing | AL | TGE
| am | Production meeting | in café/production tent | AL, KF, HW-W, LM, GH, CT
| 1300 | Lunch
| 1400 | continue as required | some rehearsals on rig | AL | ALL
| pm | final site checks |  | AL
| pm | sound checks |  |  | Cirk Vost, 3d productions
| 1730 | De-rig Heras compound | when safe to do after match | AL | TMC | 6 x crew
| 1800 | Dinner |  |  | ALL
| 1900 | medical on site |  |  | Heart
| 1900 | Pre show checks |  |  | Cirk Vost
| 1900 | Volunteer briefing |  | ???
| 1930 | Show security on site | Gareth to brief | GH | Prestige
| 2000 | carpark up & running |  |  | Prestige
| 2030 | gates to deckchairs open
| 2130 | SHOW 1
| 2230 | Show finish
| 2300 | Clear site
| 2300 | Finish & Turn off | may need to refocus some lighting
| 2330 | security changeover |  |  | Prestige
Sun 13th August | 800 | security changeover |  |  | Prestige
| am | toilets serviced |  |  | Add Plant
| am | cleansing on site |  |  | Hull CC
| 1100 | Work as required |  | AL | Cirk Vost
| 1300 | Lunch
| 1400 | continue as required |  | AL | ALL
| pm | Soundchecks |  |  | Cirk Vost, 3d productions
| pm | final site checks |  | AL
| 1800 | Dinner |  |  | ALL
| 1900 | medical on site |  |  | Heart
| 1900 | Pre show checks |  |  | Cirk Vost
| 1900 | Volunteer briefing |  | ???
| 1930 | Show security on site | Gareth to brief | GH | Prestige
| 2000 | carpark up & running |  |  | Prestige
| 2030 | gates to deckchairs open
| 2130 | SHOW 1
| 2230 | Show finish
| 2230 | Begin get-out - Finish @ 0100 | deck chairs, lighting & sound | AL | Cirk Vost, freelancers, TMC | 8 stage, 3 lx
| 2230 | sound get-out |  |  | Cirk Vost, 3d productions
| 2300 | Clear site
| 2300 | re-instate build barriers | set-up tower lights | AL
2330
| 2330 | security changeover |  |  | Prestige
| 100 | Finish
Mon 14th August | 800 | security changeover |  | AL | Prestige
| 800 | On site |  | AL | Cirk Vost
| 800 | Crane on site |  | AL | central crane services
| 800 | crew on site | De-rig | AL | Cirk Vost | 4 stage, 2 lx
| am | Cleansing on site | clean audience areas |  | HULL CC
| am | Public toilets collected |  |  | Add Plant
| am | De-rig site lighting |  | AL
| 1000 | Trucks on site |  |  | Cirk Vost
| 1300 | Crane off site |  |  | central crane services
| 1300 | Lunch
| 1400 | Contnue & load | De-rig show compound |  | Cirk Vost | 4 stage, 2 lx
| pm | production power out |  | AL | TGE
| 1630 | Cirk Vost leave |  |  | Cirk Vost
| 1700 | Tidy show site |  | AL | TGE
| 2000 | Finish |  | AL | TGE
| 2000 | security changeover |  |  | Prestige
Tues 15th August | 800 | On site | de-rig backstage power | AL | TGE
| 800 | Remove trak |  |  | LIVE
| 900 | remove marquee |  |  | Nationwide
| 1000 | Remove production compound |  | AL | TGE
| am | Cleansing on site | clean all |  | HULL CC
| am | return comms | to pacific exchange | AL | TGE
| 1100 | Distro collected | telehandler required | AL | IDE
| 1200 | Generators collected | Forks required | AL | John F Hunts
| 1300 | Lunch
| 1400 | Barriers collected | telehandler required | AL | Actavo
| pm | bins collected |  |  | Hull CC
| pm | Comms collected | from Pacific exchange |  | 900 communications
| 1700 | Trakway finished |  |  | LIVE
| 1700 | plant collected | Forks & telehandler |  | Nixons
| 1800 | final tidy & site check | Hand back to park | AL | TGE
| 1900 | Off site |  | AL | TGE

## production contacts
NAME | COMPANY | WHAT | MOBILE NUMBER
Adam Long | TGE | Prodction manager | 07754 728316
Katy Fuller | Hull 17 | Exec producer | 07771 764656
Gareth Hughes | Hull 17 | Event manager | 07733 112272
Hannah Williams-Walton | Hull 17 | Producer | 07500 838553
Lily Mellor | Hull 17 | Assistant Producer | 07740 557720
Carys Taverner | Hull 17 | Assistant PM | 07851 077582
Steve McKee | Hull cc | Cleansing | 07789 372506
HCAL
HCAL
Jan Naets | Cirk Vost | Technical manager | 33698921034
Gaz Harding | 3d Productions | Sound engineer | 07834 058259
Mark Hare | LIVE events | Trakway | 07725 028122
Dave Graham | Nixon Extra | Plant hire | 07917 507314
Brian | Nationwide | Marquee Hire | 07775 515398
Stuart Barnett | IDE | Distro Hire | 01543 574111
Jean Byers | John F Hunt | Generators | 0191 4111200
Joy Whitley | Actavo | Barriers & fencing | 01652 601390
Paul | Heart Medical | Medical | 07764 926970
Justine peacocock | Prestige | Stewarding & child protection | 07886 838597
Jon Masters | Add Plant | toilets & plant | 07738 817940
Rona | The Music consortium | local crew | 07710 024749
Josh | Freelancer | lighting tech
| Freelancer | lighting tech
| Freelancer | lighting tech
| Freelancer | Site crew