|  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- |
| **ARTIST** | **CONTACT** | **OUTLINE** | **AREA** | **KEY DATES** | **TO DO** |
| **Joshua Sofaer** | joshua@joshuasofaer.com<http://www.joshuasofaer.com/> | Nose Emporium  | Bransholme North Point Shopping Centre – Louise Smith  | 27/28 July site visit28 – 30 August get in31-4 Sept – Live 5 Sept get out | Marketing steer – Nose to see you # or 2017?Safeguarding – DBS check to be sent in, policy/guide advice to be givenRisk Ass & PL to be sent to centreSet design planVolunteer requirements sent to SR |
| **Periplum****Claire Raftery****Damian Wright** | periplumperformance@googlemail.com<http://www.periplum.co.uk> | Message in a Bottle | East – Greatfield with workshops also on Preston roadGreatfield Hub – Claire Taylorclaire@greatfield.org.uk Child Dynamix – Paul Clark Paul.Clark@childdynamix.co.ukPurple House - Christina Reading Christina.Reading@purplehouse.co.ukSt Stephens – Jennie Masonjennie\_mason@hotmail.com | Dates to be discussed – workshops late August – residency Late Sept & early Oct | Site visit 12 July Getting delivery options & contacts – Milk float ongoingList of east & north groups – Site visit to Preston Road & GreatfieldSchedule of deliveries – a more realistic plan than 7 consecutive days Bottle designRearrange meeting with Claire Taylor |
| **Davy & Kristin McGuire** | davyandkristinmcguire@gmail.com<http://www.davyandkristinmcguire.com> | Little Film Scenes  | North/WestBingo Hall & Anlaby Rd | 7 – 12th Sept Live | Hire car – extra info required by foxy – EB to get other care hire contact for LOGG artistsLocation advice – Anlaby Road, outside of bingo hall and doorway for 2016 possibly inside for 2017Permissions for bingo hallOther site along Anlaby Rd to be identified Story board |