|  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- |
| **ARTIST** | **CONTACT** | **OUTLINE** | **AREA** | **KEY DATES** | **TO DO** |
| **Joshua Sofaer** | [joshua@joshuasofaer.com](mailto:joshua@joshuasofaer.com)  <http://www.joshuasofaer.com/> | Nose Emporium | Bransholme North Point Shopping Centre – Louise Smith | 27/28 July site visit  28 – 30 August get in  31-4 Sept – Live  5 Sept get out | Marketing steer – Nose to see you # or 2017?  Safeguarding – DBS check to be sent in, policy/guide advice to be given  Risk Ass & PL to be sent to centre  Set design plan  Volunteer requirements sent to SR |
| **Periplum**  **Claire Raftery**  **Damian Wright** | [periplumperformance@googlemail.com](mailto:periplumperformance@googlemail.com)  <http://www.periplum.co.uk> | Message in a Bottle | East – Greatfield with workshops also on Preston road  Greatfield Hub – Claire Taylor  [claire@greatfield.org.uk](mailto:claire@greatfield.org.uk)  Child Dynamix – Paul Clark [Paul.Clark@childdynamix.co.uk](mailto:Paul.Clark@childdynamix.co.uk)  Purple House - Christina Reading [Christina.Reading@purplehouse.co.uk](mailto:Christina.Reading@purplehouse.co.uk)  St Stephens – Jennie Mason  [jennie\_mason@hotmail.com](mailto:jennie_mason@hotmail.com) | Dates to be discussed – workshops late August – residency Late Sept & early Oct | Site visit 12 July  Getting delivery options & contacts – Milk float ongoing  List of east & north groups – Site visit to Preston Road & Greatfield  Schedule of deliveries – a more realistic plan than 7 consecutive days  Bottle design  Rearrange meeting with Claire Taylor |
| **Davy & Kristin McGuire** | [davyandkristinmcguire@gmail.com](mailto:davyandkristinmcguire@gmail.com)  <http://www.davyandkristinmcguire.com> | Little Film Scenes | North/West  Bingo Hall & Anlaby Rd | 7 – 12th Sept Live | Hire car – extra info required by foxy – EB to get other care hire contact for LOGG artists  Location advice – Anlaby Road, outside of bingo hall and doorway for 2016 possibly inside for 2017  Permissions for bingo hall  Other site along Anlaby Rd to be identified  Story board |