## Milestones
Week | Dates | Headings | Actions | Completed/Follow Through
Week 28 | 22nd August to 28th August
|  | Think Ins structure | the plan for how open/invited thinkins will work
|  | Plan of Attack | the schedule from Henri/how we programme.
|  | Circle of Friends | Preparation for the next meeting
|  | Marketing and Comms | What do we want from Marketing and Coms.
|  | Book in Think ins | Booking public space
|  | Hairdressers | Have a chat with haire dressers on Newland how to gather
Week 27 | 29th August to 4th September
|  | Think in Meeting | Planning and Prep
|  | Marc Comms | Meeting
|  | City Hall Visit | MO to take lots of photos
Week 26 | 5th Sept to 11th September
|  | POW WOW | Meeting with LH, BR, MO CoF and Think ins
|  | Meeting with Barbara | How to documment the process
|  | WOW Core activities | Mentors etc.
|  | Circle of Friends | Tasks and outreach for CoF
Week 25 | 12th Sept to 18th Sept
|  | Think Ins | Dates confirmed and marketing signed off
all venues confirmed.
|  | Programming | Schemes for feedback and promotion
Meeting with Heads up/BFI/ Hull Truck
|  | Bradford | Meeting with Evie Manning
|  | Marketing | Website
Week 24 | 19th Sept to 25th Sept
|  | Education | Campaign and activities for schools
|  | Volunteers | Confirm volunteer support thinkins
|  | Digital Launch | with 2017 launch?
|  | Thinkins | Structure and equipment signed off
Week 23 | 26th Sept to 2nd Oct
|  | Thinkins | First Thinkins and feedback/ data feedback
|  | Headliners | Meeting and Short list of Headliners
|  | Review? | Review points
|  | Programming | Performances/Artists - Rash Dash/Ethel Leginska etc
Week 22 | 3rd Oct to 9th Oct
|  | Circle of Friends | Meeting - Report on First thinkins/Bradford and the rest of the programme
|  | Thinkins | Next Thinkins's and feedback/ data feedback
|  | Programming | Headliners and Performances on going
Schedule programme - Wow core activites
Week 21 | 10th Oct to 16th Oct
|  | Thinkin | Next Thinkins's and feedback/Big Think in Structure
|  | Programming | Draft Programming proposal
Headliners/Performances/
Subjects and Speakers Long list
|  | Ideas | Hairdressing/Coffee Cards/Hull Heroes
City Hall Dress up Ideas and Planning - Campaign to launch at big thinkin
|  | Marketing | Pushing Big Thinkin
Week 20 | 17th Oct to 23rd Oct
|  | Thinkin | Next Thinkins's and feedback/ data feedback
|  | Programming | Meeting with HD,LH,BP to go over draft programme for WOW Southbank
Subject and Speakers Shortlist
Legacy impact?
|  | Ideas | Hairdressing/Coffee Cards/Hull Heroes
City Hall Dress up Ideas and Planning - Campaign to launch at big thinkin
|  | Marketing | Pushing Big Think In
Week 19 | 24th Oct to 30th Oct
|  | Programming | WOW Southbank 1st Deadline
|  | Thinkins | Next Thinkins's and feedback/
Compile Data Feedback
|  | Ideas | Hairdressing/Coffee Cards/Hull Heroes
Week 18 | 31st Oct to 6th Nov
|  | Thinkins | Big Think in
|  | Programming | Headliners update/Performances
|  | Circle of Friends | Meeting and repoting on the draft programme
|  | WOW Bradford | Attend, learn and represent Hull WOW
|  | Ideas | Hairdressing/Coffee Cards/Hull Heroes
Week 17 | 7th Nov to 13th Nov
|  | Thinkin evalautation | Evaluation and research
Investigation on feedback for Thinkin
Programming
|  | Idea | Crafts Call Out? Community element
Week 16 | 14th Nov to 20th Nov
|  | Programming | Market Place Ideas and List
Workhop and Hull Bites
Headliners/Performances/Speakers/Talks update
Workshops/Hull Bites Provisional Lists
Commissions
Week 15 | 21st Nov to 27th Nov
|  | Programming | Ferens Studio Confirmed
Saturday Schedule Outline
Sunday Schedule Outline
Research and Details.
Week 14 | 28th Nov to 4th Dec
|  | Programming | Panel speakers outline and letters approached.
Hull Bites Scheduled
|  | Circle of Friends | Circle of Friends meetings
|  | Marketing | WOW Brochure
WOW Film List

## Adjusted timeline
Adjusted Milestone
Week 15 | 21st Nov to 27th Nov
|  | Programming | Ferens Studio Confirmed
Saturday Schedule Outline
Sunday Schedule Outline
Research and Details.
Week 14 | 28th Nov to 4th Dec
|  | Programming | Panel speakers outline and letters approached.
Hull Bites Scheduled
|  | Circle of Friends | Circle of Friends meetings
|  | Marketing | WOW Brochure
WOW Film List
Week 13 | 5th Dec to 11th Dec
|  | Programming | 2nd South Bank Deadline
|  | Marketing | WOW Brochure Signed Off
Week 12 | 12th Dec to 18th Dec
|  | Planning | Event plan the festival
Week 11 | 19th Dec to 25th Dec |  | Christmas Break
Week 10 | 26th Dec to 1st Jan |  | Christmas Break
Week 9 | 2nd Jan to 8th Jan
|  | Event | Commissions
Community Craft making
Production Meeting - requirements
|  | Marketing | Digital Campaign
Distribution
Week 8 | 9th Jan to 15th Jan
|  | Event | Commissions
Community
Production - Staffing
Week 7 | 16th Jan to 22nd Jan
|  | Event | Commissions
Community
Production - Staffing
Week 6 | 23rd Jan to 29th Jan
|  | Event | Commissions
Community
Production - Staffing
Week 5 | 30th Jan to 5th Feb
|  | Event | Commissions
Community
Production - Staffing
Week 4 | 6th Feb to 12th Feb
|  | Event | Commissions
Community
Production - Staffing
Week 3 | 13th Feb to 19th Feb
|  | Event | Commissions
Community
Production - Staffing
Week 2 | 20th Feb to 26th Feb
Week 1 | 27th Feb to 5th March
Production Week