**LOGG WEEKLY ACTIVITY UPDATE**

|  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- |
|  | **PUBLIC FACING EVENTS/MOMENTS** | **INTERNAL**  | **PRESS** | **DIGITAL** | **OTHER** |
| **Monday 5 June** | A large stack of crates is delivered to Northpoint Atrium by GGF (including ginger smelling one)  | Weekly catch up  |  |  |   |
| **Tuesday 6 June** |  |  |  |  |  |
| **Wednesday 7 June**  | Crate disappears  |  |  | GGF open the crate, which is full of noses from last year |  |
| **Thursday 8 June**  |  |  Budget catch upAswarm MarComms chat Macnas catch up  |  |  |  |
| **Friday 9 June**  | Crates start disappearing into shop  |  | HDM print article about the noses being found / can now reveal a space at NP will be nose house for showing the gold nose temp until Aug. |  |  |
| **Saturday 10 June**  |  |  |  |  |  |
| **Sunday 11 June**  |  |  |  |  |  |

**Updates**

Lone Twin

- And Now: contract is nearly finalised

- Licence notice has been confirmed for Lone Twin activity week and finale

- GH writing EMP for Guild of Commoners

Davy

- Springhead Pumping Station now confirmed as venue for McGuire’s Cardboard City

- Garth West have agreed to supply all cardboard for Cardboard City, following a meeting with Davy and Elizabeth, and are very excited by the project

- McGuires filming in Hull now due to take place in August (instead of June). Participants are currently being identified.

Joshua

-Pamphlet getting finalized

-RAMS nearing completion

-Sponsorship confirmed with Jackson’s and North Point

-GH liaising with JS re: sound

-Schedule for 17th finalized

-M&E discussions around documentary occurring

Thor

-GH working on Yorkshire Water sponsorship

-EB scheduling recording sessions with JM, LY and Roisha

**Overdue**

-Periplum’s final budget breakdown and final payment

-Walk the Plank’s final budget breakdown and final payment

-Macnas contract draft

**Key Dates:**

17 June: Gold Nose of Green Ginger shop opens at North Point

3 – 6 July: Project VEAR voice collection

12 – 16 July: Project VEAR voice collection

9 – 15 July: Guild of Commoners activity live in Longhill

15 July: And Now bonfire, Longhill

19 August: Gold Nose of Green Ginger closing procession at North Point

6 – 9 September: Project VEAR voice collection

22 – 30 September: Project VEAR live at Pickering Park

20 October – 5 November: Cardboard City live at Springhead Pumping Station

11 November: Macnas parade in Old Town