## Sheet1
| Action | Deadline | Owner | Notes | Complete?
Programming | Secure venue |  | JZ |  | YES
| Select films |  | JZ |  | YES
Venue | Agree terms (price, hours)
The films (19 Nov) | Arrange DCP delivery
Receive DCP
Ingest DCP
Test DCP
Return hard drives
The films (26 Nov) | Arrange DCP delivery
Receive DCP
Ingest DCP
Test DCP
Return hard drive
Tickets - advance info | Agree key info (times, prices, copy)
Communicate key info
Populate Spectrix
Ensure visibility, unbroken links and correct, consistent info on HBO, Hull2017, and Culturenet
Check the above for gremlins every Monday and Friday until the event has passed
Coordination with FFFUK | Supply FFFUK with UoH/Hull 2017, BFI/FHN logos |  | JZ |  | YES
| Supply FFFUK with programme information |  | JZ |  | YES
| Supply FFFUK with URL for their programme |  | JZ
Liaise with FFFUK re: taking advantage of their publicity for the UK-wide festival (eg. acquiring copies of their print puiblicity)
Periodically check info and links on FFFUK site
Digital promotion readiness | Acquire via FFFUK images and copy to promote each film
Produce and get checked copy and images for email
Produce and get checked copy and images for Facebook
Produce and get checked copy and images for sites (eg HBO, HIC)
University comms | Negotiate social media schedule (Facebook/Twitter) with Marcomms
Include event in FACE Events mailout to all University members
Request targeted mailout to University students with French nationality/domicile
Request HUU mailout
| Mailout and comps offer to School of Arts students |  | JZ
| Include event in Culturenet mailout |  | JZ
Generate digital signage
Have event visible on screens in Library/Middleton Hall
Hull2017 comms | Negotiate social media schedule (Facebook/Twitter) with Hull2017
HIC comms | Negotiate and schedule mailout to HIC's mailing list
Boosted Facebook ads through HIC
Spreading the word | Solicit email recirculation, social media sharing, etc, with and associates, eg. Screen Yorkshire, BFI, Beverley Film Society |  | All
Event delivery | Request Hull2017 volunteers
Manage Hull2017 volunteers
Arrange Front of House team (box office mainly)
Agree set-up for Q&A with Yannik (filmmaker)
Wrangle Yannik
Prepare questionnaires
Get patrons to complete questionnaires
Post event | Acquire accurate box office info and supply it to FFFUK/distributors
Process invoices with awareness of correct cost code
Process questionnaires
Produce post-event evaluation, including final budget