**CREATIVE COMMUNITIES PROGRAMME**  
**PROJECT UPDATE REPORT**

**GENERAL INFORMATION**

|  |  |
| --- | --- |
| **PROJECT NAME:** | I Wish To Communicate With You |
| **PROJECT LEAD:** | Sharon Darley |
| **REPORT DATE:** | 15/03/2017 |

**INTRODUCTION**

Everyone who receives a grant from the Creative Communities Programme must complete this Project Update Report by the dates on the accompanying reporting schedule. Please read it straight away – you will need to collect the information throughout the lifetime of your project.

Please refer to your Agreement, and any changes you agreed with us, when you complete this Project Update Report form.

This Project Update Report tells us:

* What has happened during your project to date;
* Your current income and expenditure figures;
* What you have learned so far, and how you have adapted to these learnings.

We will send you a separate online survey about your experience of the Creative Communities Programme. We will process the information you to understand:

* The effect of our grant and support to date;
* The current effectiveness of our services and grants administration; and
* Where and how we need to make changes. We also use this information to report to our funders.

Please email this activity report to: creativecommunities@hull2017.co.uk

1. **PROJECT REPORT**

Please provide a brief update (3 or 4) sentences on each of the following areas to let us know how your project is going and how we can support you.

**EVENT PLANNING AND PROJECT MANAGEMENT**

Planning and project management is flexible and responsive.

With on-going support from James Bawn (Element 3 Design) we are able to respond in a measured way to unforeseen challenges as and when they present themselves; adapting our delivery accordingly, dependent on each block and the people who live there; therefore project management is focused and responsive to the community involved *and* to specific contexts.

**MARKETING AND COMMUNCIATIONS, PARTICIPATION AND LEARNING**

Face-to-face, flyers/posters, door-knocking, local press, national press, Facebook, Twitter, Instagram, Goodwin website.

- Blocks completed so far: 2 x Melville Street (Block 1 & 2) / 1 x New Michael Street / 3 x Porter Street (Block 1, 2 & 3).

- 600 residents (so far).

- 1 full-time resident volunteer who has gone on to be invited to sit on Goodwin’s Housing Board.

**RISK REGISTER**

We have sent you a template of a Risk Register with example risks that projects may face. Please complete this return with the Project Update Report.

**Please use the space below for any comments and supporting information.**

Risk: Residents did not want the installation – Solution: Substantial face-to-face consultation. Poster’s, leaflets, door-knocking in order to attain a good level of understanding for residents so they could make an informed decision.

Risk: H&S - Lux Levels wouldn’t meet the required standard – Solution: James Bawn (Element 3 Design) as consultant and H&S officer.

Risk: Little or no support from Hull city Council – Solution: Successfully identify specific individuals to work with.

Risk: Installation had low-impact – Solution: Trust our experience and knowledge.

**BUDGET UPDATE**

In this section we ask for a summary of the income and expenditure of your activity to date.

Pleasecomplete the Budget Template provided. The template includes instructions on how to complete it.

**Please use the space below for any comments and supporting information.**

No comment

**Specific Requirements - VAT**

If you are registered for VAT, your expenditure figures should not include VAT that you can claim back. If you are not registered for VAT, your figures should include VAT. You may need to get advice from your own accountant or the relevant tax office. For information about VAT and other taxes, contact HM Revenue and Customs (HMRC) through their website at [www.hmrc.gov.uk](http://www.hmrc.gov.uk)

**TIMELINE UPDATE**

We have sent you a copy of your original Project Timeline. Please complete the columns called Status and Notes to let us know if your project is on track.

**Please use the space below for any comments and supporting information.**

No comment

1. **MONITORING & EVALUATION REPORT**
2. **Event delivery**

**To date, how are you currently doing on reaching the targets laid out for project activity?**

|  |  |  |  |
| --- | --- | --- | --- |
|  | **ORIGINAL TARGET\*** | **REVISED TARGET\*** | **ACTUAL TO DATE\*** |
| **PROJECT VENUE/LOCATION** | | |  |
| HU1 – HU9 | 600 |  | 600 |
| Not HU1 – HU9 | City/World |  | City/World |
| **ACTIVITY** | | |  |
| Number of performances | 12 months |  | n/a |
| Number of exhibition days | 12 months |  | 3 months |
| Number of commissions\* | 1 |  | 1 |
| Number of sessions for education, training or taking part\* |  |  |  |
| Number of accessible activities | 1 |  | 1 |

**\*Original target: target(s) listed within your contract**

**\*Revised target: new suggested targets now that your project planning and delivery is underway**

**\*Actual to date: only complete this column if you have delivered some activity with the public**

**\*Commissions: a commission is defined as the hiring or payment to an artist / artistic company to create an art work or performance. A commission can be wholly or partly funded by you / your organisation.**

**\*Sessions for education, training or taking part: includes guided sessions, learning sessions, skills development workshops, formal training of volunteers, practical workshops, all other community/public facing workshops.**

If your project will incorporate heritage, please briefly say how you are developing, presenting and/or telling people about heritage or historical content, e.g. using heritage buildings or sites, collecting oral history (stories and memories), displaying historical artworks or collections, working with museums or archives, sharing or presenting historical stories or events.

n/a

1. **Project Delivery Team**

**This can include formal and informal feedback given to you by staff, freelancers and / or your own observations. You can use notes or minutes from project team meetings; informal conversations; emails; etc. to inform this.**

**Thinking about your project to date, what would you say have been the main successes for the project delivery team:**

- Successful installation of IWTCWY into 6 residential mid-rise blocks.

- Good team-dynamics

- Deadlines & targets met and surpassed

- No H&S issues

- Improving relationship with Hull City Council

**Thinking about your project to date, what would you say have been the main challenges for the project delivery team:**

- Working with Hull City Council – improving that relationship all the time

- Planning/communicating/travelling from different cities

1. **Audiences & Participants**

**To date (up to and including now), how many people have engaged with the project? If you are yet to do any public facing work, please leave this section blank.**

|  |  |  |
| --- | --- | --- |
| **TYPE OF ENGAGEMENT** | **ACTUAL TO DATE** | **% FROM HU1-HU9\*** |
| Number of audience members\* | 259,000 | ? |
| Number of participants\* | 600 | ? |
| **TOTAL BENEFICIARIES** |  |  |

**\*The % can be taken from the results of your audience and participant surveys or box office reports**  
**\*‘Audience members’ includes people going to an exhibition or performance, and people getting access to work that is printed, recorded, broadcast or on the internet.**  
**\*‘Participants’ means doing the activity.**

**Please complete the Total column within the tables below. You should collect this information using the Audience and Participant Surveys (which will be designed with support from the Hull 2017 team) and / or via the Participant Equal Opportunities Form provided in the Toolkit.**

|  |  |  |  |  |
| --- | --- | --- | --- | --- |
|  | **ACTUAL TO DATE** |  |  | **ACTUAL TO DATE** |
| **AGE GROUPS** | |  | **CONDITIONS** |  |
| 0-2 years |  |  | Learning disability |  |
| 3-5 years |  |  | Long-term illness/condition |  |
| 6-10 years |  |  | Sensory impairment |  |
| 11-15 years |  |  | Mental Health condition |  |
| 16-17 years |  |  | Physical impairment |  |
| 18-19 years |  |  | Cognitive impairment |  |
| 20-24 years |  |  | Other |  |
| 25-29 years |  |  | **ETHNICITY** |  |
| 30-34 years |  |  | Welsh / English / Scottish / Northern Irish / British |  |
| 35-39 years |  |  |
| 40-44 years |  |  | Irish |  |
| 45-49 years |  |  | Gypsy or Irish Traveller |  |
| 50-54 years |  |  | Any other White background |  |
| 55-59 years |  |  | White and Black Caribbean |  |
| 60-64 years |  |  | White and Black African |  |
| 65-69 years |  |  | White and Asian |  |
| 70-74 years |  |  | Any other Mixed/multiple ethnic background |  |
| 75+ years |  |  | Indian |  |
| Prefer not to say |  |  | Pakistani |  |
| **GENDER** |  |  | Bangladeshi |  |
| Male 86 | **86** |  | Chinese |  |
| Female |  |  | Any other Asian background |  |
| Transgender |  |  | African |  |
| Other |  |  | Caribbean |  |
| Prefer not to say |  |  | Any other Black/African/Caribbean background |  |
| **DISABILITY/LONG TERM ILLNESS** | |  | Arab |  |
| Yes |  |  | Any other ethnic group |  |
| No |  |  | Prefer not to say |  |

**This can include formal and informal feedback given to you by staff and / or your own observations. You can use comments books; informal conversations; emails; etc. to inform this.**

**Thinking about your project to date, what would you say have been the main successes for your audience members / participants:**

- Feeling part of Hull 2017.

- Feeling less isolated

- Feeling mentally well

- Feeling proud

**Thinking about your project to date, what would you say have been the main challenges for you / your audience members / participants:**

- For participants there have been none

- For audience the challenge has been to lose the preconceived negative ideas about the Thornton area

1. **Online Engagement**

**To date, how has your project impacted upon your online presence?**

|  |  |  |
| --- | --- | --- |
|  | **TOTAL PAGE VIEWS TO DATE SINCE PROJECT BEGAN** | **UNIQUE PAGE VEIWS TO DATE SINCE PROJECT BEGAN** |
| Website views relating to project |  |  |

|  |  |  |  |  |
| --- | --- | --- | --- | --- |
|  | **LIKES/FOLLOWERS AT START OF THE PROJECT** | **LIKES/FOLLOWERS SINCE PROJECT BEGAN** | **IMPRESSIONS ON POSTS RELATING TO THE PROJECT TO DATE** | **ENGAGEMENTS WITH POSTS RELATING TO THE PROJECT TO DATE** |
| Facebook |  |  |  |  |
| Twitter |  |  |  |  |
| Instagram |  |  |  |  |
| Other |  |  |  |  |

**DEFINITIONS**

* **Followers include:** Facebook Page Likes / Profile Friends; Twitter Followers; YouTube Subscribers; etc.
* **Impressions:** impressions (“views”) of Facebook posts linked to CCP project; impressions (“views”) of Twitter tweets linked to CCP project; views of YouTube videos linked to CCP project; etc.
* **Engagements:** Facebook posts, likes, shares, comments; Twitter tweets, retweets, likes; YouTube shares, comments; etc.

**In the boxes below, please share a selection of audience comments or quotes from social media made about your project:**

“I would love to help with this” – 19.03.2017 (Est of the Nat Facebook)

“Love it!” – 08.02.2017 (Est of the Nat Facebook)

“Looks fabulous. Well done to all” – 11.01.2017 (Est of the Nat Facebook)

“Brilliant” – 18.01.2017 (Est of the Nat Facebook)

“One of my favourite bits of Hull” – 17.03.2017 (Est of the Nat Facebook)

1. **Partners**

**To date, how many partners are involved with the project?**

|  |  |  |
| --- | --- | --- |
|  | **ACTUAL TO DATE BASED IN**  **HU1 – HU9** | **ACTUAL TO DATE BASED OUTSIDE**  **HU1 – HU9** |
| **PARTNER TYPE** | | |
| Artistic partner (e.g. theatre, art gallery, music venue) |  | 1 |
| Heritage partner (e.g. museum, archive) |  |  |
| Funder (e.g. Arts Council England, business, private trust) | 1 |  |
| Public Sector partner (e.g. libraries, GPs) |  |  |
| Voluntary sector partner (e.g. community group, charity) |  |  |
| Education (e.g. school, college, university) |  |  |
| Other |  |  |
| **PARTNERSHIP STAGE** | | |
| Number of new partnerships established via this project | 1 |  |
| Number of existing partners involved in this this project | 2 |  |

**This can include formal and informal feedback given to you by staff and/ or your own observations. You can use comments books; informal conversations; emails; etc. to inform this.**

**Thinking about your project to date, what would you say have been the main successes for your partners:**

Hull2017: Good support throughout the project.

Hull City Council: Improving working relationships/partnership working.

Residents: Deeper, more meaningful relationships between us and between themselves.

Audience: A more positive perspective on a poor community.

**Thinking about your project to date, what would you say have been the main challenges for your partners:**

Hull City Council: Getting their heads round and embracing something out of the ordinary

Funder: None

Residents: None

Audience: Changing their perspective about a poor community