## CHRONO
LOGG
GENERAL QUESTIONS
Heralding
Production Specification v3
06.02.17 | GDH
|  |  |  | TITLE | WHAT | FROM TEXT | LOCATION | CONSIDERATIONS
APRIL | Prologue 2 | W/C 3 April |  | Discovery of crates | Social media and press | "cache of over 500 wooden boxes" - the Indiana jones moment | Digital | Can this be done CGI? Images to be grainy | Chris Marr?
| Prologue 3 | W/C 10 April |  | Institute of Rediscovered Wonders | Moving some crates to secret location | Re Rediffusion flat bed at this point? | From ??? To Pumping Station | Actors/costume? Re-rediffusion IP - Aswarm? | The Institue of Rediscovered Wonders - practical arm - instead of Reredifussion
|  | W/C 17 April |  | Secret Location | Digital | web cam with interventions | Pumping Station | Numbers of crates, number of interventions, regularity - Size of Crates - Miniature, Standard, Huge
APRIL | Phase two | The Seven Alleys |  | Community Heralding
|  | 22/04/2017 - 03/05/2017 |  | The Seven Alleys | Public intervention | On the morning of Saturday 22nd April, staff and visitors arriving at Freedom Centre, discover a large has appeared outside. It is marked with the legend, ‘To East Hull with love, from the 7 Alleys’. Over the coming days it emanates sound – harmonic drones, hushed voices speaking urgently, as if from a faraway place, of the Land of Green Ginger and the 7 Alleys, and the ricochet of horses’ hooves galloping. | Preston Road, outside Freedom Centre | Over night install
Standard sized crate - with Specials
Need to record fiddler (horse and carriage opener) - for Nobody Nose crates
[6 empty] | " Street signs and lighting changes" |  | Gels on lampposts
Could we get a KWL truck/cherry picker branded and have their staff involved?
[6 empty] | and signs of 7 appear in the subtlest places |  | ???
MAY | Phase two | Nobody Nose
|  | 2017-05-08 |  |  | Social media and press | Institute reveal the existince of Nose Crates
|  | CHECKING DIARY WITH NORTH POINT | DURATION WED - SUN |  | Public intervention | A stack of crates in pyramid form appears in Northpoint Shopping Centre - for a few days the crates become a fixture, also providing weary shoppers a place to sit. Crates with smells - Ginger. The crates marked for Bransholme, gradually disappear as the Nose Shrine is built. | North Point Shopping Centre Atrium | Install in centre of North Point - stack of boxes - pyramid - 14x crates or 5x crates | FROM JOSHUA - the crates will have the building materials for building the shop - marked for Bransholme
|  | W/C 12 Jun |  |  | Social media and press | The crate with Golden Nose has been discovered and will be delivered to North Poitn Shopping Centre on Sat 17 June
|  | 2017-06-17 |  |  | Public intervention | The Institute then find a final crate that is delivered to the outside of North Point Shopping Centre - this is the crate with th e Gold Nose where theres a procession to the Shrine to open the Shrine.
Standard sized crates - Live - 14 or 5?
MAY - JULY | Phase two | w/c 22 May | Photo shoot - taken W/C 15th May | The Common Guild | Social media and press | Margaret finds ten crates stacked - opening finds tabards… - in a shed |  | 10x Crates - none live
|  | 22/23 JULY |  |  | Finale night | residents create bonfire of crates |  | 20x crates (more?) - burny crates - pyro
JULY - SEPTEMBER | Phase two | ??? |  | Re-Rediffusion
NOT AUGUST |  | ??? |  | Voice extraction | Social media and press | Special equipment has been discovered that the Institute are investigating its prupose.
|  | ??? |  | Voice extraction | Social media and press | The Institute have found out what the equipment does and Re-rediffusion representatives will be collecting voices.
| WTF | WTF | WTF | WTF | WTF | WTF
OCTOBER | Phase two | ??? |  | Little Town | Public intervention | Crate will house a small set up for the little people looking through windows - shutters open to reveal the little world in a crate |  |  | DAVEY-
Crates to have a little world (small version) of the city inside
NOVEMBER | Phase three |  |  | Parade | Media opportunity | Giant Crate - parade opener - with Macnas parade puppet to emerge |  | Moving people into crate out of eye line, pyro
|  |  |  | Parade | Interactions | Giant Crate - LOGG closer - to reveal library and distribute books |  | Can this be the same crate - need to carcase an interior that can be fitted over night after the parade

## Periplum notes
Periplum
Dates | IN | Saturday 29th April
| IN | Sunday 30th April
| BUILD / PM Rehearsals | Monday 1st May
| BUILD / PM Rehearsals | Tuesday 2nd May
| SHOW | Wednesday 3rd May
| SHOW | Thursday 4th May
| SHOW | Friday 5th May
| SHOW | Saturday 6th May
| OUT | Sunday 7th May
| OUT | Monday 8th May
Capacity | 1000 | per night
4 nights
Times |  | DOORS - 20:30?
SHOW - 21:00 - 21:30
CLEAR - 22:00
Duration
Locations

## Sheet1
BUDGET

## REDIFFUSION SPEC
REREDIFFUSION SPEC
4x costume | Overalls branded | Brand TBC
1x Flat bed with tail lift | Branded | Hire
TIMESCALES | All for W/c 10th April

## PROD DESIGN AREAS
PRODUCTION DESIGN
APRIL | Rerediffusion | 1x flatbed - branded - think Ghostbusters Ecto one - lights, siren (can we get away with that?)
4x staff costumes, equipment
2x special crate mover devices
1x KWL picker truck - branded - partnerships?
APRIL | Crates | Phase 1
|  | Fake street signs | 10x Land of Green Ginger or Seven Alleys
|  | Props | 20x 'standard' sized crates | Stackable with 3 people | Able to be secured as a pyramid (stack) and sat on
|  | Live crates | 6x battery PA systems, green smoke, cams for movement- Bells | Rumble packs?
JUNE | Crates | 10x standard crates - stacked | 10x strandard crates stacked | Lone Twin
??? | Crates | Bonfire crates | 20x burny crates | Lone Twin
AUGUST | Crates | Standard crates moved to public locations around Hessle Road | 20x 'standard sized crates'
OCTOBER | Crates | 100x tiny crates | picking up crates from Bingo Hall
NOVEMBER | Crates | Giant Crate | Bursting open to start the parade
Lots of standard crates - used on Parade?
|  | Giant Crate | Bursting open to reveal library

## CRATES SPEC
LOGG CRATES
SIZE
MATERIAL | Wood esk, need to look like old packing crates
Need to be robust enough to be sat on, stood on, stacked, dropped, left out in the public, fire proof?,
FIXINGS | Handles to load by two people at height
Size
Branding | Needs to be able to be replaced (plated or boarD)
http://www.cratingsolutions.co.uk/Services/Products/bespoke-timber-packing-cases-crates.html
Timescales | 3x Special crates delivered by 27 March | For photo shoot in Hull