Slung Low Notes:

Laura Clark (LC), Martin (MA), Lindsey Alvis (LA), Katy Fuller (KF).

* Crediting: Just need to establish what form that will take.
* Audience size will be determined by the site (need to agree what number of tickets to initially go on sale with as this might land before knowing fully the capacity).
* Length of the run – a week to be extended as appropriate. Pricing?
* Schools close Thursday 7 April 2017 and reopen Monday 24 April 2017. Good Friday is 14 April. Easter Sunday 16 April and Easter Monday 17 April. How does this impact the run? NSDF crossover? Turner?
* 2nd October 2017 for performance of final piece.
* Possibly make Slung Low part of a roadshow to show the digital aspect of the story. Set up conversation between Alan & David? Check roadshow dates.
* Running costs of the airstream caravan do come through running costs.
* Full Creative Team will be here in August 2016. Show them sites and confirm after this
* Deadlines for marketing for all seasons, make sure we timeline the lead image and image creativity. Need Slung Low to start thinking about this. Maybe even begin a Pinterest board with the company. Need some kind of image before launch in 22 September to be able to talk about the project. Maybe a title treatment and some copy.
* Performance sites should be confirmed for September 2016. Large warehouses?
* Script due in Oct.
* Licensing: Work on a timeline to get a license in place.
* Katy not here W/C 20 August.
* Confirmed Slung Low will lead on RA & ESAG. They have templates from previous productions. When asked if we have any way that information should be presented, Slung Low were advised they should present information in a format that was comfortable for them. Maybe speak to Chris Clay about ways of presenting information.
* Intellectual Property needs to be discussed in the contract.
* On Sale Date?

Notes and further questions:

* Do we need to make sure they are aware they need to create the seating/watching area for the performance out of their own devolved budget (if either part requires such a setup)?
* Mungo onboard as Producer?

ACTIONS

MA to re-draft deal memo

MA Budget template   
MA Conversation about pricing strategy, deadlines for season 1 & 2 (print, announce etc) with Phil. MA Set up a conversation between David & Alan re digital post meeting

MA Schedule with dates TBC   
Laura Clarke - Check R&D in 16   
LA & MA Set up visit in Aug 16

MA & LA Check the roadshow dates post first wave in meeting with Phil   
MA to speak to Chris Clay about performance sites – large warehouse? – and licensing

MA, CC, RC Check out space near office   
KF ? Put Joanna in contact with Chris Clay/Helen Thackeray? from Events team   
KF IP clause in contract

KF/LA Speak to Slung Low about volunteers, recruitment waves in 16 & 17

KF / LA Speak to SC about the community case and check timeline for community cast   
KF/ LA Speak to Alan about stories from the city and how to approach this   
KF/LA TTR and advice from DreamThinkSpeak

KF Internal conversation about producing model and CDM

LA to read contract and make suggestions & KF to speak to Will

KF BBC conversation and new guidelines

MA to speak to JR & JH about accommodation