File note Look Up, Hull 2017 Meeting – 18 July 2016 re Look Up and Planning

Alex Codd, Garry Taylor – HCC

Sam Hunt, Hazel Colquhoun 2017

1. Zephyr

Approach agreed. Any discussion should be around a timeframe of 28 days

1. The Deep

Short term installations within the landscaping around the building should not need PP, but if they go above 4m in height we may need to discuss with HCC

1. Transmigration

Need to contact Network rail direct (HWW has sent contact)

1. Roadsworth

Will need to talk with Highways – hold off until artist has visited and we can be more sure about sites

1. RIBA

GT asserted not possible for this to be sited in Trinity Square – monthly market, water features and Trinity Church’s own events will not allow this. Suggested King Edward st sq (BHS). Discussed other potential sites – east side Scale Lane Bridge, next to ASK restaurant. No objections but observations that too far from city centre.

This will clearly need consent, but should be part of the process for the architects in any case.

In general, agreed that planning committee members would be briefed and up to speed on items that were intended to be temporarily on site for Hull 2017 only.

Public Realm update

Fountains in Q Vic Sq will still be hoarded off and being worked on during first quarter of 2017, as noted previously. GT noted concerns over pedestrian flow when Zephyr installed.

Trinity Sq now 5 weeks late – finishing probably in Feb 2017.

NB Shadow Gate likely to be installed in Jan 2017 – it will probably be perceived as part of 2017 programme…