|  |  |
| --- | --- |
| **Name of Individual / Organisation** | HULL CHORAL UNION  |
| **Name of Project** | VOICES ACROSS THE HUMBER |

|  |  |  |  |  |
| --- | --- | --- | --- | --- |
| **START DATE** | **END DATE** | **ACTIVITY / TASK** | **STATUS** | **NOTES** |
|  |  |  | COMPLETE / ON-TIME / BEHIND |  |
| 12/11/2015 | 13/05/2016 | Initial discussion with Clare Drury from City Arts with S Brown and L RuggFollow-up/advice offered by Clare Drury |  |  |
| 08/09/201520/04/2016 | 01/03/201713/05/2016 | Planning meetings with reps from all three choirsPlanning/bid preparation with steering group (Suzanne Brown, Susan Hollingworth and Laurence Rugg) |  |  |
| 31/03/2016 | 01/03/2017 | Planning meetings with Sarah Jane Daniels – photographer/digital artist |  |  |
| 05/05/2016 | 05/06/2016 | Planning meeting with City Hall Manager re staging, projection and materials |  |  |
| 06/05/16 | 06/05/16 | Progress meeting with Clare Drury |  |  |
| 06/05/16 | 06/05/16 | Initial meeting with Andrea Lea (Princes Quay young photography group) |  |  |
| 01/09/2016 | 06/01/2017 | Promotion/recruitment of event with local choirs |  |  |
| 01/09/2016 | 01/03/2017 | Collection and editing of digital images and for visual presentation by Sarah Daniels and Jon Robson |  |  |
| 29/09/2017 | 29/09/16 | Project monitoring -steering group  |  |  |
| 22/10/2016 | 22/10/2016 | Children’s Photography Day on the Humber estuary |  |  |
| 04/03/2017 | 04/03/2017 | Choral workshop at Lisle Marsden School, Grimsby for all participantsEvaluation by participants |  |  |
| 05/03/2017 | 05/03/2017 | Choirs to assemble and be filmed on Humber BridgeProject monitoring – steering group |  |  |
| 25/03/2017 | 31/03/2017 | Flash mobs and flyer distribution to advertise eventMedia coverage local radio and press |  |  |
| 31/03/2017 | 31/03/2017 | Technical set up City HallOrchestra rehearsal with David Lawrence |  |  |
| 01/04/2017  | 01/04/2017  | Dress rehearsal 10.00-13.00**Public performance** 16.00-18.30(approximate timings)Evaluation sheets distributed to participants |  |  |
| 02/04/2017 | 31/05/2017 | Evaluation – steering group |  |  |