|  |  |
| --- | --- |
| **Name of Individual / Organisation** | Lansford Penn-Timity/Freetown Mix/Jive Express |
| **Name of Project** | Hull Transforming Lives in Freetown (H-T-LIF) Project |

Please provide a breakdown of key activities /tasks for your project from start to finish. Please include your preparation and planning activity as well as start / end dates of your public activity (eg. public performance, exhibitions, festival).

|  |  |  |  |  |
| --- | --- | --- | --- | --- |
| **START DATE** | **END DATE** | **ACTIVITY / TASK** | **STATUS** | **NOTES** |
|  |  |  | COMPLETE / ON-TIME / BEHIND |  |
| April 2016 | 1st August 2017 | Joint Planning/organizing meeting: Freetown Mix and Jive Express | Completed |  |
| April 2016 | 1st August 2017 | Practice sessions for Music, dance | On time/ongoing |  |
| March 4th 2017 | June 2017 | Freetown Mix Costume design session and production | On time |  |
| March 4th 2017 | April 2017 | Music Video and documentary DVD (demo/sample creation) | On time |  |
| March 4th 2017 | April 2017 | Music recording 6 original tracts on the theme Hull City of Culture | On time |  |
| March 4th 2017 | April 2017 | Music Video clip and Documentary DVD recording | On time |  |
| 5th August 2017 | 5th August 2017 | H-T-LIF Musical concert performance at Craven Park Large function Hall. | On time |  |
|  |  |  |  |  |
|  |  |  |  |  |
|  |  |  |  |  |
|  |  |  |  |  |
|  |  |  |  |  |
|  |  |  |  |  |
|  |  |  |  |  |
|  |  |  |  |  |