## Guidance
HOW TO COMPLETE A PROJECT RISK REGISTER
Every risk (what could happen) has a potential impact (what that might cause) and requires mitigating action (what you're doing to prevent it). The risk owner is the person responsible for the risk and mitigating action.
Risks are scored twice: Firstly the inherent score, before mitigation, to help you see where to focus your energies; Then the residual score, as it currently stands, to help you see where your mitigating actions haven't worked or are insufficient.
Finally, when the risk is no longer a risk to the project, set its status to Closed, so you can filter it out of future reviews.
Hover over a column heading on the risk register for help on what to put in that column.
PROMPTS
Here is a non-exhaustive list of risks you might consider for your project, with prompts for potential impact & mitigating action:
RISK | POTENTIAL IMPACT | MITIGATING ACTION
Artistic content not representative of vision | Reputational damage with creative team, stakeholders and general public | eg well managed creative process, management of expectations
Cost forecasts inaccurate | Project goes over budget or other project costs must be reduced or removed | eg thorough planning, reliable quotes
Decision making causes delays | Additional pressure on internal project team | eg foreseeing required decisions (greenlight, on sale etc) and scheduling them in
Failure to attract audience/participants | Failure to achieve project objectives and Hull 2017 KPIs | eg full MarComms plan
Failure to contract all parties effectively | Inability to deliver project | eg early involvement of Legal team, use of standard templates
Failure to engage creative team | Inability to deliver project
Failure to pay creative team, suppliers etc in timely manner | Relationships sour; third parties unable to deliver due to cashflow issues | eg early setting up of suppliers on system, correct use of POs, management of expectations
Failure to secure appropriate venue | Inability to deliver project | eg early discussions, backup plans
Failure to secure necessary permissions or licences | Inability to delivery project | eg early involvement of Tech & Ops team, appropriate slot at ESAG
Ill-defined scope: full extent of the project not explored and understood | Additional pressure on internal project team; core components of project put at risk | eg thorough planning
Insufficient budget | Inability to deliver project | eg accurate forecasts, management of expectations
Insufficient insurance cover | Significant legal, financial and reputational repercussions for all partners | eg early involvement of Legal team
Lack of project management | Project gets out of control; ineffective working causes unnecessary pressure; no agreement on roles, responsibilities, outcomes etc | eg roles & responsibilities defined, regular use of Artifax inc milestones, regular project team updates and/or meetings
Partners fail to support/deliver as expected | Additional pressure on internal project team | eg clear roles & responsibilities, contracts where required, regular updates
Procurement process causes delays | Additional pressure on internal project team; failure to procure correctly causes legal issues | eg early involvement of Tech & Ops team
Project documentation not managed centrally | Files get out of sync; people work on different versions simultaneously; no 'single source of truth' | eg agreement on shared document space with controlled access
Reduced availability of project team (due to capacity, leave, turnover, illness etc) | Additional pressure on internal project team | eg reliable documentation to allow others to pick up in someone's absence, advance planning for capacity & planned leave
Scope creep: uncontrolled additions to the project | Additional pressure on internal project team; core components of project put at risk | eg clearly defined project scope, clear process for managing change
Staff or partners inexperienced | Work takes longer than necessary; threats or opportunities are missed | eg making more experienced staff available for support, training if required
Suppliers fail to deliver | Inability to deliver project | eg thorough agreements/contracts
Weather or natural environment | Inability to deliver project as intended | eg weatherproofing, indoor alternatives

## Risk register
|  |  |  | Inherent |  |  |  | Residual |  |  |  | Open
Ref | Risk | Potential impact | Risk owner | Likelihood (1-5) | Impact (1-5) | Risk level | Mitigating action | Likelihood (1-5) | Impact (1-5) | Risk level | Status | Closed
1 | Failure to pay creative team, suppliers etc in timely manner | Relationships sour; third parties unable to deliver due to cashflow issues | Jeff | 3 | 5 | 15 | Suppliers made aware of 30-day payment terms and all been set up on system already. POs raised and awaiting approval. Project budget includes detailed projected cashflow and Finance team are aware. | 2 | 3 | 6 | Open
2 | Insufficient insurance cover | Significant legal, financial and reputational repercussions for all partners | Jeff | 3 | 5 | 15 | Not yet determined insurance requirements - on agenda for next project team meeting. | 3 | 5 | 15 | Open
3 | Scope creep: uncontrolled additions to the project | Additional pressure on internal project team; core components of project put at risk | Jeff | 4 | 4 | 16 | Scope of project signed off at SLT at greenlight. Detailed project brief attached to commissioning & production agreement. All aware that no additional budget is available for extra activity. | 2 | 4 | 8 | Open
4 | Slips, Trips, Falls | The event takes place in an outdoor area, the stage may become slippery when wet, possibility of tripping over wires & obstacles, obstructions to access & egress | BP and AT | 4 | 4 | 16 | Monitor weather forecast, stage has all weather coating, grit stage if icy, wet floor signs used if appropriate, all staff first aid & Health and safety trained, flat shoes with grips to be worn, stewards to advise public of slippery surface when guided to seating. All wires tapped to floor with duct tape, members of public to have clear spacing to seats with wide isles made between chairs for easy access and egress, cordened off runway for back stage staff to move between different sides off the stage without obstruction, stewards to ensure that walk ways are kept clear for members of the public, hazard tape placed down on stage on steps and edges of stage to ensure students are clear as to where the edge is. | 3 | 4 | 12 | closed
5 | Fire | Fire during the event | BP & AT | 3 | 5 | 15 | All 5 Senses staff are fire safety trained, the fire brigade will be made aware of the date and location of the event and expected capacity of people, no naked flames will be used in the performance, no smoking will be permitted in the area, props & costumes will be made of low flamable materieals, fire extinguishers will be provided and fire evacuation procedure will be read and signed by all stafff before the event, sockets will not be overloaded, all electrical equipment PAT tested, electrical equipment sheltered from elements, and monitored throughout use. | 2 | 5 | 10 | Closed
6 | Extreme Temperature | Hypothermia or heat stroke | All staff | 3 | 4 | 12 | All 5 Senses staff first aid trained,students have own sun cream, first aid kits on site with foil blankets, students to be monitored to ensure they are kept at safe temp, building on site for people to shelter from extreme weather, all performers to dress appropriately for weather, hot & cold drinks provided for performers and audience, costumes can be altered depending on temp. |  |  | 0
7 | Strong wind | Winds dislodging items that could injure people | All staff | 3 | 3 | 9 | Weather forecast monitored before event, gazeebos weighed down with sandbags, if wind moves marques dismantel them, do not erect marquees if wind too strong, performance not to go ahead if wind too strong. | 2 | 3 | 6 | Closed
8 | Challenging behaviour of students | Students may become anxious with change of environment and routine, and large numbers of members of public. Could have overload of sensory stimulation. All above could lead to students harming themselves or others. | All staff | 4 | 4 | 16 | All 5 Senses staff MAPA trained, certified MAPA instructer on site, first aid boxes on site, students provided with sufficient levels of support as per individual assessments, floating staff available to give extra support, time out areas provided for students, comforters and or medication on site for students, any students who become distressed during the performance are to be removed asap from the show and taken to time out area. If students do not wish to be part of the performance alternative arrangements can be made for them so they dont feel pressured. | 3 | 3 | 9 | Closed
9 | Challenging behaviour of audience members | Members of the public may show challenging behaviour by heckling, shouting or running on to the stage mid performance | Management team | 2 | 2 | 4 | All staff are MAPA trained, Management team to difuse the situation, ask individuals to leave the premises, escort off the premises if needed. Contact the police if necessary. staff to escort students to a safe place and reassure them. | 2 | 1 | 2 | Closed
10 | Manual Handling of props and staging | Staff could cause injury to themselves or others by using incorrect manual handling techniques | All staff | 4 | 4 | 16 | All staff are manual handling trained, only 5 Senses staff will move/transport props & staging, staff to use buddy system to move heavy loads, staff not to bend backs whilst lifting but bend at knees as taught in training, large items of staging not to be moved until members of the public are no longer present, contractors will be responsible for the moving and handling of their own equipment. | 2 | 4 | 8 | Closed
11 | Manual Handling of students | Staff could injure themselves or the students they are supporting | All staff | 4 | 4 | 16 | All staff are manual handling trained, all staff are aware of student support plans and individual student risk assessments, students who are unable to weightbear will remain in their wheelchairs at all times, when pushing wheelchairs staff to adopt the correct positioning, hoists available in changing area, access to the staged area limited to students higher levels of mobility, staff to assist these students on and off the staged areas. Steps and edges of stages clearly maked for students to make access and egress easier. | 2 | 4 | 8 | Closed
12 | Handling, storage & Administration of Medication | Student medication could get lost, stolen, wrongly administered or could be missed. | All staff | 4 | 5 | 20 | All staff are medication, first aid, eplilepsy and buccal trained, all staff are aware of the medications required by their students, medications on site will be the responsibility of the support worker, medications will be clearly named and dated with strengths dosage and administration times on. Rescue meds will be accompanied with management plans, emergancy contact information will be carried by the designated first aider, all medication that is administered will be double checked by a senior coordinator, if a medication error occurs a senior member of staff must be contacted immediately and medical assistance sought. If a student has a prolonged seizure, follow the steps laid out in the epilepsy management plan provided. If in doubt call for a senior member of staff then call for medical assistance. | 2 | 5 | 10 | Closed
13 | Noise Level | Sound from live music could cause hearing damage | The Gig Shop | 3 | 3 | 9 | Qualified sound technician at the event to oversee sound output from any pre-recorded or live sound. The sound technician will ensure that the sound does not exceed 90 decibels, sound checks will be carried out prior to the performance, speakers will be placed at a reasonable distance away from the performers and audience. | 1 | 3 | 3 | Closed
14 | Protestor Management | Protestors could see the opportunity to invade the stage during the event, causing distress, damage, and injury to performers or members of the audience | Management team | 1 | 3 | 3 | If an individual decideds to protest at the event, they are allowed to do so under the Human Rights Act 1998. The event stweards are allowd to approach the individual and stand near to them to ensure they are not a threat to the students, once they have finished their speech they can be peacefully escorted off the premises by the management team and the MAPA instructor, if at any point it is deemed that the individual could be hostile or a threat to others safety, the support workers should guide the students away from the protestor to a safe place. The management team should also encourage the public to do the same thing. If necessary the police should be called. |  |  | 0
15 | Safeguarding of vulnerable adults | Students may be placed in vulnerable situations due to inadequate support on the day of the performance or by being in contact with large numbers of the public | BP & AT All staff | 4 | 5 | 20 | Students have the correct levels of support provided according to their assessed level of need. All staff are SOVA trained, staff have read students behaviour and support plans, students will be reminded of the importance of not wandering off on their own or with strangers prior to or during the event, stewards will be monitoring Zebedee's Yards exits throughout the show, missing person station on site, students told where this is and who to speak to if become lost, lost person report form available, designated welfare officer on day of performance. Contact parents or police if necessary. Designated first aider reponsible for the students emergency contact folder on day of performance. | 2 | 5 | 10 | Closed
16 | Scalds and Burns | Potential scalds and burns from the sale of hot drinks at the event and the use of the hot water urn in the green room | All staff | 5 | 4 | 20 | All staff are first aid and health and safety trained, only members of staff are to operate the hot water urns, the urns are to be kept on a stable surface, thermostat on the urns to be kept below boiling point, cold water will be available to cool down students drinks, urn will be fully emptied before transportation, if anyone spills or touches the urn they should be treated immediately by putting the affected area in cool water, for at least 10 minutes, if there is any sign of blistering further medical attention will be saught by the event manager or designated first aider. Any issues or concerns should be brought to the health and safety officer, event manager or designated first aider. | 2 | 6 | 12 | Closed
17 | Smoke Machine | Smokemachine filling the area causing disorientation, smoke machine causing breathing difficulties | Health & Safety Officer | 3 | 3 | 9 | New smoke machine does not require PAT testing, has been tried and tested in external environment, will be visually inspected before use, will be operated by H&S officer on day of performance, being used in open air environment so smoke should disperse immediately, machine being used on raise surface so smoke should plume above performers and spectators, will be used at a distance from audience, will be operated in accordance to manufacturers instructions, students & staff known to suffer with breathing conditions to not be in direct line of smoke at any time. | 1 | 3 | 3 | Closed
18 | Use of electrical equipment in open air environment | electric shock | All staff | 3 | 5 | 15 | All equipment over 1 year old to be PAT tested, all contractors to provide proof to H&S officer that all electrical equipment is PAT tested before performance, if there are any electrical faults or Zebedee's Yards RCDs trip out then the management team must contact the yards employees to send an electrician to place the power back on and find the source of the loss of power, 5 Senses do not have access to the main breaker, staff and contractors to ensure they do not overload the maximum 32A on each 32A adaptor or 16AMP on the 16A adaptor this will cause the mains to trip out. All electrical equipment will be connected to an RCD mains adapter. All electrical equipment to be visually checked to be in good working order before use, do not over load sockets, fully unravel all extension leads before use, cables taped down to reduce trip hazrds, plugs and sockets protects from the elements. | 2 | 4 | 8 | Closed
19 | [5 empty] | 0 |  |  |  | 0
20 | [5 empty] | 0 |  |  |  | 0
21 | [5 empty] | 0 |  |  |  | 0
22 | [5 empty] | 0 |  |  |  | 0
23 | [5 empty] | 0 |  |  |  | 0
24 | [5 empty] | 0 |  |  |  | 0
25 | [5 empty] | 0 |  |  |  | 0
26 | [5 empty] | 0 |  |  |  | 0
27 | [5 empty] | 0 |  |  |  | 0
28 | [5 empty] | 0 |  |  |  | 0
29 | [5 empty] | 0 |  |  |  | 0
30 | [5 empty] | 0 |  |  |  | 0
31 | [5 empty] | 0 |  |  |  | 0
32 | [5 empty] | 0 |  |  |  | 0
33 | [5 empty] | 0 |  |  |  | 0
34 | [5 empty] | 0 |  |  |  | 0
35 | [5 empty] | 0 |  |  |  | 0
36 | [5 empty] | 0 |  |  |  | 0
37 | [5 empty] | 0 |  |  |  | 0
38 | [5 empty] | 0 |  |  |  | 0
39 | [5 empty] | 0 |  |  |  | 0
40 | [5 empty] | 0 |  |  |  | 0
41 | [5 empty] | 0 |  |  |  | 0
42 | [5 empty] | 0 |  |  |  | 0
43 | [5 empty] | 0 |  |  |  | 0
44 | [5 empty] | 0 |  |  |  | 0
45 | [5 empty] | 0 |  |  |  | 0
46 | [5 empty] | 0 |  |  |  | 0
47 | [5 empty] | 0 |  |  |  | 0
48 | [5 empty] | 0 |  |  |  | 0
49 | [5 empty] | 0 |  |  |  | 0
50 | [5 empty] | 0 |  |  |  | 0
Note on B2: Crawford James: What might happen?
Note on C2: Crawford James: What would be the result of that happening?
Note on D2: Crawford James: Who is responsible for managing this risk?
Note on E2: Crawford, James: 1 - Rare, 2 - Unlikely, 3 - Possible, 4 - Likely, 5 - Almost certain
Note on F2: Crawford, James: 1 - Negligible, 2 - Minor, 3 - Moderate, 4 - Major, 5 - Catastrophe
Note on H2: Crawford James: What has happened, and what else is planned, to reduce either likelihood or impact of the risk happening, or both - only drop Residual Risk when these actions have taken effect.
Note on I2: Crawford, James: 1 - Rare, 2 - Unlikely, 3 - Possible, 4 - Likely, 5 - Almost certain
Note on J2: Crawford, James: 1 - Negligible, 2 - Minor, 3 - Moderate, 4 - Major, 5 - Catastrophe
Note on L2: Crawford James: Set to 'Closed' when it is no longer a risk to the project, eg all permissions are secured, all parties are contracted...