## CHRONO
LOGG
Heralding |  | GENERAL QUESTIONS
Production Specification v5
08.02.17 | GDH
|  |  |  | TITLE | WHAT | FROM TEXT/REFERENCE FROM CDS | LOCATION | CONSIDERATIONS
FEB | Pre-production | 2017-02-13 | HERALDING | Pre-production | Design brief sent out | NA
|  | 2017-02-20 | HERALDING | Pre-production | Design brief responses received | NA
|  | W/C 27 Feb | HERALDING | Pre-production | Identify freelancers for the Institute dudes | NA
MARCH | Pre-production | 2017-03-13 | HERALDING | Pre-production | Institute of Rediscovered Wonders brand delivered and costume items | NA
|  | 14 - 31 March | HERALDING | Pre-production | Branding of flatbed, costumes and accessories | NA
|  | 27 Marc h | HERALDING | Pre-Production | 5x normal crates delivered to Hull | NA | Staples
|  | 2017-03-28 | HERALDING | Pre-Production | Crates moved to 'tunnel' location - photo shoot - and to Staples | NA | ???
APRIL | Prologue 2 | 2017-04-03 | HERALDING | Discovery of crates | Social media and press | "cache of over 500 wooden boxes" - the Indiana jones moment | Digital | Can this be done CGI? Images to be grainy | Chris Marr?
| Prologue 3 | 2017-04-12 | HERALDING | Institute of Rediscovered Wonders | Moving some crates to secret location | IfRW flat bed at this point? | From ??? To Pumping Station |  | The Institute of Rediscovered Wonders - practical arm - instead of Reredifussion
|  | W/C 17 April | HERALDING | Secret Location | Digital | web cam with interventions | Pumping Station | Numbers of crates, number of interventions, regularity - Size of Crates - Miniature, Standard, Huge
APRIL | Phase two | 15/04/2017 - 16/04/2017 | HERALDING | The Seven Alleys | Public intervention | Delivery of 1000's of scrolls to Preston Road area - invitation to come to the carriage at Freedom Centre on 20/4 - 4pm - 8pm 21/4 - 4pm - 8pm 22/04 10 - 4pm 23/04 10 - 4pm | Freedom Centre
| Phase two | 20/04/2017 - 03/05/2017 | The Seven Alleys | The Seven Alleys | Public intervention | On the morning of Saturday 22nd April, staff and visitors arriving at Freedom Centre, discover a large has appeared outside. It is marked with the legend, ‘To East Hull with love, from the 7 Alleys’. Over the coming days it emanates sound – harmonic drones, hushed voices speaking urgently, as if from a faraway place, of the Land of Green Ginger and the 7 Alleys, and the ricochet of horses’ hooves galloping. | Preston Road, outside Freedom Centre | Overnight install
|  | 20/04/2017 - 23/04/2017 | The Seven Alleys | The Seven Alleys | Public intervention - Box office | A Green Ginger Carriage is positioned at Freedom Centre as box office - actors etc etc |  | Standard sized crate - with Specials
MAY | Phase two | Nobody Nose
|  | 2017-05-08 | HERALDING | Nobody Nose | Social media and press | Institute reveal the existence of Nose Crates
|  | CHECKING DIARY WITH NORTH POINT - end w/C 15 May | DURATION WED - SUN | Nobody Nose | Public intervention | A stack of crates in pyramid form appears in Northpoint Shopping Centre - for a few days the crates become a fixture, also providing weary shoppers a place to sit. Crates with smells - Ginger. The crates marked for Bransholme, gradually disappear as the Nose Shrine is built. | North Point Shopping Centre Atrium | Install in centre of North Point - stack of boxes - pyramid - 14x crates or 5x crates | FROM JOSHUA - the crates will have the building materials for building the shop - marked for Bransholme
|  | W/C 12 Jun | HERALDING | Nobody Nose | Social media and press | The crate with Golden Nose has been discovered and will be delivered to North Point Shopping Centre on Sat 17 June
|  | 2017-06-19 | HERALDING | Nobody Nose | Public intervention | The Institute then find a final crate that is delivered to the outside of North Point Shopping Centre - this is the crate with the e Gold Nose where there's a procession to the Shrine to open the Shrine.
Standard sized crates - Live - 14 or 5?
MAY - JULY | Phase two | w/c 22 May | Photo shoot - taken 18th May | The Common Guild | Social media and press | Margaret finds a crate opening finds tabards… - in a shed |  | 1x crate
|  | 22/23 JULY |  | The Common Guild | Finale night | residents create bonfire of crates |  | 20x crates (more?) - burn crates - pyro
JULY - SEPTEMBER | Phase two
JULY |  | ??? | HERALDING | Re-Rediffusion | Social media and press | Crate found at the old rediffusion site - discovered - with sucker in
|  |  | HERALDING | Re-Rediffusion | Social media and press | The institute open a crate which have the attachments for the sucker
JULY - AUGUST |  | ??? | HERALDING | Re-Rediffusion | Digital | Rerediffusion website collect voices
SEPTEMBER |  | ??? | HERALDING | Re-Rediffusion | Public intervention | Rerediffusion staff go out (where?) to collect voices in the community
| 7 - 10 days | ??? | HERALDING | Re-Rediffusion | Public intervention | Pickering park - voice swarm
OCTOBER | Phase two | 2017-09-25 | HERALDING | Little Town | Public intervention | Crate will house a small set up for the little people looking through windows - shutters open to reveal the little world in a crate |  |  | DAVEY-
Crates to have a little world (small version) of the city inside
Like an evacuation crate - "For Anlaby Road" - positioned next to the bingo hall
NOVEMBER | Phase three | w/c 6 Nov - 11/12 Nov | HERALDING | Macnas | Media opportunity | Giant Crate - parade opener - with Macnas parade puppet to emerge - from the Small People from Little town - a facimilie of the Little People crate but BIG - in the lead up to the Parade you can see the little people getting BIG | To the start of the parade route | Outside the crate has the route map and parade information

## Flatbed schedule
FLAT BED AND INSTITUTE REQUIREMENTS
|  | TIMES | HOURS | Institution of Rediscovered Wonders - delivery arm
2017-03-14 | Flat bed delivered to Staples (or location for skin branding) | AM | N/A | N/A
2017-03-28 | Move 5x LoGG Crates to secret location - photo shoot - then return to Staples | 10:00 - 15:00 | 5 | 2
2017-04-20 | Move live crates from Staples to Freedom Centre x5 | 03:00 - 07:00 | 4 | 2
2017-05-03 | Move live crates from Freedom Centre to Staples x5 | 03:00 - 07:00 | 4 | 2
TBC - MAY | Move 12 amount of crates to North Point Shopping Centre | 00:00 - 07:00 | 7 | 4
TBC - MAY - 4 times | Remove 3 amount of crates from North Point Shopping Centre - gradually deminshing | 05:00 - 07:00 | 2 | 2
15 May??? | 1x crates moved to xxx alotment for photo shoot and removed same day | 06:00 - 08:00 | 2 | 2
2017-06-17 | Move one (Golden Nose crate) to green nr North Point Shopping Centre Car park - the Wilko one | 06:00 - 08:00 | 2 | 2
22/23 July | ???? Burny crates

## ACTIONS FROM FEB CDS
ACTIONS FROM CDS - FEB
LEAD
Who's arranging the secret tunnel location for the first photo shoot? | EB
Location for the 12 April HDM reporter to 'witness' the crates being moved? | Alix
Follow up with Yorkshire Water - sorry forgot the guys name - use for crate store | EB
Do we want crates at the Periplum site? | LY
Can we check with Tony about using the shop unit and Freedom Centre Plaza from 22 April to 3 May? | GH/LY
Can we check diary for North Point atrium - May | LY
Check size and load in access for North Point | GH
Location for Margaret's and 10 crates photo shoot | CM
Frame the bonfire conversation - Lone Twin | KF

## IfRW Spec
IfRW Specification
4x costume | Overalls branded | Brand TBC
1x Flat bed with tail lift | Branded | Hire/Partnership MKM
4x hard hats | Branded
4x pairs of gloves | Safety gloves
TIMESCALES | See Crono Schedule and Flatbed Schedule

## PROD DESIGN AREAS
PRODUCTION DESIGN
APRIL | Rerediffusion | 1x flatbed - branded - think Ghostbusters Ecto one - lights, siren (can we get away with that?)
4x staff costumes, equipment
2x special crate mover devices
1x KWL picker truck - branded - partnerships?
APRIL | Crates | Phase 1
|  | Fake street signs | 10x Land of Green Ginger or Seven Alleys
|  | Props | 20x 'standard' sized crates | Stackable with 3 people | Able to be secured as a pyramid (stack) and sat on
|  | Live crates | 6x battery PA systems, green smoke, cams for movement- Bells | Rumble packs?
JUNE | Crates | 10x standard crates - stacked | 10x strandard crates stacked | Lone Twin
??? | Crates | Bonfire crates | 20x burny crates | Lone Twin
AUGUST | Crates | Standard crates moved to public locations around Hessle Road | 20x 'standard sized crates'
OCTOBER | Crates | 100x tiny crates | picking up crates from Bingo Hall
NOVEMBER | Crates | Giant Crate | Bursting open to start the parade
Lots of standard crates - used on Parade?
|  | Giant Crate | Bursting open to reveal library

## CRATES SPEC
LOGG CRATES
SIZE
MATERIAL | Wood esk, need to look like old packing crates
Need to be robust enough to be sat on, stood on, stacked, dropped, left out in the public, fire proof?,
FIXINGS | Handles to load by two people at height
Size
Branding | Needs to be able to be replaced (plated or boarD)
http://www.cratingsolutions.co.uk/Services/Products/bespoke-timber-packing-cases-crates.html
Timescales | 3x Special crates delivered by 27 March | For photo shoot in Hull

## Periplum notes
Periplum
Dates | IN | Saturday 29th April
| IN | Sunday 30th April
| BUILD / PM Rehearsals | Monday 1st May
| BUILD / PM Rehearsals | Tuesday 2nd May
| SHOW | Wednesday 3rd May
| SHOW | Thursday 4th May
| SHOW | Friday 5th May
| SHOW | Saturday 6th May
| OUT | Sunday 7th May
| OUT | Monday 8th May
Capacity | 1000 | per night
4 nights
Times |  | DOORS - 20:30?
SHOW - 21:00 - 22:00
CLEAR - 22:30
Duration |  | 1hr
Locations |  | Gardens to the front of the Pavillion, behind the Pavillion, the road way leading to the Pavillion, the Arena to the left of the roadway