## R1BW topline budget
| Project | Radio One Big Weekend - C100 |  |  |  |  | o/s | partial spend | Spent/PO raised
| Version | LIVE
[7 empty] | Costs match to budget |  | Partial match to budget
| Item | Unit Cost | Quantity | Cost | Notes | Supplier & notes | Close match to budget |  | Cost to find,PO to raise or budget to clear
1. Venue Costs |  |  |  |  | 185622.78 |  | Actual / PO | PO to raise?
K162 / ZK108 | Licence application fee | 8190 | 1 | 8190 | premises licence | ERYC | 8190 | 0 | ZK108/K162 [1]
K136 / ZK107 | Alternative grazing, fencing etc. | 40108.1 | 1 | 40108.1 | as per Cundalls report | Burton Constable | 25000 | 15108.1 | ZK107/K136 [2] & [61]
K136 / ZK107 | Cundalls Fees | 2567.5 | 1 | 2567.5 | Cundalls |  |  | 2567.5 | ZK107/K136 [63]
K136 / ZK107 | JAS Martin fees | 600 | 1 | 600 | JAS Martin |  |  | 600 | ZK107/K136 [64]
K136 / ZK107 | Additional costs (Xan's field) | 0 | 1 | 0 | production holing area (in Cundalls costs) | Xan Foxton | 0 | 0
K136 / ZK107 | Grass cutting | 4040 | 1 | 4040 | 100 acre | Will Wastling | 4041 | -1 | ZK107/K136 [4] (various)
K257 / ZK107 | Ground works | 84079 | 1 | 84079 | see separate tab | Roche | 84079 | 0 |  |  |  | Sept cost rec'd £12,400
K136 / ZK107 | Loss of income | 7500 | 1 | 7500 | Café | Burton Constable - under negotiation |  | 7500 | ZK107/K136 [62]
K136 / ZK107 | Loss of income etc | 26101.18 | 1 | 26101.18 | House | Burton Constable - under negotiation |  | 26101.18 | ZK107/K136 [61]
K162 / ZK108 | BC Legal fees | 7687 | 1 | 7687 | Updated quote |  | 7687 | 0 | ZK108/K162 [36]
K162 / ZK108 | Natural England fees | 4750 | 1 | 4750 | for advice | Ntural England | 4750 | 0 | ZK107/K136 [3]
2. Traffic & Bus Operations - see tab for codes if not below |  |  |  |  | 570690.89
see tab | Project & traffic management | 119701.13 | 1 | 119701.13 |  | Various - see PM-TM tab | 115706 | 3995.13 | One remaining to check - CC
K161 / ZK103 | Burton Constable | 94859 | 1 | 94859 |  | Various see EXP. BC tab | 94859 | 0
K223 / ZK103 | Walton Street | 13544.7 | 1 | 13544.7 |  | Various see EXP. Walton St tab | 13045 | 499.7 | May not be charged? CC
K223 / ZK103 | Leconfield | 20847.06 | 1 | 20847.06 |  | Various, see EXP. Leconfield tab | 20847 | 0.06
K223 / ZK103 | Interchange | 4820 | 1 | 4820 |  | Gary Beestone | 4820 | 0
K223 / ZK103 | Grove Hill | 6871.81 | 1 | 6871.81 |  | Gary Beestone | 6872 | -0.19
K253 / ZK103 | Across all sites | 2368 | 1 | 2368 |  | Gary Beestone | 2368 | 0
see tab | Buses | 307679.19 | 1 | 307679.19 |  | Various, see EXP. Buses tab | 307679 | 0.19
3. Emergency Services & Medical |  |  |  |  | 33268
K261 / ZK107 | Police | 0 | 1 | 0 | Value in Kind
K261 / ZK107 | Fire | 0 | 4 | 0 | Attendance at Silver and Bronze x 2 days | Humberside Fire & Rescue (may not have to pay this)
K261 / ZK107 | Ambulance | 2070 | 1 | 2070 | Attendance at Silver - 2 days | Yorkshire Ambulance Service | 2070 | 0 | ZK107/K261 [16]
K259 / ZK107 | Medical & first aid provision | 19348 | 1 | 19348 | St John Ambulance | St John Ambulance | 19348 | 0 | ZK107/K259 [13]
K246 / ZK107 | Welfare provision | 4947 | 1 | 4947 |  | Prestige | 4947 | 0 | ZK207/K246 [14]
K247 / ZK107 | Marquees | 4507 | 1 | 4507 | BBC12 | Radio 1 | 4507 | 0 | Radio 1 | ZK107 K247
K247 / ZK107 | Furniture | 103 | 1 | 103 | BBC10 | Radio 1 | 103 | 0 | Radio 1 | ZK107 K247
K247 / ZK107 | Heating | 1580 | 1 | 1580 | BBC11 | Radio 1 | 1580 | 0 | Radio 1 | ZK107 K247
K247 / ZK107 | Welfare tent | 713 | 1 | 713 | BBC12 | Radio 1 | 713 | 0 | Radio 1 | ZK107 K247
4. Signage |  |  |  |  | 0
K271 / ZK109 | Signage outside event locations | 0 | 1 | 0 | allowance
0
5. Waste Management |  |  |  |  | 79309.03
K145 / ZK107 | Ryans | 69496.03 | 1 | 69496.03 | Ryans | Ryans | 69496 | 0.03 | ZK107/K145 [15]
K145 / ZK107 | cabins | 1650 | 1 | 1650 | BBC9 | Radio 1 | 1650 | 0 | Radio 1 | ZK107 K145
K145 / ZK107 | Buggies | 663 | 1 | 663 | BBC14 | Radio 1 | 663 | 0 | Radio 1 | ZK107 K145
K145 / ZK107 | water, power etc. | 7500 | 1 | 7500 | BBC13 | Radio 1 | 7500 | 0 | Radio 1 | ZK107 K145
6. Security & stewarding |  |  |  |  | 26992.5
K261 / ZK107 | Outiside the fence | 26992.5 | 1 | 26992.5 | CN Security | CN Security | 26992 | 0.5 | ZK107 K261 [33]
0
0
7. Health & Safety Management |  |  |  |  | 4963.1
K244 / ZK106 | H&S consultant per day | 4963.1 | 1 | 4963.1 |  | Gallowglass | 4963 | 0.1 | ZK106/K244 [17]
| Noise management plan | 0 | 1 | 0
8. Other costs |  |  |  |  | 154573
K245 / ZK106 | Lost property | 50 | 1 | 50 | allowance |  |  | 50 | CC to check with Mel
K278 / ZK110 | Resident engagement | 4523 | 1 | 4523 | actuals | Various (BKR, Humyne, Kall Kwik) | 4523 | 0 | ZK110/K278 [20] |  | NB £55 PO to be invoiced
K247 / ZK106 | Contribution to BBC costs | 150000 | 1 | 150000 |  | Radio 1 | 150000 | 0 | ZK106 K247 [51]
0
9. Marketing & Communications |  |  |  |  | 6388
K270 / ZK109 | Branding | 6388 | 1 | 6388 | onsite, stations etc. | Various - see Lisa Mayes | 6388 | 0 | ZK109/K270 [21] & ZK108 K162 [22]
0
10. Contingency |  |  |  |  | 10908.52
K283 / ZK111 | contingency | 10908.52 | 1 | 10908.52 |  | Various - see Contingency tab | 7083.31 | 3825.21 | CC to check
11. Security Related Additions |  |  |  |  | 31025.85
K266 / ZK108 | Additional infrastructure, staff etc. | 31025.85 | 1 | 31025.85 |  | Various - see Security Additions tab | 31026 | -0.15
12. Miscellaenous/Admin |  |  |  |  | -39646.81
K299 / ZK114 | Misc / Admin / Travel etc | -39646.81 | 1 | -39646.81 |  | Various - see Misc-Admin tab | 2146 | -41792.81 | CC to check
|  | Expenditure subtotal |  |  | 1064094.86
11. Income |  |  |  |  | 951055.37
| Hull City Council | 250000 | 1 | 250000
| ERYC | 125000 | 1 | 125000
| Ticketmaster actuals | 568464.04
| On the day actuals | 7591.33 |  | 576055.37 | (total actuals) | 576055 | Actuals
|  |  | Profit / Loss |  | -113039.49
notes:
i | E & OE
ii | all costs exclude VAT
iii | all costs in GBP sterling
iv | costs relate to current propsals and concepts
v | Insurance excluded
488039.49

## Groundworks
| Project | Radio One Big Weekend - C100
| Version | 17
| Item | Unit Cost | Quantity | Cost | Notes
Onsite Ground works |  |  |  |  | 84079
K162 / ZK108 | Bus entrance ramps | 29000 | 1 | 29000 | MB Roche & Sons
K136 / ZK107 | Tarmac access road | 4500 | 1 | 4500 | MB Roche & Sons
K136 / ZK107 | Remove and replace fencing | 2800 | 1 | 2800 | MB Roche & Sons
K136 / ZK107 | North access road works | 3100 | 1 | 3100 | MB Roche & Sons
K265 / ZK107 | South access road works | 11700 | 1 | 11700 | MB Roche & Sons
K136 / ZK107 | contingency | 0 | 1 | 0 | MB Roche & Sons
K136 / ZK107 | Additional ramp | 10200 | 1 | 10200 | MB Roche & Sons
K136 / ZK107 | tree surgery Jacky Lane | 300 | 1 | 300 | MB Roche & Sons
K136 / ZK107 | extra fence removal | 875 | 1 | 875 | MB Roche & Sons
K136 / ZK107 | Car park resurfacing | 3250 | 1 | 3250 | MB Roche & Sons
K136 / ZK107 | Concrete slope | 2100 | 1 | 2100 | MB Roche & Sons
K136 / ZK107 | manhole cover | 450 | 1 | 450 | MB Roche & Sons | Total Budget | Actual | To raise
K136 / ZK107 | Prod B road repairs | 6600 | 1 | 6600 | MB Roche & Sons | 74875 | 74875 | 0 | ZK800/K257 [6] & [53] | NB additional £12,400 came through in September
|  | 9204 | 1 | 9204 | Wastling extras | 9204 | 9204 | 0 | ZK107/K136 (4)

## Summary
Radio 1 Big Weekend Bus Operation Income / Expenditure Summary
Income
Actual sales | 576178
Forecast sales
Expenditure
Project & Traffic Management |  | 119701.13
Burton Constable |  | 94859
Walton Street |  | 13544.7
Hedon |  | 20847.06
Interchange |  | 4820
Grove Hill |  | 6871.81
Across all sites |  | 2368
Buses |  | 307679.19
Income Total | 576178
Expenditure Total |  | 570690.89
Profit / Loss | 5487.11

## Income
Radio 1 Big Weekend Bus Operation Income
ACTUALS - | 20/05/2017
Item | Gross | postage £ | £ after postage | Commission % on gross | Commission £ | £ after commission | VAT? | Net £ | Total Capacity | Sat Sales | Sun Sales | Sat Income | Sun Income | Combined Income
Ticket Income
Hull Paragon Interchange
Bus tickets | 13 | 0.75 | 12.25 | 6% | 0.78 | 11.47 | N | 11.47 | 12000 | 12063 | 12069 | 138362.61 | 138431.43 | 276794.04
Leconfield P&R
Bus tickets | 13 | 0.75 | 12.25 | 6% | 0.78 | 11.47 | N | 11.47 | 4500 | 2743 | 2893 | 31462.21 | 33182.71 | 64644.92
Car parking tickets | 7.5 | 0 | 7.5 | 6% | 0.45 | 7.05 | y | 5.8 | 1900 | 1122 | 1190 | 6507.6 | 6902 | 13409.6
Grove Hill
Bus tickets | 13 | 0.75 | 12.25 | 6% | 0.78 | 11.47 | N | 11.47 | 3000 | 3169 | 3224 | 36348.43 | 36979.28 | 73327.71
Walton St
Bus tickets | 13 | 0.75 | 12.25 | 6% | 0.78 | 11.47 | N | 11.47 | 5500 | 5446 | 5500 | 62465.62 | 63085 | 125550.62
Car parking tickets | 7.5 | 0 | 7.5 | 6% | 0.45 | 7.05 | y | 5.8 | 1100 | 804 | 734 | 4663.2 | 4257.2 | 8920.4
Onsite guest parking
Car parking tickets | 30 | 1.5 | 28.5 | 6% | 1.8 | 26.7 | y | 21.95 | 900 | 124 | 141 | 2721.8 | 3094.95 | 5816.75
[13 empty] | on the day sales | 7714
[13 empty] | refunds | 0
[9 empty] | Bus total | 23421 | 23686 | Total income to date |  | 576178.04
[9 empty] | Parking total | 1926 | 1924
Future Forecast at |  | Bus : | 87% | Parking: | 59.5% |  | Guest parking |  | 10%
Item | Gross | postage £ | £ after postage | Commission % on gross | Commission £ | £ after commission | VAT? | Net £ | Total Capacity | Total (100% sales) | Forecast Income per day | Total Forecast Income
Ticket Income
Hull Paragon Interchange
Bus tickets | 13 | 0.75 | 12.25 | 6% | 0.78 | 11.47 | N | 11.47 | 12000 | 137640 | 119746.8 | 239493.6
Hedon P&R
Bus tickets | 13 | 0.75 | 12.25 | 6% | 0.78 | 11.47 | N | 11.47 | 4500 | 51615 | 44905.05 | 89810.1
Car parking tickets | 7.5 | 0 | 7.5 | 6% | 0.45 | 7.05 | y | 5.8 | 1900 | 11020 | 6556.9 | 13113.8
Grove Hill
Bus tickets | 13 | 0.75 | 12.25 | 6% | 0.78 | 11.47 | N | 11.47 | 3000 | 34410 | 29936.7 | 59873.4
Walton St
Bus tickets | 13 | 0.75 | 12.25 | 6% | 0.78 | 11.47 | N | 11.47 | 5500 | 63085 | 54883.95 | 109767.9
Car parking tickets | 7.5 | 0 | 7.5 | 6% | 0.45 | 7.05 | y | 5.8 | 1100 | 6380 | 3796.1 | 7592.2
Onsite guest parking
Car parking tickets | 30 | 1.5 | 28.5 | 6% | 1.8 | 26.7 | y | 21.95 | 900 | 19755 | 1975.5 | 3951
[10 empty] | Total Forecast Income |  | 523602
[10 empty] | Forecast Income minus actuals |  | -52576.04

## Security additions
Radio 1 Big Weekend Additional Security related expenditure
Item | Rate | Quantity | Days | Total | Security |  | Budget | Actual
Skiralugh buses | 5300 | 1 | 1 | 5300 | EYMS |  | 5300 | 5300 | 0 | ZK800/K115 [19]
Ped barrier | 503 | 1 | 1 | 503 | All Occasions | Sproatley bus stop - paid | 503 | 503 | 0 | ZK111/K283 [23]
Barrier & fencing | 5273.85 | 1 | 1 | 5273.85 | Gary Beestone - GB38 | AO | 5273.85 | 5274 | -0.15 | GB
Security personnel | 19049 | 1 | 1 | 19049 | CN Security |  | 19049 | 19049 | 0 | ZK108 K266 [22]
Additional site manager | 900 | 1 | 1 | 900 | GB - 46 |  | 900 | 900 | 0 | GB ZK108 K266 [35]
0
0
0
|  |  | Total: | 31025.85 |  |  | 31025.85 | 31026 | -0.15

## Contingency
Radio 1 Big Weekend Contingency
Item | Rate | Quantity | Days | Total | Suppliers |  | Budget | Actual
Box office staff | 635 | 1 | 1 | 635 | Hull 2017 freelancers |  | 635 | 635 | 0 | ZK111/K283 [26]
Radios and mast | 1759.41 | 1 | 1 | 1759.41 | Nine Hundred Communications |  | 1759.41 | 1759 | 0.41 | ZK111/K283 [27] ZK111 K238 [27] ZK111 K283 [27]
Traffic arm | 255 | 1 | 1 | 255 | All Occasions |  | 255 | 255 | 0 | ZK111/K283 [28]
Additional Sunday buses | 550 | 4 | 1 |  | EYMS | EYMS | 0 |  | 0 | NB £2,200 not charged
Additional Sunday hours | 46.87 | 20 | 2 | 1874.8 | Stagecoach | Stagecoach | 1874.8 |  | 1874.8 | CC to check
Dilap survey | 1950 | 1 | 1 | 1950 | Local Transport Projects |  | 1950 |  | 1950 | CC to check
Thankyou drinks | 800 | 1 | 1 | 800 | Credit card (Furleys) |  | 800 | 800 | 0 | ZK111/K283 [34]
Additional time - Sparrow | 300 | 1 | 1 |  | Sparrow |  |  |  | 0
Additional barriers | 240 | 1 | 1 | 240 | All Occasions | All Occasions | 240 | 240 | 0 | ZK111/K283 [29]
Extra first Aid | 816 | 1 | 1 | 816 | Gary Beestone - GB39 |  | 816 | 816 | 0 | GB
All Occassions credit | -612.05 | 1 | 1 | -612.05 | Gary Beestone - GB40 |  | -612.05 | -612.05 | 0 | GB
Sundries | 110.13 | 1 | 1 | 110.13 | Gary Beestone - GB41 | tea, coffee, suncream, bin bags | 110.13 | 110.13 | 0 | GB
site box kit | 190.23 | 1 | 1 | 190.23 | Gary Beestone - GB44 |  | 190.23 | 190.23 | 0 | GB
Extra signage | 168 | 1 | 1 | 168 | Gary Beestone - GB45 |  | 168 | 168 | 0 | GB
CN pre event | 1472 | 1 | 1 | 1472 | Gary Beestone - GB42 |  | 1472 | 1472 | 0 | GB
CN additions | 1250 | 1 | 1 | 1250 | Gary Beestone - GB43 | wristband exchange | 1250 | 1250 | 0 | GB
|  |  | Total: | 10908.52 |  |  | 10908.52 | 7083.31 | 3825.21

## Misc-Admin
Radio 1 Big Weekend Misc / Admin
Item | Rate | Quantity | Days | Total | Supplier |  | Budget | Actual
R&D phase | 1632 | 1 | 1 | 1632 | Various - historic spend | travel, car hire, accommodation etc. | 1632 | 1632 | 0 | ZK114/K299 [24] ZK201 K115 [37]
onsite catering | 0 | 1 | 1 | 0 | Radio 1 |  | 0 |  | 0
Staff mileage |  |  |  | 0
Rebecca | 150 | 1 | 1 | 150 | Rebecca Clark |  | 150 | 150 | 0 | ZK114/K299 [25]
Helen | 335 | 1 | 1 | 335 | Helen Thackeray |  | 335 | 335 | 0 | ZK114/K299 [25]
Chris | 400 | 1 | 1 | 400 | Chris Clay |  | 400 |  | 400 | CC to check
accommodation | 380 | 1 | 1 | 380 | Chris Clay | onsite accommodation for 3 H2017 staff | 380 |  | 380 | CC to check
BBC recharges | -42573 | 1 | 1 | -42573 | Radio 1 - BBC1 |  | -42573 |  | -42573 |  | Contra to effect with BBC
Taxis | 29.19 | 1 | 1 | 29.19 | Taxi account |  | 29.19 | 29 | 0.19 | ZK114/K299 [25]
|  |  | Total: | -39646.81 |  |  |  | 2146 | -41792.81

## PM-TM
Radio 1 Big Weekend Bus Operation Expenditure - Project and Traffic Management
Item | Rate | Quantity | Days | Total | Supplier | Budget | Actual
GB Ltd. - K137 / ZK107
Pre production | 4850 | 1 | 1 | 4850 | Gary Beestone - GB1
Onsite Managemnt | 8553 | 1 | 1 | 8553 | Gery Beestone - GB1
Accomodation | 3121 | 1 | 1 | 3121 | Various hotels
Travel | 867.73 | 1 | 1 | 867.73 | Gary Beestone - GB1 | 17391.73 | 17392 | -0.27 | ZK107/K137 [7] | ok
LTP - K265 / ZK107
Initial fee | 5000 | 1 | 1 | 5000 | Local Transport Projects
Works associated with traffic mgmt |  |  |  | 2880.5 | Local Transport Projects |  |  |  |  | PO raised
Additional works | 5000 | 1 | 1 | 5756.25 | Local Transport Projects | 13636.75 | 9722 | 3914.75 | ZK107/K265 [8] | PO raised
SEP - K260 / ZK107
Service fee -SEP | 71081 | 1 | 1 | 71081 | Gary Beestone - GB47 | 71081 | 71081 | 0 | ZK107/K260 [9] | £81 balances the actual to the budget
SMC | 4000 | 1 | 1 | 5291.65 | Stadium Management Co. | 5291.65 | 5292 | -0.35 | ZK107/K261 [30]
Bus recovery vehicle | 12300 | 1 | 1 | 12300 | Sparrow | 12300 | 12300 | 0 | ZK800/K260 [31]
|  |  | Total: | 119701.13

## EXP. all sites
Radio 1 Big Weekend Bus Operation Expenditure - across all sites
Item | Rate | Quantity | Days | Total
Infrastructure
crew | 2211 | 1 | 1 | 2211 | GB2
fuel & bowser | 0 | 1 | 1 | 0
radios | 113 | 1 | 1 | 113 | GB3
Liability disclaimer signs | 44 | 1 | 1 | 44 | GB4
|  | 1 | 1 | 0
|  | 1 | 1 | 0
|  | 1 | 1 | 0
|  | 1 | 1 | 0
|  | 1 | 1 | 0
|  | 1 | 1 | 0
|  |  | Total: | 2368

## EXP. BC
Radio 1 Big Weekend Bus Operation Expenditure - Burton Constable
Item | Rate | Quantity | Days | Total | Supplier
Venue Costs
Hire fees |  |  |  | 0
Other venue costs |  |  |  | 0
Personnel
Site Manager |  |  |  | 0
Asst. Site Manager |  |  |  | 0
Bus Controller |  |  |  | 0
Security |  |  |  | 0
Stewards |  |  |  | 0
Infrastructure
Fencing | 23688 | 1 | 1 | 23800 | Radio 1 - BBC2 | ZK103 K161 |  | PO for 88,564
CCB | 0 | 1 | 1 | 0
Trackway | 53664 | 1 | 1 | 53664 | Radio 1 - BBC3 | ZK103 K161
Trackway standby | 1500 | 1 | 1 | 1500 | Radio 1 - BBC4 | ZK103 K161
Lighting | 6490 | 1 | 1 | 6490 | Radio 1 - BBC5 | ZK103 K161
Signage | 944 | 1 | 1 | 944 | Gary Beestone - GB5
Toilets | 2110 | 1 | 1 | 2110 | Radio 1 - BBC6 | ZK103 K161
VMS sign | 0 | 1 | 1 | 0
Cabins | 1000 | 1 | 1 | 1000 | Radio 1 - BBC7 | ZK103 K161
Loud hailers | 0 | 1 | 1 | 0
PA system | 1278 | 1 | 1 | 1278 | Gary Beestone - GB6
Distro | 532 | 1 | 1 | 532 | Gary Beestone - GB7
Ped Barriers /Heras Fencing |  |  |  | 895 |  |  | ZK111 K283 [38]
Ped Barriers /Heras Fencing extended |  |  |  | 685 |  |  | ZK111 K283 [38]
Tree |  |  |  | 100 |  |  | ZK107 K136 [38]
Gate Repair |  |  |  | 295 |  |  | ZK107 K136 [38]
Extra heras fencing |  |  |  | 1566 | Radio 1 |  | ZK106 K247 [40]
|  |  | Total: | 94859

## EXP. Walton St
Radio 1 Big Weekend Bus Operation Expenditure - Walton St / KCOM
Item | Rate | Quantity | Days | Total | Supplier
Venue Costs
Hire fees | 250 | 1 | 2 | 500 | NPS Number | May not be charged
Other venue costs |  |  |  | 0
Personnel
Bus Controller |  |  |  | 0
First aid | 204 | 1 | 1 | 204 | Gary Beestone - GB15
Stewards | 4717.5 | 1 | 1 | 4717.5 | Gary Beestone - GB8
Infrastructure
CCB | 750 | 1 | 1 | 750 | Gary Beestone - GB9
Toilets | 2495 | 1 | 1 | 2495 | Gary Beestone - GB10
Waste Management | 800 | 1 | 1 | 800 | Gary Beestone - GB11
Signage | 114 | 1 | 1 | 114 | Gary Beestone - GB12
Driver welfare | 764.2 | 1 | 1 | 764.2 | Gary Beestone - GB13
lighting | 3200 | 1 | 1 | 3200 | Gary Beestone- GB14
|  |  | Total: | 13544.7

## EXP. Leconfield
Radio 1 Big Weekend Bus Operation Expenditure - Leconfield
Item | Rate | Quantity | Days | Total | Supplier
Venue Costs
Hire fees | 3932 | 1 | 1 | 3932 | Ministry of Defence | 3932 | 3932 | 0 | ZK800 K223 [32]
Landscaping | 0 | 1 | 1 | 0
Personnel
Security | 5662.5 | 1 | 1 | 5662.5 | Gary Beestone - GB16
first aid | 204 | 1 | 1 | 204 | Gary Beestone - GB17
Crew |  | 1 | 1 | 0
Infrastructure
Fencing | 1482 | 1 | 1 | 1482 | Gary Beestone - GB18
Trackway | 0 | 1 | 1 | 0
Lighting | 6400 | 1 | 1 | 6400 | Gary Beestone - GB19
Toilets | 1875 | 1 | 1 | 1875 | Gary Beestone - GB20
Waste Management | 626.56 | 1 | 1 | 626.56 | Gary Beestone - GB21
Signage | 144 | 1 | 1 | 144 | Gary Beestone - GB22
Driver Welfare | 521 | 1 | 1 | 521 | Gary Beestone - GB23
|  |  | Total: | 20847.06

## EXP. Interchange
Radio 1 Big Weekend Bus Operation Expenditure - Interchange
Item | Rate | Quantity | Days | Total
Venue Costs
Hire fees |  |  |  | 0
Other venue costs |  |  |  | 0
Personnel
Site Manager |  |  |  | 0
Asst. Site Manager |  |  |  | 0
Bus Controller |  |  |  | 0
Security | 2837 | 1 | 1 | 2837 | GB24
Infrastructure
Fencing |  |  |  | 0
CCB | 399 | 1 | 1 | 399 | GB25
Waste Management | 800 | 1 | 1 | 800 | GB26
Signage | 90 | 1 | 1 | 90 | GB27
Toilets | 490 | 1 | 1 | 490 | GB28
First Aid | 204 | 1 | 1 | 204 | GB29
Other 4 |  |  |  | 0
|  |  | Total: | 4820

## EXP. Grove Hill
Radio 1 Big Weekend Bus Operation Expenditure - Grove Hill
Item | Rate | Quantity | Days | Total
Venue Costs
Hire fees |  |  |  | 0
Other venue costs |  |  |  | 0
Personnel
Bus Controller |  |  |  | 0
Security | 3578 | 1 | 1 | 3578 | GB30
First aid | 204 | 1 | 1 | 204 | GB31
Infrastructure
Fencing | 698.25 | 1 | 1 | 698.25 | GB32
CCB |  |  |  | 0
Lighting | 800 | 1 | 1 | 800 | GB33
Cabins |  |  |  | 0
Toilets | 565 | 1 | 1 | 565 | GB34
Waste Management | 226.56 | 1 | 1 | 226.56 | GB35
Signage | 36 | 1 | 1 | 36 | GB36
Driver welfare | 764 | 1 | 1 | 764 | GB37
Other 3 |  |  |  | 0
Other 4 |  |  |  | 0
|  |  | Total: | 6871.81

## EXP. Buses
Radio 1 Big Weekend Bus Operation Expenditure - Buses - Total Req. 169
Item | Rate | Quantity | Days | Total | Supplier | Budget | Actual
Operator - EYMS - K115 / ZK102 | [11 empty] | 0
Buses | 390 | 20 | 2 | 15600 | EYMS
Supervisors | 300 | 4 | 2 | 2400 | EYMS
Additional for non local buses | 80 | 10 | 2 | 1600 | EYMS
Additonal Mileage | 4758 | 1 | 1 | 4758 | EYMS | 24358 | 24358 | 0 | ZK800/K115 [19]
Operator Stagecoach - K116 / ZK 102
Buses local- 16 hours | 750 | 30 | 2 | 45000 | Stagecoach
Buses national 16 hour | 750 | 24 | 2 | 36000 | Stagecoach
Buses local 8 hour | 375 | 34 | 2 | 25500 | Stagecoach
Substinence | 40 | 38 | 3 | 4560 | Stagecoach
relocation of buses | 375 | 24 | 2 | 18000 | Stagecoach
Supervisors | 216 | 15 | 2 | 6480 | Stagecoach
Accommodation | 10753.75 | 1 | 1 | 10753.75
Mileage | 12650.74 | 1 | 1 | 12650.74 | Stagecoach
Route registering | 60 | 1 | 1 | 60 | Stagecoach | 159004.49 | 159004 | 0.49 | ZK800/K116 [10]
Operator First Group - K202 / ZK102 | [8 empty] | ZK102/K116 [39]
Buses | 0 | 23 | 2 | 0 | First Group |  |  |  | ZK106/K248 [39]
Buses | 0 | 12 | 2 | 0 | First Group |  |  |  | ZK 107/K258 [39]
Egress bus | 0 | 9 | 2 | 0 | First Group
Egress buses | 0 | 8 | 2 | 0 | First Group
Supervisors | 0 | 2 | 2 | 0 | First Group
Route registering | 0 | 1 | 1 | 0 | First Group
Other 2 | 97986.87 | 1 | 1 | 97986.87 |  | 97986.87 | 97987 | -0.13 |  | ZK800 K202 [52]
Operator Acklams - K203 / ZK102
Buses | 850 | 8 | 2 | 13600 | Acklams
Sweeper | 1160 | 1 | 2 | 2320 | Acklams | 15920 | 15920 | 0 | ZK800/K203 [11]
Mileage |  |  |  | 0
Other 2 |  |  |  | 0
Route registering
Additional mileage | 0 | 1 | 1 | 0 |  | allowance
Wristbands K258 / ZK107
Wristband printing | 9209.83 | 1 | 1 | 9209.83 | ID&C | 9209.83 | 9210 | -0.17 | ZK107/K258+ZK109/K270 [12] |  | Identified £723 to be invoiced by IDC. Hold in contingency
Additional bands | 0 | 1 | 1 | 0 |  | Change of services
resident bands | 0 | 1 | 1 | 0
Trackway test | 1200 | 1 | 1 | 1200 | Davis Track Hire | 1200 | 1200 | 0 | ZK800/K115 [18]
|  |  | Total | 307679.19 |  | 307679.19 | 307679 | 0.19
Note on H18: Glenn Harley: £150,122 Stagecoach £8,882 All other accomodation

## Sheet2
Gross Budgeted Expenditure |  |  | 1064094.86
INVOICE TO RECEIVE
Alternative grazing, fencing etc. | BC | 15108.1 |  | ZK107 K136 (part of £41,209) |  |  |  |  | 15108.1
Cundalls Fees |  | 2567.5 |  | ZK107 K136 |  |  |  |  | 2567.5
JAS Martin fees |  | 600 |  | ZK107 K137 |  |  |  |  | 600
Loss of income | Café | 7500 |  | ZK107 K136 |  |  |  |  | 7500
Loss of income | BC | 26101.18 |  | ZK107 K136 (part of £41,209) |  |  |  |  | 26101.18
-51876.78
CC INVESTIGATING
PM-TM |  | 1034 |  | ZK107 K265
PM-TM |  | 2880.5 |  | ZK107 K266 | but currently in Tech/Opps
Walton Street |  | 500
Lost property |  | 50
Contingency | Stagecoach | 1874.8
Contingency | Local Transport Projects | 1950 |  | ZK111 K283
-8289.3
R1
BC |  | 88564
Marquees |  | 4507
Furniture |  | 103
Heating |  | 1580
Welfare tent |  | 713 |  |  |  | Actuals |  | 2017-10-24 | 2017-11-08 |  |  | Actuals
cabins |  | 1650
Buggies |  | 663 |  |  |  | 50933 | 16/17 | 50933 | 50933 |  |  | 50933 | 16/17
water, power etc. |  | 7500 |  |  |  | 41011 | 17/18 | 301398 | 356259 |  |  | 41011 | 17/18
Misc-Admin |  | -42573 |  |  |  | 10444 | PO's | 115224 | 115224 |  |  | 10444 | PO's
|  |  | -62707 |  |  | -500 | PO to cancel | 0 | 0 |  |  | -500 | PO to cancel
[6 empty] | 150000 | BBC | 0 |  |  |  | 150000 | BBC | 51
Misc-Admin |  | 400 |  |  |  | 12400 | Roche | 0 |  |  |  | 12400 | Roche | 53
Misc-Admin |  | 380 |  |  |  | 96307 | First | 0 |  |  |  | 96307 | First | 52
|  |  | -780 |  |  | 1680 | First | 0 |  |  |  | 1680 | First | 52
[12 empty] | 88564 | BBC
[12 empty] | 9813 | Cabins,buggies,power
|  |  | 940441.78 | [8 empty] | 6903 | Marquees,furniture,heating
[12 empty] | 41209 | BC Compensation | 61
Net Income |  |  | -576055.37 | [8 empty] | 7500 | Caterers | 62
[8 empty] | 467555 | 522416 |  |  | 2568 | Cundalls | 63
Total |  |  | 364386.41 |  |  | 362275 |  |  |  | 2111.41 | Variance to find | 600 | Jas Martin | 64
[12 empty] | 1034 | Traffic Mgmt
[10 empty] | 220 | Unidentified Actual costs | 1950 | Traffic Mgmt
[6 empty] | 51877 | O/S invoices | 51877 |  |  | Unidentified Pos
[6 empty] | 8288.5 | CC check | 5409 |  | 220 |  | 2881
[6 empty] | 105280 | BBC R1
[6 empty] | -42573 | BBC R2 | -42573
[6 empty] | 780 |  | 780
525297
[6 empty] | 485927.5 | Estimated net cost | 483048
576055
[6 empty] | 1061982.5 | Estimated Gross Cost
-2112.36