## Agenda
THE LAST TESTAMENT OF LILLIAN BILOCCA
Project Team Meetings
AGENDA ITEM | NOTES / ACTIONS | INITIALS
PRODUCTION MANAGEMENT
CREATIVE / ARTIST
PRODUCTION / TECHNICAL
VENUE
STAFFING
BUDGET
ADMIN / CONTRACTS
MARCOMMS
COMMUNITY COMPANY
MISC

## Sheet1
THE LAST TESTAMENT OF LILLIAN BILOCCA
Project Team Meetings
AGENDA ITEM | NOTES / ACTIONS | INITIALS
PRODUCTION MANAGEMENT
CREATIVE / ARTIST
PRODUCTION / TECHNICAL
VENUE
STAFFING
BUDGET
ADMIN / CONTRACTS
MARCOMMS
COMMUNITY COMPANY
MISC

## 05.09.17
THE LAST TESTAMENT OF LILLIAN BILOCCA
Project Team Meetings
AGENDA ITEM | NOTES / ACTIONS | INITIALS
PROJECT MANAGEMENT | Final risk register, roles breakdown to be agreed | LA / EJ
| Organogram to be shared with LA, BP & AR | RA
CREATIVE / ARTISTIC | Check plans for first day of rehearsals with Sarah | LA
| Establish number of child performers per show, rehearsal model & audition process with Sarah | LA
| Conversation re JB role with community company & performance role with Sarah. Offer fee top up | LA
PRODUCTION / TECHNICAL | No notes
VENUE | Insurance feedback to EJ | AC / LA / PB
| New route to be confirmed with creative team and circulated to all | BP
| Unison still proving difficult to reach. PB to pick up this conversation. LA sourced email contact | PB
| Venue contract & deal negotiation to pick up next week | LA
| BP talking to venues adjacent re technical matters & lighting | BP
| Schedule to be added as outlook diary & info re weddings to be circulated to BP & AC | RA / LA
STAFFING | Volunteering - on next weeks agenda. Volunteering meeting next week. LA to arrange. | all / LA
| DSM recruitment was disappointing and no suitable candidates. BP to speak to SF re 2 ASMs | BP
BUDGET | Assistants & makers line has been ammended | EJ
| Factor in JB top up fee | EJ
| Accommodation to be reviewed with KN. Budget to be reviewed | EJ
| EJ & LA to discuss budget on Thurs | EJ / LA
ADMIN / CONTRACTS | Sarah & Fi's contracts have been issued
| Actor contracts & riders to be drafted by KN for input | KN / EJ / LA / AC
| Digs lists to be sent out asap . Completed subsequent to meeting. | KN / EJ
| Press contacts to be shared with KN for contact sheet | LA
MARCOMMS | Community cast tickets need to be released by 02.10.17 | AR / RP
| Staff category to be reviewed in project meeting next week | all
| Counsellors to be accommodated. HTT usually invite all 70 but low attendance. Agreed we can accommodate councellors somewhere 1 ticket each - dates TBC. Guildhall staff to attend dress. | RP
| Relationship to be explored with Kardomeh as production bar & hosting press night. In kind support for posters etc in return for custom | PB
| Access conversation taken place with George at Council. They can provide scooter & wheelchair. Audio description is happening. Captioned show is dependent on wifi. Ben leading on wifi conversation. Confirm details by end of Sept. | PB / BP
COMMUNITY COMPANY | Molly & Rach to support admin of applications on Fri as required. JB av all Sat should additional slots be required. AR to allocate slots on Fri. HTT to provide Ipad for filming. PB to cover fire evac and H&S info. JB to provide usual welcome briefing. AR to read all health forms, flag any issues with JB and sign. | PB / AR / RA / MS
| Letter to be reviewed by EJ and sent out | EJ / LA / AR
| Rehearsal space to be confirmed next week | EJ / AC
| Community engagement plan to be circulated next week | RP
MISC

## 13.09.17
THE LAST TESTAMENT OF LILLIAN BILOCCA
Project Team Meetings
AGENDA ITEM | NOTES / ACTIONS | INITIALS
CREATIVE / ARTIST | Route rundown reviewed. C1 used on ground floor & Raleigh Room require additional permissions. | LA
| Pram race. BP to advise on reason for moving to end. Children called later may be an issue. | LA / EJ
| Voice sessions to be booked in. Natalie Grady is a good option & Manc based. | LA
| LA confirmed 1 child performer with Sarah. Casting to be carried out by HTT team. 3 rehearsal sessions | EJ
| Jon Beney to be offered professional role on an actor's wage. Remove £1k expenses in favour of subs | LA
PRODUCTION / TECHNICAL
VENUE | Professional rehearsals at HTT. Community Company pre rehearsals at HTT. | EJ
| Release Holy Apostles | MS
| Guildhall for community company during main period | LA
| Unison to be chased | PB
| Kardomeh to be chased | PB
STAFFING | DSM options being explored with BP & AC | BP / AC
| Potential for propping to start week before rehearsals suggested by SF. BP to consider | BP / AC
BUDGET | Updates - to be reviewed by EJ & LA and signed off by JMW on her return | EJ / LA / JMW
ADMIN / CONTRACTS
MARCOMMS | Community - 5 groups & individuals. Hessle Rd, Orchard Park, Bransholme, Goodwin areas. Heron pop up box offices in each area. Ticket allocation for each. PWYD. 2 per person. | RP
| Guest ticket list to be reviewed next week. Invites to go out w/c 25 Sept. H17 & HTT lists to be compared. | JMW / RP
| Programme - pamphlet style. Content provided by History Centre or Alec Gill. | RP
| Exhibition FOH at HTT to be explored. Previous connection to Alec Gill discussed. | RP
| Richard Davenport booked to do photography. | VT
COMMUNITY COMPANY | First day on Fri 22 Sept at 6pm in the studio. Invite HTT team. Invite Amanda & Fi to take measurements. | MS / LA / AR / AC
| Comm Comp form to be sent to AR re their biogs. | RP / AR
| AR & LA to finalise offers to participants. | LA / AC
| RYAE to be approached & EJ to lead financial conversation about offering bursery. | MS / EJ | Decided not to pursue this post the meeting due to feedback from Imogen.
ACCESS | Audio described is confirmed. Radio/headphones to be explored. | PB
| Captioned is still TBC | PB
VOLUNTEERING | Meeting on Fri with Harriet. 38 people in total. 2 per community rehearsals. Pram race & children. | AC / LA / PB
MISC

## 19.09.17
THE LAST TESTAMENT OF LILLIAN BILOCCA
Project Team Meetings
AGENDA ITEM | NOTES / ACTIONS | INITIALS
CREATIVE / ARTIST | Natalie Grady is on board as voice coach
| Offer to Bret Yount (fight dir) | LA
| Check that no communication with Adrian has implied we'll only do 6 shows in last week so that if the Guildhall allows us to add 5.30 on final Friday we can do that. | LA
PRODUCTION / TECHNICAL
VENUE | Check Guildhall AV for 5.30 performance on final Fri | LA
| TP has been struggling to get hold of the Kardomah mgt. Lindsey will see if she can find a contact via Hull 2017. If that fails, EJ will assist TP in drafting a letter, to come from Janthi. | LA initially
| Strategic Leadership Meeting with Council on Tues 3rd to clarify expectations. Lindsey & Ben to be accompanied by Mark or Janthi. | LA
| TP to do letter of agreement with Unison - EJ will assist. Issues to explore: cleaners, cross purpose marketing, wifi. | TP/EJ
STAFFING | EJ and AC have altered Stage Management configuration. Den Body to DSM. Will hand over to 2 ASMs after press night. For shows - 2 x ASM, 1 x CSM. Contracts to be sent. | EJ
BUDGET | Budget to be signed off by JMW with EJ & LA . EJ will issues budget with notes for departmental budget holders. | EJ
ADMIN / CONTRACTS | Nothing to report
MARCOMMS | Alec Gill exhibition not touring so may be available for our foyer. Follow up. | LA
Banners have been signed off
| Plan is to do a press release re cast next week | VT
| Speak to Sarah about filming query from Vicki | LA
COMMUNITY COMPANY | Amber reported she has offered to all today. Meet and Greet on Fri (also measurements)
| Send Danielle Community cast list for ticket allocation | AR
| Deadline for claiming tickets: Fri 29th (Entitled to 2 tickets - 1 comp & 1 paid for) | AR/DM
| Send list to Harriet - how many are Hull 2017 Volunteers? | AR
| Organise refreshments for Friday (check no alcohol policy with Janthi - waiver was agreed post-meeting) | TP
| Send invite to Friday meet and greet to all staff | MS
| Bring the big ground plan on Fri | RA
ACCESS | TP to attend disability training a Kardomah, 10-1 tomorrow | TP
| Still questions about wifi and captioning. TP has spoken to D4. Exploring an independent laptop router. | TP
| Audio description: talk to Ben, Mat, Martin Atkinson and dreamthinkspeak about the tech side and how to do it | TP
| Take George (Council access person) around the route | TP/Danielle
TP confirmed we can borrow Guildhall's scooters and wheelchairs. Most people should be able to stay in their own but if they are larger they may need to move to the Guildhall ones.
| Need to measure doors for table room and lifts | TP
All noted we're not trying to achieve a relaxed performance.
| Danielle to run access pre email past the team | DM
VOLUNTEERING | Put together a plan of what we think FOH looks like then put to Sarah | TP
| Harriet advocated dreamthinkspeak model for division of FOH roles - training 50 people to cover all roles | AC/TP/LA
| Safeguarding for pram race - need a system in place | EJ / LA
| If we can find the money, would it be better to work with a defined goup with chaperones? NAPA? | EJ/ LA
| LA to ask Sarah about reason for pram race moving to the end | LA
| If we can get the pram race back to the beginning, we'll pursue idea of using volunteers wih Harriet | LA
| Create a dot map of the building for the volunteers | TP/AC
| Food - paid ushers don't have meals provided, 2017 volunteers do. Community company don't at the minute. We need to ensure we treat different groups appropriately and in way which doesn't affect team spirit. | LA/ EJ
| Ask Harriet to tell us what Hull 2017 would budget for feeding volunteers to see if we can cover community cast on 5.30/8.30pm days (3-4 shows total) | LA
| LA and TP to look at volunteers' shift schedule | LA /TP /AC
| w.c 25th deadline for all Voluneer info to Harriet | LA /TP / AC
MISC | None

## 26.09.17
THE LAST TESTAMENT OF LILLIAN BILOCCA
Project Team Meetings
AGENDA ITEM | NOTES / ACTIONS | INITIALS
Attending: Lindsey Alvis, Elizabeth Jones, Paul Bennet, Ruth Puckering, Amber Rennison, Rachael Abbey (Danielle McLoughlin late)
UPDATES | Natalie booked as voice coach and has already attended first session,
| brett yant flight director on board just need AL to set fee. | AL
Kardomah not responding to TP but all ok with martin
strategic meeting with council is next tues and AL and Ben Pugh to check.
SM all set and offers set off.
Budgets to be signed off by Janthi.
| Alec Gills hessel road photograhic exhimbition - RP to talk to Phil Batty to talk about exhibition with the lil company | RP
| plan to do a press release about casting this week. Go to ruth to talk about all press. RA to send RP cast list. LA keen to make sure theres no backlash about not hiring a hull actress in lead role | RA
Community cast had meet and greet last Friday , measurements taken. Com Cast offered 2 tickets, 1 comp 1 paid. If they want more than 2 it will be offered on a case by case basis.
| deadline for claiming tickets by C Cast is Friday 29th and general release is Monday 2nd. AL to attend RP meeting with Janthi about councillors allocation | AL/RP
| Harriet got list of voluteers - AR to chase her to find out who is a h17 vol. | AR
TP did access training. TP confirmed that we can use the guildhall scooters. No relaxed performance. Harriet advocated a Dream Think Speak model for front of house.
Conversation happened about food about costs with AL.
| AL having active convo with Sarah F about pram race. Paul is creating a map. TP to talk about shift schedule. | AL
MARKETING AND COMMS | EJ has sent RP performance terminology through about what the difference between press night and guest night are. Press night will be a chance for actors and company to join audience in Kardomah. Few holds left for Press for actors in case of agents etc. Press night is official first night. Press and Guest post show drinks at KArdomah. RP to talk to janthi about guest invites. | RP
| LA is managing VIPs for guest night, DMs list is quite general. DM to think about whether the release date of excess tickets should be 2nd or 9th oct. Tickets for Ccast are to be reserved not given to them in case of drop outs | LA/DM
| Programme - RP to pick up with Emma. Heron have come back to RP about selling tickets in store. DM to tell RP how many community tickets are available to sell at Heron Box Offices - first come first served - pay what you can. RP to write out method statement on the Heron initiaitve to give to ben McKnight in case of backlash - michael to be lead box office for it - limited to 2 pp. AL to chase sarah for BBC filming. First day rehearsals - AL to ask kate to book all tickets over. First day - Ruth Mark Lindsey Amy tickets needed. Refunds only available 24 hours before. Not publicised selling on the door. 10am standby release as usual. | RP
ACCESS | Captioning - Need dongle wifi/internal wifi and the live captioner will submit the words to iPads. Worth progressing with it despite pervious concerns. Captioning kit already booked. TP to go to Flood to watch captioning. TP to contact SMHS. 20 tickets held off for captiong on wed 15th at 5.30. Audio description is more difficult but its quite resource heavy. LA to talk to a audio describer to discuss the best most feesable outcome. Budgeting the options for audio description. After conversations , a descison will be made hopefully next week. | TP/LA
wheelchair spaces not booked, potential for targeted sales
Ade at Unison - TP has talked to them and we have access to wifi for box office systems, we may need to make a mop and bucket to do additional cleaning.
VENUE | AL spoke to richard C1 is booked out. Think additional show has go ahead. AL has contact to adjecent buildings for lighting into the building. Revised contract with guildhall. Test event 19th oct for test event. Venue meeting next week, can predict what they want to know
security gates will be put in at main reception, need to check if they will be installed before the show or not. Creative team have been told.
COMMUNITY COMPANY | meet and greet went well. AR got in contact with missing 5. rehearsals start this week. Cash will be given for travel. Petty cash for AR so she can buy refreshments. Needs a proper health and saftey walk around so they can have the code for backstage doors.

## 03.10.17
THE LAST TESTAMENT OF LILLIAN BILOCCA
Project Team Meetings
AGENDA ITEM | NOTES / ACTIONS | INITIALS
FOH/ACCESS | PB and DM To have meeting with George | PB/DM
| PB to talk to technicians to get the correct style dongle | PB
| PB to talk to Malcom r.e. Kardomah and go to The City Pub as research | PB
| Need a FOH meeting to talk about costume etc | BP
| PB and EJ to go through FOH Risk assessments | PB/ EJ
MARCOMMS | LA needs councillors list for guest night | LA
| RP to send casting press release to LA first | RP
| talk to guildhall about tours | LA
| RP to chase Phil Batty about information for the other Lil production and set up meeting with the other company | RP
| diary to be hopefully kept by community cast member and potenitally put on blog | AR
COMMUNITY COMPANY | Amber needs a key for Rehearsal room, AR and BP need security codes etc | RA
| Need to check accreditation lanyards for spelling mistakes or missing people | AR

## 09.10.2017
THE LAST TESTAMENT OF LILLIAN BILOCCA
Project Team Meetings
AGENDA ITEM | NOTES / ACTIONS | INITIALS | Action?
Matters Arising
FOH/ACCESS | PB and DM To have meeting with George | PB/DM | will be Wed 11 Oct
| PB to talk to technicians to get the correct style dongle | PB | on agenda
| PB to talk to Malcom r.e. Kardomah and go to The City Pub as research | PB | on agenda
| Need a FOH meeting to talk about costume etc | BP | TP will update BP with info about numbers
| PB and EJ to go through FOH Risk assessments | PB/ EJ | ongoing
MARCOMMS | LA needs councillors list for guest night | LA | still o/s
| RP to send casting press release to LA first | RP | been done….with SF
| talk to guildhall about tours | LA | not done yet
| RP to chase Phil Batty about information for the other Lil production and set up meeting with the other company | RP | RP has liaised
| diary to be hopefully kept by community cast member and potenitally put on blog | AR | AR on with this…
COMMUNITY COMPANY | Amber needs a key for Rehearsal room, AR and BP need security codes etc | RA | AR has codes, PB will tell BP
| Need to check accreditation lanyards for spelling mistakes or missing people | AR | AR on the case
And today's meeting
FOH/ACCESS | DM has done a draft access statement for public which PH & EJ will check and liaise further with wider group. | EJ /PH
| Risk Assessment for Unison to be drafted by PH/EJ and then checking w Brian | EJ /PH
| Tell Andy about Unison not wishing to sign | EJ
| Ruth would like to go and look at Unison re audience experience, signage etc | PH
| General plan for use (toilets/cleaning etc) | PH
| Audience don't now need numbering - so just wristbands | PH
| PH has met with Harriet, is asking for 16 volunteers (11 min per show) - going to go for training pool of 50. Form to be completed & checked with LA. Suzy is doing one for backstage. Training Thurs 26 Oct. | PH /SS
| FoH drinks facility and Guest Night location still to be solved. | PB / RP / LA
| PB to meet with MA re captioning chat | PB
| LA to email HODs re test event | LA
MARCOMMS | Cast release awaiting sign off | SF / L A
| Programme concept awaiting sign off | SF / L A
| Key fishing groups given 25 tickets each | RP
| Heron PWYC ongoing | RP
| Exhibition going up at HTT on 26 Oct. Cost £500 | RP / PB
| Chase guest list from LA & Dav | RP
COMMUNITY COMPANY | One participant upset last week - dislosed by another participant. Check in with her at next session. | AR
| RA competed for participant who is pregnant. Monitoring ongoing | AR / JB / KN

## 17.10.17
THE LAST TESTAMENT OF LILLIAN BILOCCA
Project Team Meetings
AGENDA ITEM | NOTES / ACTIONS | INITIALS
All previous actions completed
FOH | PB picked up unison keys. Adrian will get 2 comps as a thank you. | PB/DM
| wristbands to be ordered. LA to send PB the exact colours of them. | TP/LA
| Audio describer and 8 FOH to attend on Thursday for the test event | TP
| RA to ask AC/ SS who will attend test event from their team | RA
| PB to ask Richard if they have wet floor signs Etc | PB
| Will there be radios between tech and FOH? | AC/ BP
| PB to consider how to handle cloakroom as part of the show | PB
| PB to get price of beer, wine and prosecco for press night | PB
BOX OFFICE | edits to be made to the email of customer information | DM
| Cutomer information email to be sent to Sarah F to proof | RP
All creative team need tickets every night until press night x10.
MISC | DM to get number of tickets total going back on sale to LA | DM
MARCOMMS | Excess VIPs to be redistributed throughout other performances | DM/LA/RP
| Sarah needs to proof the programme | RP
| RP to send next draft of invites letter to LA | RP
COMMUNITY COMPANY | Friday 17th additional show to go ahead, Ccast to find out | AR
| Saturday morning rehearsal to go ahead? AR to ask Jon | AR
| Need to get Preganancy RA signed and to forward to LA | AR
OTHER | Who is organising cast party on the 9th? | ALL
| Who organises the card? Can we get H2017 signatures on it? | RA
| Who organises cast and creative gifts? | RA