RICHARD WOODS STUDIO LTD

27 Coate Street

London E2 9AG

Method statement (starting date 22.06.17)

For

Hull City of Culture

Employees

(All supplied with hard hats, hi-vis waistcoats and steel toe capped shoes)

Richard Woods

Kieran Mullen

Michael Iverson

Site address

Humber Street area of Hull

Tools

Tape Measure

Step ladder

Cherry picker

Stanley knife

Carpenters Pencils

Straight edge

Paint roller and roller tray

Latex protective gloves

Hard Hat

Protective googles

Scaffold tower

Protective builders gloves

Materials

Red 350 gsm paper ( supplied by GF Smith)

Grey 350 gsm paper  ( supplied by GF Smith)

water based exterior PVA glue ( screwfix brand)

Job Description

Pasting sheets of 350 GSM paper to plywood boards in a brick motif pattern.

The plywood boards have been pre fixed to three buildings in the Humber Street area of Hull.

Method

Using a carpenters pencil and tape measure, draw a  brick pattern onto the  plywood sheets ( the plywood has been pre fitted to the buildings on Humber Street).

Once this pattern has been completed start filling the pencil drawn brick shapes in with the red paper sheets.

The paper sheets will be glued using water based exterior PVA glue. Glue will be applied using a decorators roller.

Some of the wall will be above head height. When paper is attached to walls that are above head height a scaffold tower will be used .

If the ground is not level enough for a scaffold tower then we will use a cherry picker.

Once all the red paper sheets have been attached to the plywood clad wall , we will cut the grey paper to the correct size to fill the spaces left. We will cut the grey paper using a stanley knife and a steel straight edge. Protective builders gloves to be used whilst cutting with a Stanley knife.