|  |  |
| --- | --- |
| **Name of Individual / Organisation** | Hull LGBT+ COMMUNITY PRIDE |
| **Name of Project** | Pride in Hull 2017 |

Please provide a breakdown of key activities /tasks for your project from start to finish. Please include your preparation and planning activity as well as start / end dates of your public activity (eg. public performance, exhibitions, festival).

|  |  |  |  |  |
| --- | --- | --- | --- | --- |
| **START DATE** | **END DATE** | **ACTIVITY / TASK** | **STATUS** | **NOTES** |
|  |  |  | COMPLETE / ON-TIME / BEHIND |  |
| 01.09.16 | 01.12.16 | Venue, event site and parade route planning | Complete |  |
| 01.09.16 | 31.03.17 | Film and song writing competitions | On time (song writing is not going ahead) |  |
| 01.10.16 | 31.03.17 | Site safety, first aid and security planning with ESAG collaboration | On time |  |
| 01.10.16 | 31.03.17 | Sponsorship promotion and sales | On time |  |
| 01.12.16 | 31.03.17 | Headline artist booking | Behind |  |
| 01.01.17 | 31.03.17 | Small venue booking | Behind |  |
| 01.01.17 | 31.03.17 | Sound, light, security, toilet facilities hire, infrastructure equipment hire | On time |  |
| 01.01.16 | 31.05.17 | Local and other artists booking | On time |  |
| 01.01.16 | 30.06.17 | Community market, vendor and local agencies engagement | On time |  |
| 01.01.17 | 29.07.17 | Marketing and PR activities | On time |  |
| 01.01.17 | 29.07.17 | Volunteer programme | On time |  |
| 01.08.17 | 30.10.17 | Feedback to Hull 2017 | On time |  |
| 01.08.17 | 30.10.17 | Feedback from local authority and police  | On time |  |
|  |  |  |  |  |
|  |  |  |  |  |

Activity Examples: Planning Meeting, Auditions, Contracting, Rehearsal, Costume Design, Performances