Thor phone catch up

Wednesday 29th March, Lowgate Project Room 1. Present: Katy (partially), Lou, Elizabeth, Thor (on the phone)

Update on narrative

- 1st Heralding:

  - Yorkshire Water are doing some routine digs across the city, including outside Asda on Beverley Road and in Pickering Park. At their dig at Asda, they have come across one crate at each site (though the one at Asda is an actual crate and the other at Pickering Park is a digital manifestation). Both crates have GGF and Re-rediffusion logos on them. One crate contains part of a Viero and the other crate contains the other part.

  - Yorkshire Water call in the GGF, who make a press call out, asking for people who worked for Rediffusion. Some social media plants (i.e. volunteers who’ve been trained up and have RRD characters) respond with personal connections (e.g. First bit: actual Redifussion guy says we never did work like that but there was a tale of a secret research branch, but we all thought that it was an urban legend. Then another person says oh my grandpa used to work for a secret research department called Re-Rediffussion, and recently in my loft I found a box with the plans for the contraption you’ve found… etc). More social media round ups of all these (plants) who know different bits about the org.

- Following weekend press moment (i.e. 26th): whole team photoshoot with a request for the public to contribute your voice to this project. Includes the now assembled Viero.

- First set of voice collection Saturday 1st

  - 5 days out in the community and on the streets doing voice collecting from Beverley Road.

    - Pre-programmed with different community groups, schools, shopping centres, etc. along Beverley Rd but moving towards Hessle Rd

  - Then 5 days’ hiatus for editing

  - Followed by 5 more days of voice collecting starting from the 12th

    - Head wider and closer to Hessle Rd. Hopefully with the social media campaign they’ll get individuals suggesting they visit their homes/parties/groups to collect their voices

- Hiatus over August. Various press moments showing photos of RRD team making site visits all over Hull, searching for a suitable power source to finally create their Voice Diffuser.

  - We’ll also need to general more comms around distilling Hull’s voice and why we need a public-facing outdoor location.

- 2nd Heralding: 1st week in September

  - A giant crate the size of a cabin magically appears in Pickering Park. Members of the GGF and RRD teams go to investigate. They open the crate and find the loose part to the power source they have been searching for!

  - At the same time as this, there will be more voice collecting going on from the 6th to the 9th this time in the Hessle Rd area. They go out again on Saturday 16th.

- Install at Pickering Park Tues 19th to Thurs 21st.

- Fri 22nd Soft Launch inviting key people to this (including press, participants, volunteers who helped make it happen, etc.)

- Sat 23rd public opening, then open every day from 3 to 8pm till 31st with a de-rig by the 1st.

Volunteers

- ‘Working with the public and Viero training’ workshop in early May. 3 hours. 15-30 people. These volunteers will be invited because their skills are relevant to the brief, and may also include some of the volunteers he worked with last year at the bus stop.

- Initial call out would need all the delivery dates in it so that people would know their availability right away.

- After this workshop we could pool down to about 8 committed voice collectors.

- The way it will work is that two volunteers will be paired with two professional voice collectors when they’re out on site.

- All volunteers should be able to sign up for a minimum of six shifts. They should also be available to attend the soft launch and delivery dates.

Installation Design

- TBC approximately 30 ‘voice vessel’ pods spread over the paddling pool zone. They vary in size and form from Melon size up to several awesome large suspended pods (3-4m diameter) that people can walk under. These pods have a hidden inner space and aperture, related to a shell, vase and cocoon form (see visual mood board). They will have a uniform feel and texture (as if they are from the same family), but be made up of around 6-8 groups. These groups reflect the type of vocal sound they contain. e.g. ahhhs or oohhhs, Plossives or Nasals etc.  edit/added2

- Pods distributed inside the (drained) paddling pool Zone (e.g. Blue been shape on the Google earth image) at Pickering Park.

- Light element: The pods pulse with light as they speak

- Squirts vapour as they speak. Some vapours will be perfumed.

- The Pods are triggered by people calling into them perhaps in combination with touch (if we feel it needs more localised direct interaction). There will be a one to one talk back interaction between a person calling into one and it replying with one of the bank of sampled vocal sounds it holds (in its group), then there are also further modes we are experimenting with which will for example make a ripple effect of one pod, followed by another and another (for example: from Consonant like vocalisation to Vowel like and etc), e.g. “bhh” followed “Ah!”, followed “Luh” then maybe another person finds “oooh” and then..??. Some are quite short and solo and others maybe be longer and grander like a chorus of voices. The Big Suspended Pods will carry some phat baritone bassy sounds or big choral samples. The result being something that plays with the edge of spoken language and also expression, emotion and utterance. Essentially a playful and exploratory system. Some sounds are quintessentially Hull like, others perhaps introduce a north African Arabic sound, some are abrupt and “Plossive” others warm and “mmmm| like etc..e

- They have 2 modes of operation. Autonomous and also networked together so we can potentially have a mode for fewer people and many people. e

  - Daytime: more localised operation. Night time: light element will become apparent, like it could take on a murmuration affect. If you excite the whole colony enough, they could trigger lights in surrounding trees (giving sense that this colony of voices or ‘collective voice’ has potential to have effects that ripple out beyond just this space...) e

- Distillation process happens branching out from but to one side (thus spreading the footprint of options for people to interact with), manned by volunteers. They are busy adjusting the distillation process, ‘filling’ bottles with Hull’s distilled ‘super-voice’ and giving them as special gifts to visitors once they have explored the installation and ideally contributed their own voice in exchange. (we want this to be a special thing that perhaps a family is given 1 precious vial.) e

- Need to think of ways to entertain people if we end up with queues waiting to see installation. Can we add vocal excursuses and VEARO’s (voice collectors) can be there collecting more voices? Perhaps a volunteer has one Voice pod sample they can carry about and demonstrate and talk about e

- We’ll also need front of house volunteers and potentially a freelancer to help manage them. Or maybe just a front of house manager to help manage crowds.

Budget

- We will take off app. £4699 from Thor’s budget and pay for some of the production costs ourselves

- Might need to keep cherry picker in case we need it for festooning trees with lights (but shouldn’t need for the project otherwise, as there are no street lights to interact with in this location) e

- May need an engineer to check the weight on the paddling pool – could it crack??