## Sheet1
Kaleidoscope
Project Updates
14th - 19th August
Action Point | Detail | Completed |  | Information
Check against football matches |  |  | Not yet updated | Cube in Venue's car park
Parking at Hull Fair Site | Ask HT |  | NPS: Nick Howbridge | 6 changing rooms and 1 classroom (children furthest end)
Check availability of 2 cubes | Ask JM |  | Enquired with JM + RB | 720 seats ?
How big are they? |  |  | Enquired with JM + RB | Tenser to snake around FOH and keep queueing audience inside in front of reception
Hull-based carpenter/floorer to Mark and Wilky | Check suppliers database. Ask MM |  | GeoTech | 2x banners at main entrance
Who did Re-Rooted pipe and drape? | Ask MM |  | HPSS
How many battery LEDs do we have? | Ask CC. For lighting audience entrance end of drapes
BTO FOH staff rates | Find contract or ask TF |  | £8.75 per hour | Lis Poulsom, Katie McCreaddie, Rachael Long, Jillian Arnold, Andrew Carruthers, Beth M
Check availability of council radios | Ask JB |  | Yes. In calendar 5th August - 21st August
2x Hire car Quote for 2 weeks | Ask RC |  | Enquired with RC
Location | Staffing 14th - 19th August | Amount | Hours
Airco | FOH | 6 | 10am - 7pm
| Security | 5 | 10am - 7pm
| Volunteers | 14 | 10am - 2pm + 2pm - 7pm
Cube | FOH | 2 | 10am - 7pm
| Security | 1 | 10am - 7pm
| Volunteers | 2 | 10am - 7pm
24 Hours | Security | 1 | 5th - 19th
| Security | 1 | 13th - 19th