## DELIVERY PLAN
MONITORING & EVALUATION DELIVERY PLAN
NAME OF ORGANISATION | Hull UK City of Culture 2017 Limited
NAME OF PROJECT/EVENT | Back to Ours
MONITORING & EVALUATION
|  |  | W/C 5 DECEMBER | [6 empty] | W/C/ 12 DECEMBER | [6 empty] | W/C 19 DECEMBER | [6 empty] | W/C 26 DECEMBER | [6 empty] | W/C 2 JANUARY | [6 empty] | W/C 9 JANUARY | [6 empty] | W/C 16 JANUARY | [6 empty] | W/C 23 JANUARY | [6 empty] | W/C 30 JANUARY | [6 empty] | W/C 6 FEBRUARY | [6 empty] | W/C 13 FEBRUARY | [6 empty] | W/C 20 FEBRUARY | [6 empty] | W/C 27 FEBRUARY | [6 empty] | W/C 6 MARCH
ACTIVITY | RESPONSIBILITY | RESPONDENTS | M | T | W | T | F | Sa | Su | M | T | W | T | F | Sa | Su | M | T | W | T | F | Sa | Su | M | T | W | T | F | Sa | Su | M | T | W | T | F | Sa | Su | M | T | W | T | F | Sa | Su | M | T | W | T | F | Sa | Su | M | T | W | T | F | Sa | Su | M | T | W | T | F | Sa | Su | M | T | W | T | F | Sa | Su | M | T | W | T | F | Sa | Su | M | T | W | T | F | Sa | Su | M | T | W | T | F | Sa | Su | M | T | W | T | F | Sa | Su
PROJECT MONITORING SHEET
Creative team to complete Equal Opps Form | LY | n/a | bar: W/C 26 DECEMBER F
Commissioned artists to complete Equal Opps Form | LY | n/a | bar: W/C 26 DECEMBER F
Populate sheet with existing data | LY | n/a | bar: W/C 2 JANUARY M to W/C 2 JANUARY W
Enter data into sheet for the previous week | LY | n/a | bar: W/C 9 JANUARY M; W/C 16 JANUARY M; W/C 23 JANUARY M; W/C 30 JANUARY M
Submit completed sheet to EU | LY | n/a | bar: W/C 30 JANUARY F
FORMATIVE EVALUATION
Submit Poker Game findings to evaluators | JM | n/a | bar: W/C 30 JANUARY F
Review Poker Game findings | EU | n/a | bar: W/C 30 JANUARY F
Review Meeting Notes | EU | n/a | bar: W/C 30 JANUARY F
AUDIENCE MEASUREMENT
Box Office Season Reports | DW | n/a | bar: W/C 26 DECEMBER M
Box Office Final Reports | DW | n/a | bar: W/C 26 DECEMBER M
AUDIENCE POST-SHOW SURVEY
Source 2 x Tablets per venue | AB & DW | n/a | bar: W/C 26 DECEMBER M
Sign off audience survey | EU & LY | n/a | bar: W/C 2 JANUARY F
Install audience survey on tablets | EU & DW | n/a | bar: W/C 2 JANUARY F
Recruit Volunteers | EU & LY | Volunteers | bar: W/C 2 JANUARY F
Write brief for M&E - audience survey | AB | Event Lead, Venue Manager, Volunteers | bar: W/C 2 JANUARY F
Breif Volunteers | Venue Manager | Volunteers | bar: W/C 2 JANUARY F
Undertake audience survey fieldwork | Volunteers | Audiences | bar: W/C 2 JANUARY F
Post-show online audience survey | EU & DW | Ticket bookers for BTO | bar: W/C 2 JANUARY F
Audience Survey Data Analysis - Seasonal | External consultant | n/a | bar: W/C 2 JANUARY F
Audience Survey Evaluation Report - Seasonal | External consultant | n/a | bar: W/C 2 JANUARY F
Audience Survey Data Analysis - Final | External consultant | n/a | bar: W/C 2 JANUARY F
Audience Survey Evaluation Report - Final | External consultant | n/a | bar: W/C 2 JANUARY M to W/C 13 FEBRUARY M
SELFIE BOOTH
Source easels | AB | n/a | bar: W/C 2 JANUARY M to W/C 2 JANUARY W
Source whiteboards or chalkboards for show name | AB | n/a | bar: W/C 2 JANUARY M to W/C 2 JANUARY W
Design and source emoji masks | EU & LY | Audiences | bar: W/C 26 DECEMBER W to W/C 26 DECEMBER Su
Create Custom Hash Tags and Captions | DW, CM | n/a | bar: W/C 2 JANUARY M to W/C 2 JANUARY W
Recruit Volunteers as Personal Attendants | LY | Volunteers | bar: W/C 2 JANUARY M to W/C 2 JANUARY W
Write brief for M&E - selfie booth | AB | Event Lead, Venue Manager, Volunteers | bar: W/C 2 JANUARY M to W/C 2 JANUARY W
Brief Volunteers | Venue Manager | Volunteers | bar: W/C 2 JANUARY M to W/C 2 JANUARY W
Set Up Selfie Booth | Volunteers | n/a | bar: W/C 26 DECEMBER W to W/C 26 DECEMBER Su
Release forms for use of photos | ? | Audiences | bar: W/C 26 DECEMBER W to W/C 26 DECEMBER Su
Take photos for Hull 2017 and audience member | Volunteers | Audiences | bar: W/C 26 DECEMBER W to W/C 26 DECEMBER Su
Analysis and reporting fo all photos | External consultant | n/a | bar: W/C 26 DECEMBER W to W/C 26 DECEMBER Su
CULTURE COUNTER VOTING TUBES |  | As above
Source and purchase culture counters | AB & LM | n/a | bar: W/C 30 JANUARY T to W/C 6 FEBRUARY F
Source and purchase counter contrainers | AB & LM | n/a | bar: W/C 30 JANUARY T to W/C 6 FEBRUARY F
Select Key Question for Instant Poll | EU, AB & LY | Audiences | bar: W/C 30 JANUARY T to W/C 6 FEBRUARY F
Source and purchase Usherette Trays | AB & LM | n/a | bar: W/C 30 JANUARY T to W/C 6 FEBRUARY F
Write brief for M&E - post-show key question | AB | Event Lead, Venue Manager, Volunteers | bar: W/C 30 JANUARY T to W/C 6 FEBRUARY F
Brief Volunteers | Venue Manager | Volunteers | bar: W/C 30 JANUARY T to W/C 6 FEBRUARY F
Poll audiences | Volunteers | Audiences | bar: W/C 30 JANUARY T to W/C 6 FEBRUARY F
Post-Show Count of Counters | Volunteers | n/a | bar: W/C 13 FEBRUARY W
Record Post-Show Counts | Volunteers | n/a | bar: W/C 20 FEBRUARY F
AUDIENCE DEPTH INTERVIEWS (CHAT WITH NAN)
Sign off script and discussion guide for Nan | AB & EU | n/a | bar: W/C 20 FEBRUARY F
Create "Chat with Gran" schedule | EU | n/a | bar: W/C 27 FEBRUARY M to W/C 6 MARCH Su
Recruit "Gran" | RB & EU | bar: W/C 27 FEBRUARY M to W/C 6 MARCH Su
Source Props for "Chat with Gran" | AB | bar: W/C 27 FEBRUARY M to W/C 6 MARCH Su
Source recording device for "Chat with Nan" booth | AB & EU | bar: W/C 27 FEBRUARY M to W/C 6 MARCH Su
Train Gran | AB & EU | bar: W/C 27 FEBRUARY M to W/C 6 MARCH Su
Fieldwork | Hellen | bar: W/C 27 FEBRUARY M to W/C 6 MARCH Su
Code and analyse "Chat with Gran" | bar: W/C 27 FEBRUARY M to W/C 6 MARCH Su
HULL 2017 DELIVERY TEAM
Design pre-event discussion guide | Regeneris, EU, PB | n/a | bar: W/C 19 DECEMBER W to W/C 19 DECEMBER F
Deliver pre-event discussion group | Regeneris, EU, PB | n/a | bar: W/C 19 DECEMBER W to W/C 19 DECEMBER F
Season 1 debrief | Regeneris | Creative Core Team (see 'Notes' below)
Season 2 debrief | Regeneris | Creative Core Team (see 'Notes' below)
Season 3 debrief
Design end of project discussion guide
Deliver end of project discussion group
VENUE TEAMS
Design pre-event survey | Regeneris, EU, PB | n/a | bar: W/C 19 DECEMBER W to W/C 19 DECEMBER F
Design pre-event discussion guide | Regeneris, EU, PB | n/a | bar: W/C 19 DECEMBER W to W/C 19 DECEMBER F
Deliver pre-event survey | Regeneris | Creative Core Team (see 'Notes' below)
Deliver pre-event discussion group | Regeneris | Creative Core Team (see 'Notes' below)
Analysis of data
Season 1 debrief
Season 2 debrief
Season 3 debrief
Design post-event survey | Regeneris, EU, PB | n/a | bar: W/C 19 DECEMBER W to W/C 19 DECEMBER F
Design post-event discussion guide | Regeneris, EU, PB | n/a | bar: W/C 19 DECEMBER W to W/C 19 DECEMBER F
Deliver post-event survey | Regeneris | Creative Core Team (see 'Notes' below)
Deliver post-event discussion group | Regeneris | Creative Core Team (see 'Notes' below)
Analysis of data
AGENT/PROMOTER/ARTIST INTERVIEWS
Design discussion guide for Pre-event | Regeneris, EU, PB | n/a | bar: W/C 19 DECEMBER W to W/C 19 DECEMBER F
Pre-event depth interviews | Regeneris | Artists, Heritage Partners (see 'Notes' below)
Analysis of data | Regeneris | n/a
Design discussion guide for post-event | Regeneris, EU, PB | n/a | bar: W/C 19 DECEMBER W to W/C 19 DECEMBER F
Post-event depth interviews | Regeneris | Artists, Heritage Partners (see 'Notes' below)
Analysis of data | Regeneris | n/a
PEER SURVEY
Design pre-event survey | Regeneris, EU, PB | n/a | bar: W/C 19 DECEMBER W to W/C 19 DECEMBER F
Design post-event survey | Regeneris, EU, PB | n/a | bar: W/C 19 DECEMBER W to W/C 19 DECEMBER F
Pre-event Survey | Regeneris | Peer - TBC
Post-event Survey | Regeneris | Peer - TBC
Analysis of data | Regeneris | n/a
PEER DEPTH INTERVIEWS
Design discussion guide for pre-event | Regeneris, EU, PB | n/a | bar: W/C 19 DECEMBER W to W/C 19 DECEMBER F
Design discussion guide for post-event | Regeneris, EU, PB | n/a | bar: W/C 19 DECEMBER W to W/C 19 DECEMBER F
Pre-event depth interviews | Regeneris | Peer - TBC
Post-event depth interviews | Regeneris | Peer - TBC
Analysis of data | Regeneris | n/a
MEDIA & PR
Media Monitoring | AJ & Gorkana | n/a | bar: W/C/ 12 DECEMBER T to W/C 30 JANUARY Su
Media Analysis | AJ & Gorkana | n/a | bar: W/C/ 12 DECEMBER T to W/C 6 FEBRUARY F
PR Report??? | BMc & PR Company | n/a | bar: W/C 13 FEBRUARY M to W/C 13 FEBRUARY W
NOTES
Hull 2017 Delivery Team | Henri Duckworth
Lousie Yates
Tom Freeth
Carys Taverner
Lisa Mayes
James McGuire
Ian Read
Jo Charlton
Martin Atkinson
Venue - Key Staff | LY to do intro
Agents/Promoters/Artists | Hull 2017 to do intro