## Sheet1
Word / Literature
| Target | Notes / considerations | Completed
Children's Literature Festival - Hull Library Service |  | 28 June onwards?
Festival Director advertising | Sept | Michelle | Done
Festival Director interviews | Sept | Michelle | Done
FD start date agreed | Sept | Michelle
Confirm dates of festival | Sept
Confirm date of the Laureate Announcement | Sept | Emily BookTrust
Confirm Festival site/venues | Nov | based on budget work
Confirm Book Awards site/venues | Oct
Confirm Laureate Announcement Venue | Oct
Festival Steering Group set-up and first meeting | Oct | Ellen/Michelle
Publishers on board: Pan Macmillan, Walker, Waterstones* | Nov | Ellen
Facilitate sponsorship from above (and others) | Nov | Ellen/Liz
Schools, Nurseries & Children's Centres involved | Nov | Ellen/Ian
Prep draft plan based on 10-day festival | Nov | Ellen/Michelle
Prep draft budget based on 10-day festival | Oct | Ellen/Gareth
Production support required?
Production company settled
Book East Park | Nov | based on budget/other work
Book 2 x Inflatable cubes | Sept | Phil | Done
Additional funding sources identified | Oct | Ellen/Michelle
Funding applications prepped/sent | Oct | Ellen/Michelle
Hull 2017 budgetted and Greenlit | June | £20k | Done
Confirm Hull 2017 role & budget breakdown for allocation | Oct | Henri/Will/Ellen
Hull 2017 contract with CLF | Oct | Henri/Will/HCAL | in progress
CLF Project Plan & Milestones agreed | Oct | Ellen/Will
Hull2017 PID produced | June | Update
Hull 2017 Volunteers confirmed | Oct | Ellen/Volunteering
Monitoring & Evaluation in place | Oct | Ellen/Hull2017
Festival Programme confirmed | Feb
Writer Development & Prof Development Programme | Feb
Commissions Offered | Feb
Launch date set - and who announces? | Dec | Ellen/Phil/Henri (& celebrity?)
Prep draft marketing budget | Nov | Ellen/Phil?
Prep draft marketing plan | Nov | Ellen/Phil?
Web page? | Jan | Ellen/Digital?
Ticket prices agreed | Dec
Ticketting arrangements in place | March
Festival brochure published | April | Ellen/Marketing/Digital
Aarhus 39 Project / Hay Festival |  | Invite authors from here?
Make link with Juliana (A.Dir,Aarhus) & Matt Haig as conduit? |  | Ellen/Michelle
Children's Laureate Announcement - BookTrust |  | June 7th
Confirm date of announcement (also Lit Festival) | Sept | Emily
Confirm site/venue of announcement | Oct | Emily
Receive planning documents from BookTrust | Oct | Emily
Receive confirmation of support from Waterstones | Oct | Emily
Initial phone conversation with BookTrust | Aug | Jill | Done
Initial meeting with BookTrust | Sept | Emily | Done
Understand Waterstones* sponsorship of Laureate | Oct | Emily
Agree proposal for all past Laureates to come to Hull | Nov | Emily
Dolly Parton… |  | Sam
Dollywood Foundation/Imagination Library - Reading at Festival?
Penguin Group (UK) - Partners
Princess Royal… |  | Ben
Launch date set
Receive marketing plan from Booktrust
Digital activity?
Create Guest List
Invitations to Guests
BBC - Contains Strong Language Festival |  | 28 Sept to 1 Oct
Funding application to ACE submitted by Wrecking Ball Press | Done | £99k - hear outcome November | Done
Artist's Commissions agreed
BBC
Hull 2017 budgetted and Greenlit |  | £65k - £9 earmarked - incl £10k BritCouncil
Confirm Hull 2017 role & budget breakdown for allocation |  | Henri/Will/Sue - our in-kind support
Hull 2017 cooperation agreement with BBC | Oct | Henri/Will/Sue | in progress
Project Plan & Milestones agreed | Oct | Henri/Will/Sue
Budget allocated to access?
Hull2017 PID produced
Hull 2017 Volunteers confirmed
Hull 2017 Staff Support required? |  | Us? Opps team?
Monitoring & Evaluation in place
British Council Carib Poetry Slam project - we contract artists? |  | or WB invoice us?
Apples & Snakes |  | Contact for a meeting?
Audience Development Work |  | Kate Fox and/or Firm of Poets?
Community Education? |  | Phil/Ian?
Launch date set |  | Already mentioned at Sept 22 launch
Prep draft marketing budget |  | ?
Prep draft marketing plan
Web page? |  | BBC presumably
Ticket prices agreed |  | Are Apples & Snakes free? WBall events?
Ticketting arrangements in place |  | see above
Festival brochure published |  | does this apply?
Anything about festival returning to Hull in 2019, then next CoC?
National Poetry Day - Forward Foundation (part of BBC project) |  | 2016-09-28
BBC Writers Room |  | Justine Potter
Hull Truck
Word on the Street - Firm of Poets / Freedom Festival
Humber Mouth Festival - Wrecking Ball / City Arts
Two year funding agreed from ACE | Done | 72120 | Done
Two year funding agreed from Hull2017 | Done | 25000 | Done
Grant agreement for £25k agreed | in progress | Will/Ruth | in progress
Project Plan & Milestones agreed | in progress | Ruth/Shane | in progress
Hull 2017 Budget in place | in progress | Cashflow to be agreed with Shane | in progress
Budget allocated to access?
Hull2017 PID produced
Hull 2017 Volunteers confirmed
Monitoring & Evaluation in place
First Story
Reading Rooms - The Verbal - CCP Project (Big Lottery)
University of Hull
Hull Rises
The Garden
Bridge to Everywhere
Children's Laureate Conference |  | Dates set?
Freedom Festival - Spoken Word Programme
Freedom Festival & Hull 2017 project to scope | Oct | Meeting Mikey/Henri
Hull Libraries Service (excl Child's Lit Fest & Book Awards above)
Summer Reading Challenge
Under 5's Language & Literacy Development
Bookstart
Chatterbooks
Out of School Activity
World Book Day, Child's Book Week, NPD, etc
Notes / Actions from last meeting
Set-up next meeting
Overall Literary programme review
Confirm Hull 2017 role with each project
Record in Artifax
Keep colleagues updated
Clarify capacity required of Producer
Commissioning the Poet Laureate?
Ian Read's Festival of Children