## Performance Week
HULL
DEPART Tour 2017 PRODUCTION SCHEDULE_ Access to Thoresby Primary School V3
Pre-production | Access schedule to Thoresby Primary School (Production Base & Backstage for DEPART in Hull).
Tuesday, 18th April | 1700 - 2100 Rehearsal won't start until 1730. On-site evening rehearsal with performance and choir guides. If we could please have access to Thoresby Primary School ground floor hall and toilets for wet weather contingency and for access to toilets. Expecting to work with 18 to 25 people. Contact person leading rehearsal on site: Alice Lee Holland +44 07845713784
Thursday, 20th April | 1100 - 1700 Access to upper level kitchen & toilets. On-site rehearsal with 13 Northern School of Contemporary Dance dancers.
Friday, 12th May | 1700 - 2100 Rehearsal won't start until 1830. On-site evening rehearsal with choir. If we could please have access to Thoresby Primary School ground floor hall and toilets for wet weather contingency and for access to toilets. Expecting to work with around 100 people. Contact person leading rehearsal on site: Alice Lee Holland +44 07845713784
Saturday, 13th May | 0900 - 1800 Access to upper level production office. Rigging work on trees with crew.
Sunday, May 14th | 1000 - 1800 Access to upper level production office and two large halls. Site familiarisation day with 26 performers and rigging crew.
1000 - 1100 | Crew arrive on site to work on trees.
1100 - 1300 | Performers on site for a rehearsal and work on trees.
1300 - 1400 | Lunch Break
1400 - 1800 | Rehearsal on Site. All to leave school premises by 6pm.
Production week
Monday, May 15th | 0900 - 2200 Access to upper level production office.
0900 - 1300 | Crew & security to arrive on site. Site Deliveries: generator, toilets, x2 20ft containers, steel deck & sound equipment. Rigging work on trees.
1300 - 1400 | Lunch Break
1400 - 1800 | Technical set-up and works on site.
1800 - 1900 | Dinner Break
1900 - 2200 | Works on site to continue until 21.30, followed by a clear out of all movable equipment and locking that up in the production's containers stored on-site. Overnight securtiy will be given keys to the production toilets unit located by school side entrance to the General Cemetery. All crew to leave site and collect their belongings from Thoresby Primary School premises by 2200.
Tuesday, May 16th | 0900 - 0000 Access to upper level production office & 1600 - 2200 Access also to two large halls & laundry unit.
0900 - 1300 | Crew on site. Technical set-up. Rigging team & aerial performers to work on trees.
1300 - 1400 | Lunch Break
1400 - 1600 | Technical Set-up for evening's rehearsal with cast.
1400 - 1800 | All performers (except choir) & crew on site. Technical set-up with performers, i.e. Final rigging checks.
1800 - 1900 | Dinner Break / Choir to arrive on site.
1900 - 0000 | Evening rehearsal on site with CIRCA et al. All to strike the site and leave school premises by 0000.
Wednesday, May 17th | 0900 - 0000 Access to upper level production office & 1600 - 0000 Access also to two large halls & laundry unit.
0900 - 1300 | Crew on site. Technical set-up. Rigging team & aerial performers to work on trees.
1300 - 1400 | Lunch Break
1400 - 1600 | Technical Set-up for evening's rehearsal with cast.
1600 - 1800 | All performers (except choir) & crew on site. Technical set-up with performers, i.e. Final rigging checks.
1800 - 1900 | Dinner Break / Choir to arrive on site.
1900 - 0000 | Last checks and dress rehearsal at 2115. All to strike the site and leave school premises by 0000.
Thursday, May 18th | 1000 - 0000 Access to upper level production office & 1600 - 0000 Access also to two large halls & laundry unit.
1000 - 1300 | Crew & Wardrobe Assistant arrive on site. Technical set-up, checks and work on site.
1300 - 1400 | Lunch Break
1400 - 1600 | Technical set-up, checks & work on site.
1600 - 1800 | ALL cast to arrive on site & shool premises. Warm-up.
1800 - 1900 | Dinner Break
1900 - 0000 | ALL on site. Warm-up. Last checks. Show 1 at 2130. ALL to strike the site and leave school premises by 0000.
Friday, May 19th | 1000 - 0000 Access to upper level production office & 1600 - 0000 Access also to two large halls & laundry unit.
1000 - 1300 | Wardrobe Assistant arrive on site. Laundry checks & maintenance work.
1300 - 1400 | Lunch Break
1400 - 1600 | Crew arrive on site. Technical set-up, checks & work on site.
1600 - 1800 | ALL cast to arrive on site & shool premises. Warm-up.
1800 - 1900 | Dinner Break
1900 - 0000 | ALL on site. Warm-up. Last checks. Show 2 at 2130. ALL to strike the site and leave school premises by 0000.
Saturday, May 20th | 1000 - 0000 Access to upper level, laundry facilities & two large halls.
1000 - 1300 | Wardrobe Assistant arrive on site. Laundry checks & maintenance work.
1300 - 1400 | Lunch Break
1400 - 1700 | ALL cast to arrive on site & shool premises. Warm-up. Crew work on site.
1700 - 1800 | Dinner Break
1800 - 1900 | Warm-up, final checks. Show 3 at 1915
2000 - 2100 | Reset for Show 4. ALL on site. Warm-up.
2100 - 0000 | ALL on site. Last checks. Show 4 at 2130. ALL to strike the site and leave school premises by 0000.
Sunday, May 21st | 1000 - 0000 Access to upper level, laundry facilities & two large halls. 0000 - 0200 Access to upper level for the use of Production team only.
1000 - 1300 | Wardrobe Assistant arrive on site. Laundry checks & maintenance work.
1300 - 1400 | Lunch Break
1400 - 1600 | Crew arrive on site. Technical set-up, checks & work on site.
1600 - 1800 | ALL cast to arrive on site & shool premises. Warm-up.
1800 - 1900 | Dinner Break
1900 - 0000 | ALL on site. Warm-up. Last checks. Show 5 at 2130. Cast to leave school premises by 0000.
0000 - 0200 | Crew on site. Get-out. ALL to strike the site and leave school premises by 0200.
Monday, May 22nd | 0900 - 1800 Access to upper level & laundry facilities
0900 - 1300 | Crew to arrive on site. Site Pick-ups: generator, toilets, x2 20ft containers, steel deck & sound equipment. Rigging work on trees.
1300 - 1400 | Lunch Break
1400 - 1800 | Site clear-out & overall tidy.
CONTACTS: | Depart Production Manager - Simon MacColl | Telephone: 07730404809
| Depart Producer - Linda Peterkopa | Telephone: 07783541853