**CRITICAL PATH: BACK TO OURS (MAY) – POST EASTER**

|  |  |  |
| --- | --- | --- |
| **Detail** | **Date** | **Responsibility** |
| All non-programme specific copy updated | w/c 10 Apr | LM |
| Confirmation of programme | Thurs 13 Apr | Programming |
| All final copy and images received | Tues 18 Apr | Touring companies/LM |
| Round one artwork | 19-20 Apr | LM |
| First round sent to Hull 2017 | Thur 20 Apr | Bluestorm |
| Version sent to partners for approval | Thur 20 Apr | LM/Partnerships |
| Amends collated and sent back to Bluestorm | Fri 21 Apr | LM |
| Second round sent to Hull 2017 and final amends. SIGN OFF REQUIRED. | Mon 24 Apr | Bluestorm |
| Sent to print deadline | Tue 25 Apr | Bluestorm |
| Delivery of print to Lowgate House | Fri 28 Apr | Bluestorm |