## PID
Project name | We Made Ourselves Over - Blast Theory
Last updated | 2016-03-30 | [5 empty] | Objectives & metrics
[7 empty] | Metrics |  | Target |  | Forecast/actual
Related documents | [6 empty] | # audience |  | 80000 (website target)
Project plan |  |  | Risk management plan |  |  |  |  | Hull residents |  | Y
Budget |  |  | Marketing & comms plan |  |  |  |  | regional |  | Y
[8 empty] | national |  | Y
Dates | [7 empty] | international |  | Y
Project start date | 2016-06-01 |  | Project live date |  | 2017-09-01 |  |  | children (<16) |  | Y
End of Live date | 2017-12-31 |  | End of eval. date |  | 2018-03-01 |  |  | young people (16-25) |  | Y
[8 empty] | families |  | Y
Categories | [7 empty] | older people (60+) |  | Y
Type | Hull 2017 Commission |  |  | Strand |  | Blast Theory |  | self-identify as disabled |  | Y
Season | Tell the World |  |  | Digital requirements |  | Very high |  | BME |  | Y
[8 empty] | NEET |  | N
Finance | [6 empty] | # temporary jobs created |  | 0
Total project budget |  | 250000 |  |  |  |  | # freelance contracts created |  | 10 to 15
Hull 2017 contribution |  | 250000 |  |  |  |  | # participation opportunities |  | TBC
Analysis/project code(s) | [6 empty] | of which for school age |  | TBC
[7 empty] | # commissions |  | 5 TBC
[7 empty] | Objective |  | Met? | Notes
Partner with Aarhus 2017 - European Capital of Culture
People | [6 empty] | Exploring the following four key issues: • The environment and climate change • Global and local economies • New technologies, city infrastructure and civic space • Community, identity, family life and culture
Project Lead | Sam Hunt |  |  | Volunteering lead
Producer |  |  |  | Education lead |  |  | Five film produced that capture the project and the relationship between Hull and Aarhus
Assistant Producer | Hannah Williams Walton |  |  | Marketing lead
Production Manager |  |  |  | Community Eng lead |  |  | Engage a wide range of audience digitally and through the live events and film screenings
Evaluation lead
Performance, Residency & Legacy
What is the model for delivering this project? eg we will employ a creative team, we will outsource to an agency, we are contributing funding but no other resource… | [6 empty] | Performance: Summary of events, including dates, times, venues, ticketing strategy (free/paid, (un)ticketed), age guidelines (free text OR UKFC categories) etc. NB Do not duplicate information stored in Artifax.
This is a commision with Blast Theory. They will be responsible for recruiting and contracting additional staff for the project. We will provide support idenitifying and building relationships within Hull linking Blast Theory to independent researchers and development groups, establishing relationships with community and youth groups and helping to assemble a production team of local film-makers, visual artists, performers and makers for Blast Theory to involve in the delivery of the final work.
How will delivery partners be identified and procured? Refer to the procurement flowchart and note below the agreed process (A–G) for each contract. | [6 empty] | Residency: How will you realise your residency work? What opportunities will be created within the project for our education programme? How will the project help to build new audiences through engagement? Note numbers, types and duration of participation opportunities.
Blast Theory will be responsible for sourcing and contracting suppliers, delivery partners and additional members of staff.
Who are the delivery partners? (Contact & organisation name, contract status for each) | [6 empty] | Legacy: What is built into the core project that will ensure legacy?
Blast Theory, Unit 5, 20 Wellington Road Portslade Brighton BN41 1DN +44 (0) 1273 413 455 | [6 empty] | The website will be a lasting legacy from the project, along with the interactive smartphone app and the five films that will have been created.
Volunteer management: What is your expectation of volunteer requirements? (Numbers, roles, responsibilities, duration / period required) | [6 empty] | Project description (200–400 words) for use in marketing materials, on webpages etc. Note that this may be edited.
Various volunteer needs throughout the duration of the project. They will need volunteers to test early prototypes of the app at some point between June-Dec 2016. They will also need volunteers to support and possibly feature in filming between Apr – Aug 2017. There will also be volunteer needs for the period the project is live between Sept 17-Dec 17. | [6 empty] | We Made Ourselves Over is a science fiction project that takes its audiences on a journey into an imagined future. Blast Theory will work in partnership with diverse communities from Aarhus and Hull to develop a speculative vision of the world in 2097; employing writing, photography, mobile gaming and film to construct a provocative and personal set of stories from each city. We Made Ourselves Over springs from the respective histories and insights of communities in each city while drawing on the work of economists, futurologists, technologists, climate scientists and architects to frame their common challenges in the face of global migration, technical innovation and climate change. We Made Ourselves Over reflects on the capacity of people to adapt within the inevitable cycles of decay and renewal of a city, postulating a lifetime of changes that will transform the city in the coming century. Delving through time zones past and future, Blast Theory will deliver and screen a series of extraordinary films, alongside a programme of public events in each city from September to December 2017 using phone boxes, an app for smartphones and intimate face to face encounters across the city.
Version control
Date | Changes and/or approvals
1899-12-31
ACE
British Council
HLF
Treasury
University of Hull
Big Lottery
Health
Spirit of 2012
Trusts & Foundations
Key funders
Note on Q17: Direct employee of Hull 2017 or partner organisation
Note on Q18: Including creative teams etc

## Option sets
Status | Type | Strand | Season | Digital | Y/N
Completed | Hull 2017 Production | 365 Grant Fund | Made in Hull | Very high | Y
Draft | Hull 2017 Commission | Blast Theory | Roots & Routes | High | N
Pending | Co-commission | Caravan of Love | Freedom | Medium
| Funded (strategic partner) | Circus | Tell the World | Low
| Funded (presenting) | Codhead | Curtain Raisers
| Grant-funded | Curtain Raiser 2016 | Thru 2017
| Non-funded (strategic partner) | Dance | Post-2017
| Non-funded (presenting) | Digital commission | n/a
| Non-artistic | Film
Freedom Festival
Fuerza Bruta
Hull 2017 @ New Theatre
Hull Truck
Humber St Arts Programme
Land of Green Ginger
Literature commission
Look Up
Museums / Libraries service
Music
Neighbourhood Network
New Years Eve
PRS New Music Biennial
Radio 1 Big Weekend
Singing City
Site-specific theatre
Slung Low
Street animation
Theatre Sector dev & commissions
Turner Prize