16. PLANNING SCHEDULE

| Date | Action | Completed |
| --- | --- | --- |
| 23/2/2017 | First Site visit | Completed |
| 10/3/2017 | Second site visit and Marquee planning | Completed |
| 15/3/2017 | Deposit on Zeebedees paid | Completed |
| 26/3/2017 | DJ and External sound system booked |  |
| 29/3/2017 | Colours ordered |  |
| 29/3/2017 | Volunteers course attended | Booked on the 26/4/17 |
| 1/4/2017 | Tenders to be sent for Food stalls | Meeting arranged on the 15/4/17 |
| 5/4/2017 | Marquees and washing facilities contract awarded |  |
| 15/4/2017 | Schools contacted |  |
| 15/4/17 | Poster printing Wrist band |  |
| 15/4/2017 | Food contracts awarded |  |
| 20/4/2017 | Cleaning contract awarded and barriers ordered |  |
| 20/4/2017 | Publicity documents posted at surgeries etc |  |
| 21/4/2017 | Further site visit with successful contract holders |  |
| 26/4/2017 | Stage programme finalised |  |
| 15/5/2017 | Site visit with all participants and volunteers |  |
| 28/5/2017 | After 6pm Set up |  |
| 29/5/2017 | EVENT |  |

17. CONTACT DETAILS

Email: HERHCA2014@gmail.com,

TEL numbers Navin Mobile……….., Hiten Mobile 07545472876, Uma Mobile………, Tapan Mobile …………. Sona Mobile……. Shakti Mobile……………